## README
Enterprise project portfolio dataset
Source workbook for the portfolio web app. Twelve related tables, one per sheet, all joined on stable IDs.
How to read it
Blue text | Inputs. Safe to edit; the app and every formula update from them.
Green text | Lookups pulled from another table by ID (INDEX/MATCH).
Black text | Calculated. Do not overwrite; change the inputs or Settings instead.
Yellow fill | Key assumptions in Settings (RAG thresholds, contingency, as-of date).
Tables
tbl_Projects | One row per project. Contract, schedule, earned value (EV, PV, CPI, SPI, EAC), margin, cash and RAG status.
tbl_Resources | People, rates, capacity and live utilization.
tbl_Allocations | Who is assigned to which project, when, and at what %. Planned vs actual hours.
tbl_Estimates | Effort estimates by phase. v1 Baseline for all; v2 Re-forecast where a project was re-planned.
tbl_Budget | Approved budget by project and cost category, with burn against actuals.
tbl_Actuals | Monthly cost ledger: timesheets, supplier invoices, expenses.
tbl_Milestones | Five milestones per project; Fixed Price milestones trigger billing.
tbl_Invoices | Invoices raised, payment status and aging.
tbl_RAID | Risks, issues, assumptions and dependencies with scoring and exposure.
tbl_ChangeRequests | Scope and budget changes. Only Approved CRs flow into project value and budget.
tbl_Snapshots | Month-end history (Jan-Aug 2026) for trend charts. Append-only static values.
tbl_Clients | Client accounts and payment terms.
tbl_KPIs / roll-ups | Summary sheet: headline KPIs with drill targets, portfolio roll-up and monthly trend.
tbl_Settings | Thresholds and the AsOfDate. Named ranges make formulas readable (e.g. RAG_CostRed).
Relationships
ProjectID | Projects -> Allocations, Estimates, Budget, Actuals, Milestones, Invoices, RAID, ChangeRequests, Snapshots
EmployeeID | Resources -> Allocations, Actuals, Projects.ProjectManagerID, RAID.OwnerID, ChangeRequests.RaisedByID
ClientID | Clients -> Projects (Invoices reach Clients through Projects)
MilestoneID | Milestones -> Invoices (Fixed Price billing)
Built-in test scenarios
Healthy | P-1001, P-1004, P-1007, P-1009, P-1011, P-1012, P-1014, P-1016 - on budget and on time.
Cost overrun | P-1002 (severe - margin now Red), P-1013 (mild) - burning budget faster than progress.
Schedule slip | P-1003 (late), P-1010 (past baseline end, still open).
Everything at risk | P-1005, P-1017 (P-1017 forecasts a negative margin).
Margin squeeze | P-1006 (margin Amber). P-1015 has a CR that costs more than it earns but is still Green - a leading indicator to watch in trends.
Other states | P-1018 to P-1020 Completed (P-1019 finished 6 weeks late and over budget), P-1021 On Hold, P-1022 to P-1024 Planned.
People | A handful of people are overallocated (>100%) and some sit on the bench, to exercise the resource heatmap.
Cash | Aurora Retail and Bluewater Municipal have disputed invoices and Harbourview pays late, so every aging bucket is populated.
For the app
Read tables by name | Read each tbl_* by name, not by sheet or cell range, so inserting rows or moving columns never breaks the sync.
AsOfDate | Fixed at 2026-09-11 so results are reproducible. Set it to =TODAY() for live use.
Formula results | Calculated values (EAC, RAG, HealthScore) are computed in the workbook, so the app can display them directly or recompute them itself.
Data volume | 24 projects, 63 people, ~1,400 ledger lines, ~100 invoices, ~70 RAID items.

## Summary
Portfolio summary
As of 11 Sep 2026 ¦ actuals to 31 Aug 2026
Every value is a live formula. DrillTarget describes the filter the app should open when the number is tapped.
KPI | Value | DrillTarget
Active projects | 17 | Projects ¦ Status = Active
Active contract value | 16200000 | Projects ¦ Status = Active ¦ sort CurrentContractValue desc
Active budget (BAC) | 10875900 | Projects ¦ Status = Active
Actual cost to date (active) | 7204719.12 | Actuals ¦ Project.Status = Active
Estimate at completion (active) | 11145599.5472 | Projects ¦ Status = Active ¦ sort VAC asc
Forecast margin % (active) | 31.2% | Projects ¦ Status = Active ¦ sort ForecastMarginPct asc
Target margin % (weighted) | 36.28% | Projects ¦ Status = Active
Red projects | 4 | Projects ¦ Status = Active AND OverallRAG = Red
Amber projects | 4 | Projects ¦ Status = Active AND OverallRAG = Amber
Green projects | 9 | Projects ¦ Status = Active AND OverallRAG = Green
Average health score | 74.1176 | Projects ¦ Status = Active ¦ sort HealthScore asc
Average schedule slip (days) | 17.9412 | Projects ¦ Status = Active ¦ sort ScheduleSlipDays desc
Overallocated people | 6 | Resources ¦ UtilizationStatus = Overallocated
Under-utilized people | 23 | Resources ¦ UtilizationStatus = Under-utilized
Bench capacity (hrs/week) | 720 | Resources ¦ AvailableHrsPerWeek > 0
Outstanding receivables | 1937308.92 | Invoices ¦ Status <> Paid
Overdue receivables | 789503.99 | Invoices ¦ Status = Overdue ¦ sort DaysOverdue desc
Unbilled WIP (active) | 2117514.41 | Projects ¦ Status = Active ¦ sort UnbilledWIP desc
Open critical risks | 6 | RAID ¦ Severity = Critical AND Status <> Closed
Open risk exposure (weighted) | 1632400 | RAID ¦ Status <> Closed ¦ sort ExpectedExposure desc
Pending change requests | 8 | ChangeRequests ¦ IsPending = Yes
Pending CR cost impact | 402000 | ChangeRequests ¦ IsPending = Yes
Overdue milestones | 4 | Milestones ¦ Status = Overdue
By portfolio (active projects)
Portfolio | ActiveProjects | ContractValue | Budget | ActualCost | EAC | ForecastMarginPct | RedProjects | AvgHealthScore
Customer Experience | 4 | 3345000 | 2264800 | 2077124.5 | 2459104.5075 | 26.48% | 2 | 50.75
Data & AI | 4 | 3765000 | 2449000 | 1294670.08 | 2569291.105 | 31.76% | 1 | 70.75
Cloud & Infrastructure | 3 | 3370000 | 2218900 | 1631497.16 | 2165651.4239 | 35.74% | 0 | 89
Digital Transformation | 3 | 3945000 | 2739700 | 1489505.24 | 2677873.0149 | 32.12% | 0 | 89.6667
Operational Excellence | 3 | 1775000 | 1203500 | 711922.14 | 1273679.496 | 28.24% | 1 | 79.3333
Monthly trend (all projects)
MonthEnd | LabourCost | NonLabourCost | TotalCost | HoursLogged | BillableValue | Invoiced | Collected
2025-09-30 | 226537.33 | 60878.79 | 287416.12 | 2508.1 | 440100 | 222055.56 | 124000
2025-10-31 | 308954.55 | 60021.69 | 368976.24 | 3627.6 | 589236.5 | 327691.25 | 399635.69
2025-11-30 | 338524.28 | 113878.9 | 452403.18 | 3956.9 | 648146.5 | 287739.67 | 161111.12
2025-12-31 | 451604.36 | 76822.19 | 528426.55 | 5293.6 | 872226.5 | 1143552.15 | 528868.46
2026-01-31 | 497834.41 | 87184.61 | 585019.02 | 5871.3 | 950566 | 530581.74 | 848791.2
2026-02-28 | 569847.6 | 107260.81 | 677108.41 | 6692.9 | 1094059 | 824162.77 | 600753.08
2026-03-31 | 715100.43 | 142395.94 | 857496.37 | 8495.3 | 1375508 | 734835.08 | 890179.04
2026-04-30 | 755200.62 | 205185.93 | 960386.55 | 8986.2 | 1450093 | 922901.46 | 412835.19
2026-05-31 | 721440.5 | 156690.34 | 878130.84 | 8546.1 | 1379447.5 | 1067186.06 | 1270401.46
2026-06-30 | 746624.31 | 151714.79 | 898339.1 | 8801.9 | 1443917.5 | 1331587.49 | 670630.5
2026-07-31 | 767116.61 | 154180.86 | 921297.47 | 9005.7 | 1478260.5 | 1627762.79 | 1403118.79
2026-08-31 | 709187.36 | 153370.12 | 862557.48 | 8321.5 | 1365848.5 | 721864.92 | 765692.15
Formulas:
ForecastMarginPct = SUMIFS(Invoices!$F2:F2000,Invoices!$D2:D2000,">"&EOMONTH([KPI],-1),Invoices!$D2:D2000,"<="&[KPI])
RedProjects = SUMIFS(Invoices!$F2:F2000,Invoices!$G2:G2000,">"&EOMONTH([KPI],-1),Invoices!$G2:G2000,"<="&[KPI])

## Projects
ProjectID | ProjectName | ClientID | ClientName | Portfolio | BusinessUnit | ProjectManagerID | ProjectManager | ExecutiveSponsor | Status | Phase | Priority | ContractType | StrategicScore | BaselineStart | BaselineEnd | ForecastEnd | OriginalContractValue | TargetMarginPct | PctComplete | LastStatusUpdate | ApprovedCRRevenue | CurrentContractValue | BaselineBudget | ApprovedCRCost | CurrentBudget | ActualHours | ActualCost | ElapsedPct | EarnedValue | PlannedValue | CPI | SPI | EAC | ETC | VAC | BudgetBurnPct | ForecastMarginAmt | ForecastMarginPct | MarginVsTarget | ScheduleSlipDays | DaysRemaining | InvoicedToDate | CollectedToDate | UnbilledWIP | OpenRisks | OpenIssues | OpenRiskExposure | PendingCRs | TeamSize | NextMilestoneDate | CostRAG | ScheduleRAG | MarginRAG | OverallRAG | HealthScore
P-1001 | Patient Portal Modernization | C-101 | Northgate Health Network | Customer Experience | Health & Public | E-0003 | Aisha Tremblay | Dr. Anne Keller | Active | Test & Deploy | P2 | Fixed Price | 7 | 2025-11-03 | 2026-10-30 | 2026-11-03 | 1100000 | 34% | 87% | 2026-09-07 | 35000 | 1135000 | 726500 | 22000 | 748500 | 5585 | 569689.28 | 86.43% | 651195 | 646903.0471 | 1.1431 | 1.0066 | 654815.2644 | 85125.9844 | 93684.7356 | 76.11% | 480184.7356 | 42.31% | 8.307% | 4 | 53 | 660000 | 660000 | 327450 | 0 | 0 | 0 | 0 | 4 | 2026-09-28 | Green | Green | Green | Green | 98
P-1002 | Claims Automation Engine | C-102 | Crestline Insurance | Operational Excellence | Financial Services | E-0004 | Liam Roy | Robert Lindqvist | Active | Execute | P1 | Fixed Price | 7 | 2026-01-12 | 2026-12-18 | 2027-01-04 | 685000 | 32% | 57% | 2026-09-06 | 85000 | 770000 | 466100 | 70000 | 536100 | 4086.4 | 382554.58 | 71.18% | 305577 | 381577.0588 | 0.79878 | 0.80083 | 671148.386 | 288593.806 | -135048.386 | 71.36% | 98851.614 | 12.84% | -19.16% | 17 | 115 | 205500 | 205500 | 233400 | 3 | 0 | 105800 | 1 | 6 | 2026-09-04 | Amber | Amber | Red | Red | 43
P-1003 | Enterprise Data Lakehouse | C-103 | Maple Ridge Financial | Data & AI | Financial Services | E-0005 | Mei Fraser | Janet Osei | Active | Execute | P3 | Time & Materials | 10 | 2025-09-08 | 2026-11-27 | 2027-01-07 | 1165000 | 42% | 66% | 2026-09-05 | 180000 | 1345000 | 769600 | 110000 | 879600 | 5722.4 | 614808.15 | 82.7% | 580536 | 727399.5506 | 0.94426 | 0.7981 | 931527.5 | 316719.35 | -51927.5 | 69.9% | 413472.5 | 30.74% | -11.26% | 41 | 118 | 1061258.45 | 875084.78 | -173558.45 | 2 | 0 | 108800 | 1 | 5 | 2026-08-29 | Green | Amber | Amber | Amber | 61
P-1004 | Cloud Migration Wave 2 | C-104 | Harbourview Logistics | Cloud & Infrastructure | Industrial | E-0006 | Noah Rahimi | Paul Moreau | Active | Execute | P1 | Fixed Price | 6 | 2026-02-02 | 2027-01-29 | 2027-02-04 | 1155000 | 36% | 61% | 2026-09-04 | 0 | 1155000 | 738500 | 0 | 738500 | 2972.5 | 440837.72 | 61.22% | 450485 | 452101.108 | 1.0219 | 0.99643 | 722684.7869 | 281847.0669 | 15815.2131 | 59.69% | 432315.2131 | 37.43% | 1.43% | 6 | 146 | 346500 | 346500 | 358050 | 0 | 1 | 65400 | 1 | 4 | 2026-10-15 | Green | Green | Green | Green | 98
P-1005 | Fraud Detection ML Platform | C-105 | Ironbridge Capital | Data & AI | Financial Services | E-0007 | Fatima Cohen | Karen Whitfield | Active | Execute | P1 | Fixed Price | 5 | 2026-03-02 | 2027-02-26 | 2027-05-03 | 740000 | 38% | 40% | 2026-09-08 | 120000 | 860000 | 459200 | 95000 | 554200 | 2942.1 | 289303.7 | 53.46% | 221680 | 296289.7507 | 0.76625 | 0.74819 | 723259.25 | 433955.55 | -169059.25 | 52.2% | 136740.75 | 15.9% | -22.1% | 66 | 234 | 222000 | 222000 | 122000 | 2 | 1 | 337800 | 2 | 6 | 2026-12-21 | Amber | Red | Amber | Red | 22
P-1006 | Omnichannel Commerce Replatform | C-106 | Aurora Retail Group | Customer Experience | Consumer | E-0009 | Olivia Silva | Luc Bergeron | Active | Test & Deploy | P2 | Fixed Price | 7 | 2025-10-06 | 2026-09-25 | 2026-10-05 | 940000 | 38% | 92% | 2026-09-07 | 40000 | 980000 | 582300 | 48000 | 630300 | 7769.4 | 622397.49 | 96.05% | 579876 | 605372.8814 | 0.93168 | 0.95788 | 676519.0109 | 54121.5209 | -46219.0109 | 98.75% | 303480.9891 | 30.97% | -7.033% | 10 | 24 | 752000 | 282000 | 149600 | 0 | 1 | 21000 | 0 | 4 | 2026-10-05 | Green | Green | Amber | Amber | 75
P-1007 | Student Information System Upgrade | C-107 | Pinecrest University | Digital Transformation | Health & Public | E-0008 | Ethan Park | Prof. Ellen Shaw | Active | Execute | P1 | Fixed Price | 10 | 2026-04-06 | 2027-03-26 | 2027-03-29 | 970000 | 34% | 43% | 2026-09-06 | 0 | 970000 | 639400 | 0 | 639400 | 2307 | 249953.93 | 44.63% | 274942 | 285381.9209 | 1.1 | 0.96342 | 581288.2093 | 331334.2793 | 58111.7907 | 39.09% | 388711.7907 | 40.07% | 6.073% | 3 | 199 | 291000 | 97000 | 126100 | 2 | 0 | 22800 | 1 | 5 | 2026-12-10 | Green | Green | Green | Green | 99
P-1008 | Network Operations Centre Refresh | C-108 | Summit Telecom | Cloud & Infrastructure | Industrial | E-0010 | Arjun Baptiste | Trevor Nakamura | Active | Test & Deploy | P2 | Time & Materials | 9 | 2026-01-05 | 2026-10-16 | 2026-11-02 | 710000 | 42% | 85% | 2026-09-05 | 55000 | 765000 | 498500 | 38000 | 536500 | 3581.3 | 464449.86 | 87.68% | 456025 | 470382.0423 | 0.98186 | 0.96948 | 546411.6 | 81961.74 | -9911.6 | 86.57% | 218588.4 | 28.57% | -13.43% | 17 | 52 | 716418.97 | 639535.85 | -66168.97 | 1 | 0 | 6000 | 0 | 4 | 2026-10-01 | Green | Amber | Amber | Amber | 71
P-1009 | Smart Factory IoT Pilot | C-109 | Granite Manufacturing | Operational Excellence | Industrial | E-0005 | Mei Fraser | Greg Kowalski | Active | Execute | P2 | Fixed Price | 10 | 2026-05-04 | 2026-12-11 | 2026-12-14 | 535000 | 36% | 50% | 2026-09-04 | 0 | 535000 | 342700 | 0 | 342700 | 1798 | 160755.53 | 58.82% | 171350 | 201588.2353 | 1.0659 | 0.85 | 321511.06 | 160755.53 | 21188.94 | 46.91% | 213488.94 | 39.9% | 3.904% | 3 | 94 | 160500 | 160500 | 107000 | 1 | 1 | 70600 | 0 | 6 | 2026-10-06 | Green | Green | Green | Green | 99
P-1010 | 311 Citizen Services App | C-110 | Bluewater Municipal Services | Customer Experience | Health & Public | E-0007 | Fatima Cohen | Mayor's Office - D. Price | Active | Test & Deploy | P2 | Fixed Price | 10 | 2025-12-01 | 2026-08-28 | 2026-10-16 | 735000 | 38% | 86% | 2026-09-08 | 30000 | 765000 | 455000 | 42000 | 497000 | 5522.3 | 513842.3 | 100% | 427420 | 497000 | 0.83181 | 0.86 | 597491.0465 | 83648.7465 | -100491.0465 | 103.4% | 167508.9535 | 21.9% | -16.1% | 49 | 35 | 441000 | 220500 | 216900 | 2 | 1 | 286400 | 0 | 4 | 2026-09-02 | Amber | Red | Amber | Red | 30
P-1011 | Clinical Trials Data Hub | C-111 | Evergreen Pharma | Data & AI | Health & Public | E-0006 | Noah Rahimi | Dr. Mira Castellano | Active | Execute | P3 | Time & Materials | 6 | 2026-02-16 | 2027-04-30 | 2027-04-30 | 975000 | 42% | 42% | 2026-09-07 | 75000 | 1050000 | 620700 | 48000 | 668700 | 2296.3 | 248297.41 | 47.26% | 280854 | 316029.4521 | 1.1311 | 0.8887 | 591184.3095 | 342886.8995 | 77515.6905 | 37.13% | 458815.6905 | 43.7% | 1.697% | 0 | 231 | 415431.38 | 263059.05 | 25568.62 | 1 | 0 | 25200 | 0 | 6 | 2026-12-18 | Green | Green | Green | Green | 100
P-1012 | Grid Analytics Dashboard | C-112 | Lakeshore Energy | Data & AI | Industrial | E-0010 | Arjun Baptiste | Alan Fortier | Active | Execute | P2 | Fixed Price | 5 | 2026-06-01 | 2026-12-18 | 2026-12-18 | 510000 | 32% | 44% | 2026-09-06 | 0 | 510000 | 346500 | 0 | 346500 | 1289.2 | 142260.82 | 51% | 152460 | 176715 | 1.0717 | 0.86275 | 323320.0455 | 181059.2255 | 23179.9545 | 41.06% | 186679.9545 | 36.6% | 4.604% | 0 | 98 | 153000 | 153000 | 71400 | 0 | 0 | 0 | 0 | 6 | 2026-10-19 | Green | Green | Green | Green | 100
P-1013 | Core Banking API Layer | C-103 | Maple Ridge Financial | Digital Transformation | Financial Services | E-0004 | Liam Roy | Janet Osei | Active | Test & Deploy | P3 | Fixed Price | 9 | 2025-08-04 | 2026-10-30 | 2026-11-16 | 1415000 | 34% | 82% | 2026-09-05 | 95000 | 1510000 | 934500 | 88000 | 1022500 | 9097.1 | 899800.48 | 89.16% | 838450 | 911653.7611 | 0.93182 | 0.9197 | 1097317.6585 | 197517.1785 | -74817.6585 | 88% | 412682.3415 | 27.33% | -6.67% | 17 | 66 | 849000 | 849000 | 389200 | 1 | 0 | 9000 | 1 | 6 | 2026-09-28 | Green | Amber | Amber | Amber | 74
P-1014 | Managed Cloud Operations | C-104 | Harbourview Logistics | Cloud & Infrastructure | Industrial | E-0008 | Ethan Park | Paul Moreau | Active | Test & Deploy | P2 | Retainer | 8 | 2025-07-01 | 2026-12-31 | 2027-01-04 | 1450000 | 35% | 81% | 2026-09-04 | 0 | 1450000 | 943900 | 0 | 943900 | 5350.9 | 726209.58 | 79.74% | 764559 | 752708.5766 | 1.0528 | 1.0157 | 896555.037 | 170345.457 | 47344.963 | 76.94% | 553444.963 | 38.17% | 3.169% | 4 | 115 | 1127777.84 | 886111.16 | 46722.16 | 0 | 2 | 55000 | 0 | 4 | 2026-11-09 | Green | Green | Green | Green | 98
P-1015 | Policy Admin Consolidation | C-102 | Crestline Insurance | Digital Transformation | Financial Services | E-0009 | Olivia Silva | Robert Lindqvist | Active | Execute | P2 | Fixed Price | 6 | 2026-03-16 | 2027-06-25 | 2027-07-05 | 1315000 | 32% | 34% | 2026-09-08 | 150000 | 1465000 | 892800 | 185000 | 1077800 | 3253.7 | 339750.83 | 38.41% | 366452 | 414004.721 | 1.0786 | 0.88514 | 999267.1471 | 659516.3171 | 78532.8529 | 31.52% | 465732.8529 | 31.79% | -0.2094% | 10 | 297 | 394500 | 394500 | 103600 | 2 | 0 | 29400 | 0 | 5 | 2027-02-11 | Green | Green | Green | Green | 96
P-1016 | Warehouse Robotics Integration | C-104 | Harbourview Logistics | Operational Excellence | Industrial | E-0003 | Aisha Tremblay | Susan Tran | Active | Execute | P2 | Time & Materials | 10 | 2026-04-13 | 2026-11-20 | 2026-11-23 | 405000 | 42% | 60% | 2026-09-07 | 65000 | 470000 | 283700 | 41000 | 324700 | 1553 | 168612.03 | 68.33% | 194820 | 221853.8462 | 1.1554 | 0.87815 | 281020.05 | 112408.02 | 43679.95 | 51.93% | 188979.95 | 40.21% | -1.792% | 3 | 73 | 248248.95 | 85035.83 | 33751.05 | 1 | 0 | 31800 | 0 | 6 | 2026-09-15 | Green | Green | Green | Green | 96
P-1017 | Loyalty Program Relaunch | C-106 | Aurora Retail Group | Customer Experience | Consumer | E-0005 | Mei Fraser | Luc Bergeron | Active | Execute | P1 | Fixed Price | 5 | 2026-01-19 | 2026-09-30 | 2026-11-24 | 465000 | 30% | 70% | 2026-09-06 | 0 | 465000 | 324000 | 65000 | 389000 | 4351.8 | 371195.43 | 92.52% | 272300 | 359901.5748 | 0.73358 | 0.7566 | 530279.1857 | 159083.7557 | -141279.1857 | 95.42% | -65279.1857 | -14.04% | -44.04% | 55 | 74 | 279000 | 46500 | 46500 | 3 | 1 | 388400 | 1 | 4 | 2026-09-05 | Red | Red | Red | Red | 0
P-1018 | Cybersecurity Posture Assessment | C-108 | Summit Telecom | Cloud & Infrastructure | Industrial | E-0006 | Noah Rahimi | Trevor Nakamura | Completed | Close | P2 | Fixed Price | 6 | 2025-06-02 | 2025-12-19 | 2025-12-19 | 620000 | 32% | 100% | 2025-12-19 | 0 | 620000 | 421900 | 0 | 421900 | 2971.4 | 386550.33 | 100% | 421900 | 421900 | 1.0914 | 1 | 386550.33 | 0 | 35349.67 | 91.62% | 233449.67 | 37.65% | 5.653% | 0 | 0 | 620000 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 |  | Green | Green | Green | Green | 100
P-1019 | HR Self-Service Portal | C-107 | Pinecrest University | Digital Transformation | Health & Public | E-0010 | Arjun Baptiste | Prof. Ellen Shaw | Completed | Close | P1 | Fixed Price | 9 | 2025-05-05 | 2026-02-27 | 2026-04-10 | 985000 | 38% | 100% | 2026-04-10 | 60000 | 1045000 | 609200 | 52000 | 661200 | 7207.3 | 699825.98 | 100% | 661200 | 661200 | 0.94481 | 1 | 699825.98 | 0 | -38625.98 | 105.8% | 345174.02 | 33.03% | -4.969% | 42 | 0 | 985000 | 985000 | 60000 | 0 | 0 | 0 | 0 | 0 |  | Green | Amber | Green | Amber | 67
P-1020 | Demand Forecasting Model | C-109 | Granite Manufacturing | Data & AI | Industrial | E-0006 | Noah Rahimi | Greg Kowalski | Completed | Close | P1 | Time & Materials | 9 | 2025-10-13 | 2026-05-29 | 2026-06-01 | 590000 | 42% | 100% | 2026-06-01 | 0 | 590000 | 412900 | 0 | 412900 | 3546.4 | 376556.9 | 100% | 412900 | 412900 | 1.0965 | 1 | 376556.9 | 0 | 36343.1 | 91.2% | 213443.1 | 36.18% | -5.823% | 3 | 0 | 575520.34 | 575520.34 | 14479.66 | 0 | 0 | 0 | 0 | 0 |  | Green | Green | Amber | Amber | 90
P-1021 | Field Service Mobile App | C-112 | Lakeshore Energy | Operational Excellence | Industrial | E-0010 | Arjun Baptiste | Alan Fortier | On Hold | Execute | P1 | Fixed Price | 7 | 2026-02-09 | 2026-12-04 | 2027-03-04 | 625000 | 36% | 42% | 2026-07-10 | 0 | 625000 | 398600 | 0 | 398600 | 1962 | 183595.87 | 71.81% | 167412 | 286242.953 | 0.91185 | 0.58486 | 437133.0238 | 253537.1538 | -38533.0238 | 46.06% | 187866.9762 | 30.06% | -5.941% | 90 | 174 | 187500 | 187500 | 75000 | 1 | 0 | 51000 | 0 | 0 | 2026-10-30 | Green | Red | Amber | Red | 49
P-1022 | Regulatory Reporting Automation | C-105 | Ironbridge Capital | Operational Excellence | Financial Services | E-0003 | Aisha Tremblay | Karen Whitfield | Planned | Initiate | P2 | Fixed Price | 9 | 2026-10-05 | 2027-05-28 | 2027-05-28 | 515000 | 34% | 0% | 2026-08-20 | 0 | 515000 | 340500 | 0 | 340500 | 0 | 0 | 0% | 0 | 0 | 1 | 1 | 340500 | 340500 | 0 | 0% | 174500 | 33.88% | -0.1165% | 0 | 259 | 0 | 0 | 0 | 1 | 0 | 18000 | 0 | 0 | 2026-10-28 | N/A | N/A | N/A | N/A
P-1023 | GenAI Knowledge Assistant | C-111 | Evergreen Pharma | Data & AI | Health & Public | E-0004 | Liam Roy | Dr. Mira Castellano | Planned | Initiate | P2 | Time & Materials | 8 | 2026-11-02 | 2027-06-25 | 2027-06-25 | 520000 | 42% | 0% | 2026-08-19 | 0 | 520000 | 340000 | 0 | 340000 | 0 | 0 | 0% | 0 | 0 | 1 | 1 | 340000 | 340000 | 0 | 0% | 180000 | 34.62% | -7.385% | 0 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-11-25 | N/A | N/A | N/A | N/A
P-1024 | Municipal Asset Management | C-110 | Bluewater Municipal Services | Digital Transformation | Health & Public | E-0005 | Mei Fraser | Mayor's Office - D. Price | Planned | Initiate | P2 | Fixed Price | 9 | 2027-01-11 | 2027-10-29 | 2027-10-29 | 1090000 | 36% | 0% | 2026-08-18 | 0 | 1090000 | 698500 | 0 | 698500 | 0 | 0 | 0% | 0 | 0 | 1 | 1 | 698500 | 698500 | 0 | 0% | 391500 | 35.92% | -0.08257% | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2027-02-09 | N/A | N/A | N/A | N/A
Formulas:
NextMilestoneDate = IF(COUNTIFS(Milestones!$B2:B2000,[ProjectID],Milestones!$L2:L2000,"<>Completed")=0,"",MINIFS(Milestones!$F2:F2000,Milestones!$B2:B2000,[ProjectID],Milestones!$L2:L2000,"<>Completed"))

## Resources
EmployeeID | FullName | Role | Department | Level | Location | EmploymentType | CostRateHr | BillRateHr | WeeklyCapacityHrs | ManagerID | ManagerName | PrimarySkill | StartDate | CurrentAllocationPct | ActiveAssignments | AvailableHrsPerWeek | UtilizationStatus | HoursLoggedYTD | BillableHoursYTD | BillableRatioYTD
E-0001 | Helena Marsh | Director, Delivery | PMO | L7 | Toronto | FTE | 135 | 0 | 0 |  |  | Portfolio governance | 2016-03-07 | 0% | 0 | 0 | Non-assignable | 0 | 0 | 0%
E-0002 | Gordon Achebe | Director, Engineering | Engineering | L7 | Toronto | FTE | 140 | 0 | 0 |  |  | Engineering leadership | 2017-09-11 | 0% | 0 | 0 | Non-assignable | 0 | 0 | 0%
E-0003 | Aisha Tremblay | Project Manager | PMO | L6 | Toronto | FTE | 102.08 | 205 | 40 | E-0001 | Helena Marsh | Stakeholder mgmt | 2022-02-22 | 75% | 2 | 10 | Healthy | 876.7 | 673.1 | 76.78%
E-0004 | Liam Roy | Project Manager | PMO | L6 | Ottawa | FTE | 102.08 | 205 | 40 | E-0003 | Aisha Tremblay | Stakeholder mgmt | 2017-10-25 | 75% | 2 | 10 | Healthy | 1358.1 | 1358.1 | 100%
E-0005 | Mei Fraser | Project Manager | PMO | L2 | Remote | FTE | 74.8 | 150 | 40 | E-0003 | Aisha Tremblay | Stakeholder mgmt | 2023-11-26 | 125% | 3 | 0 | Overallocated | 1621.1 | 1248.4 | 77.01%
E-0006 | Noah Rahimi | Project Manager | PMO | L4 | Vancouver | FTE | 88 | 175 | 40 | E-0003 | Aisha Tremblay | Stakeholder mgmt | 2020-08-02 | 50% | 2 | 20 | Under-utilized | 1000.5 | 303.8 | 30.36%
E-0007 | Fatima Cohen | Project Manager | PMO | L6 | Toronto | FTE | 102.08 | 205 | 40 | E-0003 | Aisha Tremblay | PRINCE2 | 2017-10-13 | 75% | 2 | 10 | Healthy | 1229.3 | 1229.3 | 100%
E-0008 | Ethan Park | Project Manager | PMO | L5 | Toronto | FTE | 95.04 | 190 | 40 | E-0003 | Aisha Tremblay | Agile delivery | 2023-04-25 | 75% | 2 | 10 | Healthy | 766.6 | 766.6 | 100%
E-0009 | Olivia Silva | Project Manager | PMO | L2 | Remote | FTE | 74.8 | 150 | 40 | E-0003 | Aisha Tremblay | Agile delivery | 2023-04-22 | 100% | 2 | 0 | Healthy | 1444.7 | 1444.7 | 100%
E-0010 | Arjun Baptiste | Project Manager | PMO | L4 | Toronto | FTE | 88 | 175 | 40 | E-0003 | Aisha Tremblay | Agile delivery | 2022-11-22 | 75% | 2 | 10 | Healthy | 1256.1 | 838.4 | 66.75%
E-0011 | Chloe Reyes | Solution Architect | Architecture | L6 | Mississauga | FTE | 129.92 | 260 | 40 | E-0002 | Gordon Achebe | Salesforce | 2024-12-09 | 25% | 1 | 30 | Under-utilized | 583.6 | 583.6 | 100%
E-0012 | Mateo Bianchi | Solution Architect | Architecture | L6 | Montreal | FTE | 129.92 | 260 | 40 | E-0011 | Chloe Reyes | Salesforce | 2025-10-11 | 25% | 1 | 30 | Under-utilized | 711 | 711 | 100%
E-0013 | Hana Clarke | Solution Architect | Architecture | L5 | Mississauga | FTE | 120.96 | 245 | 40 | E-0011 | Chloe Reyes | Integration | 2021-02-11 | 50% | 2 | 20 | Under-utilized | 790 | 790 | 100%
E-0014 | Lucas Okoro | Solution Architect | Architecture | L3 | Remote | FTE | 104.16 | 210 | 40 | E-0011 | Chloe Reyes | Integration | 2020-10-25 | 50% | 1 | 20 | Under-utilized | 775.1 | 775.1 | 100%
E-0015 | Zara Vasquez | Business Analyst | Delivery | L6 | Toronto | FTE | 78.88 | 160 | 40 | E-0001 | Helena Marsh | Process mapping | 2023-05-05 | 50% | 1 | 20 | Under-utilized | 976.9 | 976.9 | 100%
E-0016 | Owen Bennett | Business Analyst | Delivery | L5 | Mississauga | FTE | 73.44 | 150 | 40 | E-0015 | Zara Vasquez | Requirements | 2023-01-17 | 50% | 1 | 20 | Under-utilized | 1413 | 1413 | 100%
E-0017 | Amara Martin | Business Analyst | Delivery | L3 | Mississauga | FTE | 63.24 | 130 | 40 | E-0015 | Zara Vasquez | Requirements | 2019-10-02 | 50% | 1 | 20 | Under-utilized | 1462.2 | 1462.2 | 100%
E-0018 | Ravi Gagnon | Business Analyst | Delivery | L5 | Toronto | FTE | 73.44 | 150 | 40 | E-0015 | Zara Vasquez | Requirements | 2019-02-18 | 100% | 2 | 0 | Healthy | 1162.9 | 1162.9 | 100%
E-0019 | Emma Leblanc | Business Analyst | Delivery | L2 | Toronto | Contractor | 72.25 | 120 | 40 | E-0015 | Zara Vasquez | SQL | 2026-03-09 | 75% | 1 | 10 | Healthy | 1692.4 | 1692.4 | 100%
E-0020 | Diego Costa | UX Designer | Design | L6 | Remote | FTE | 85.84 | 175 | 40 | E-0001 | Helena Marsh | Accessibility | 2016-02-15 | 0% | 0 | 40 | Under-utilized | 605.9 | 605.9 | 100%
E-0021 | Nadia Aziz | UX Designer | Design | L3 | Toronto | FTE | 68.82 | 140 | 40 | E-0020 | Diego Costa | Research | 2019-03-20 | 0% | 0 | 40 | Under-utilized | 613.3 | 613.3 | 100%
E-0022 | Samuel Mehta | UX Designer | Design | L2 | Toronto | FTE | 62.9 | 130 | 40 | E-0020 | Diego Costa | Research | 2020-08-28 | 0% | 0 | 40 | Under-utilized | 1001.2 | 1001.2 | 100%
E-0023 | Yuki Wright | Senior Developer | Engineering | L6 | Remote | FTE | 106.72 | 215 | 40 | E-0002 | Gordon Achebe | Java | 2020-09-02 | 75% | 1 | 10 | Healthy | 994 | 994 | 100%
E-0024 | Isabel Gill | Senior Developer | Engineering | L5 | Toronto | FTE | 99.36 | 200 | 40 | E-0023 | Yuki Wright | Java | 2020-09-02 | 125% | 2 | 0 | Overallocated | 1858.1 | 1858.1 | 100%
E-0025 | Kwame Malik | Senior Developer | Engineering | L3 | Montreal | Contractor | 106.95 | 170 | 40 | E-0023 | Yuki Wright | .NET | 2026-01-03 | 100% | 2 | 0 | Healthy | 1463.8 | 1463.8 | 100%
E-0026 | Leah Haddad | Senior Developer | Engineering | L3 | Toronto | FTE | 85.56 | 170 | 40 | E-0023 | Yuki Wright | .NET | 2016-05-24 | 75% | 1 | 10 | Healthy | 2032 | 2032 | 100%
E-0027 | Omar Bose | Senior Developer | Engineering | L5 | Vancouver | FTE | 99.36 | 200 | 40 | E-0023 | Yuki Wright | React | 2021-07-13 | 125% | 2 | 0 | Overallocated | 1540.2 | 1540.2 | 100%
E-0028 | Grace Chowdhury | Senior Developer | Engineering | L3 | Mississauga | FTE | 85.56 | 170 | 40 | E-0023 | Yuki Wright | .NET | 2018-09-24 | 150% | 2 | 0 | Overallocated | 1878 | 1878 | 100%
E-0029 | Tariq Obi | Senior Developer | Engineering | L5 | Ottawa | FTE | 99.36 | 200 | 40 | E-0023 | Yuki Wright | .NET | 2019-10-25 | 100% | 2 | 0 | Healthy | 1525 | 1525 | 100%
E-0030 | Sofia Hassan | Senior Developer | Engineering | L3 | Remote | FTE | 85.56 | 170 | 40 | E-0023 | Yuki Wright | Java | 2025-01-03 | 100% | 1 | 0 | Healthy | 1687.5 | 1687.5 | 100%
E-0031 | Jin Alvarez | Developer | Engineering | L6 | Toronto | FTE | 74.24 | 150 | 40 | E-0023 | Yuki Wright | React | 2016-09-17 | 100% | 1 | 0 | Healthy | 1355.1 | 1355.1 | 100%
E-0032 | Maya Osei | Developer | Engineering | L3 | Toronto | FTE | 59.52 | 120 | 40 | E-0023 | Yuki Wright | React | 2022-01-23 | 75% | 1 | 10 | Healthy | 1410.3 | 1410.3 | 100%
E-0033 | Elijah Adeyemi | Developer | Engineering | L3 | Toronto | FTE | 59.52 | 120 | 40 | E-0023 | Yuki Wright | Node.js | 2019-09-03 | 50% | 1 | 20 | Under-utilized | 1249.4 | 1249.4 | 100%
E-0034 | Anika Farouk | Developer | Engineering | L2 | Toronto | FTE | 54.4 | 110 | 32 | E-0023 | Yuki Wright | Python | 2015-03-20 | 50% | 1 | 16 | Under-utilized | 1131.9 | 1131.9 | 100%
E-0035 | Felix Singh | Developer | Engineering | L3 | Remote | FTE | 59.52 | 120 | 40 | E-0023 | Yuki Wright | React | 2021-09-09 | 100% | 1 | 0 | Healthy | 1775.2 | 1775.2 | 100%
E-0036 | Rosa Qureshi | Developer | Engineering | L3 | Montreal | FTE | 59.52 | 120 | 40 | E-0023 | Yuki Wright | Python | 2024-12-06 | 100% | 2 | 0 | Healthy | 1293.6 | 1293.6 | 100%
E-0037 | Imran Ivanova | Developer | Engineering | L2 | Remote | Contractor | 68 | 110 | 40 | E-0023 | Yuki Wright | React | 2025-02-14 | 75% | 1 | 10 | Healthy | 942.5 | 942.5 | 100%
E-0038 | Clara Boateng | Developer | Engineering | L6 | Toronto | FTE | 74.24 | 150 | 40 | E-0023 | Yuki Wright | React | 2024-10-22 | 100% | 2 | 0 | Healthy | 1297.4 | 1297.4 | 100%
E-0039 | Theo Siddiqui | Developer | Engineering | L2 | Ottawa | FTE | 54.4 | 110 | 40 | E-0023 | Yuki Wright | React | 2023-09-17 | 50% | 1 | 20 | Under-utilized | 547.1 | 547.1 | 100%
E-0040 | Leila Nguyen | Developer | Engineering | L4 | Ottawa | FTE | 64 | 130 | 40 | E-0023 | Yuki Wright | React | 2016-07-13 | 125% | 2 | 0 | Overallocated | 1141.2 | 1141.2 | 100%
E-0041 | Andre Fontaine | Developer | Engineering | L4 | Montreal | FTE | 64 | 130 | 40 | E-0023 | Yuki Wright | React | 2025-12-25 | 50% | 1 | 20 | Under-utilized | 881.4 | 881.4 | 100%
E-0042 | Nina Yilmaz | QA Analyst | Quality | L6 | Remote | FTE | 64.96 | 135 | 40 | E-0002 | Gordon Achebe | Automation | 2019-07-10 | 100% | 2 | 0 | Healthy | 735.8 | 735.8 | 100%
E-0043 | Victor Chen | QA Analyst | Quality | L6 | Remote | Contractor | 81.2 | 135 | 40 | E-0042 | Nina Yilmaz | Selenium | 2026-03-22 | 150% | 4 | 0 | Overallocated | 875.1 | 875.1 | 100%
E-0044 | Simran Patel | QA Analyst | Quality | L4 | Mississauga | Contractor | 70 | 115 | 40 | E-0042 | Nina Yilmaz | Automation | 2025-04-02 | 50% | 1 | 20 | Under-utilized | 490.2 | 490.2 | 100%
E-0045 | Hugo Ahmed | QA Analyst | Quality | L3 | Toronto | FTE | 52.08 | 105 | 40 | E-0042 | Nina Yilmaz | Selenium | 2022-09-15 | 50% | 1 | 20 | Under-utilized | 692.8 | 692.8 | 100%
E-0046 | Ines Morales | QA Analyst | Quality | L4 | Remote | FTE | 56 | 115 | 40 | E-0042 | Nina Yilmaz | Automation | 2022-10-28 | 100% | 2 | 0 | Healthy | 626.6 | 626.6 | 100%
E-0047 | Kofi Mensah | QA Analyst | Quality | L6 | Montreal | FTE | 64.96 | 135 | 40 | E-0042 | Nina Yilmaz | Selenium | 2023-04-02 | 100% | 2 | 0 | Healthy | 776.8 | 776.8 | 100%
E-0048 | Tessa Rossi | Data Engineer | Data & AI | L6 | Toronto | FTE | 104.4 | 210 | 40 | E-0002 | Gordon Achebe | dbt | 2019-06-24 | 100% | 1 | 0 | Healthy | 1538.7 | 1538.7 | 100%
E-0049 | Bilal Novak | Data Engineer | Data & AI | L2 | Toronto | FTE | 76.5 | 155 | 40 | E-0048 | Tessa Rossi | Spark | 2024-12-28 | 75% | 1 | 10 | Healthy | 1102.6 | 1102.6 | 100%
E-0050 | Julia Karimi | Data Engineer | Data & AI | L6 | Ottawa | FTE | 104.4 | 210 | 32 | E-0048 | Tessa Rossi | dbt | 2016-10-22 | 75% | 1 | 8 | Healthy | 679.4 | 679.4 | 100%
E-0051 | Marco Laurent | Data Engineer | Data & AI | L5 | Ottawa | FTE | 97.2 | 195 | 40 | E-0048 | Tessa Rossi | Databricks | 2015-02-06 | 75% | 1 | 10 | Healthy | 1249 | 1249 | 100%
E-0052 | Ayesha Schmidt | Data Scientist | Data & AI | L6 | Montreal | FTE | 113.68 | 230 | 40 | E-0048 | Tessa Rossi | ML | 2016-06-06 | 100% | 2 | 0 | Healthy | 1180.2 | 1180.2 | 100%
E-0053 | Declan Iyer | Data Scientist | Data & AI | L4 | Ottawa | FTE | 98 | 200 | 40 | E-0048 | Tessa Rossi | Python | 2020-02-03 | 75% | 1 | 10 | Healthy | 960.3 | 960.3 | 100%
E-0054 | Lina Lindgren | Data Scientist | Data & AI | L6 | Mississauga | FTE | 113.68 | 230 | 40 | E-0048 | Tessa Rossi | ML | 2023-07-04 | 75% | 1 | 10 | Healthy | 206 | 206 | 100%
E-0055 | Rohan Keller | Cloud Engineer | Infrastructure | L6 | Ottawa | FTE | 109.04 | 220 | 40 | E-0002 | Gordon Achebe | AWS | 2016-10-02 | 100% | 1 | 0 | Healthy | 1186.9 | 1186.9 | 100%
E-0056 | Esme Khan | Cloud Engineer | Infrastructure | L4 | Toronto | Contractor | 117.5 | 190 | 40 | E-0055 | Rohan Keller | AWS | 2025-05-02 | 75% | 1 | 10 | Healthy | 1231.5 | 1231.5 | 100%
E-0057 | Caleb Walsh | Cloud Engineer | Infrastructure | L6 | Toronto | FTE | 109.04 | 220 | 40 | E-0055 | Rohan Keller | Terraform | 2019-04-28 | 75% | 1 | 10 | Healthy | 1016.1 | 1016.1 | 100%
E-0058 | Noor Sato | Cloud Engineer | Infrastructure | L5 | Vancouver | Contractor | 126.9 | 205 | 40 | E-0055 | Rohan Keller | Azure | 2026-06-10 | 0% | 0 | 40 | Under-utilized | 0 | 0 | 0%
E-0059 | Adrian Kapoor | DevOps Engineer | Infrastructure | L6 | Toronto | FTE | 99.76 | 205 | 40 | E-0055 | Rohan Keller | CI/CD | 2022-10-15 | 50% | 1 | 20 | Under-utilized | 605.4 | 605.4 | 100%
E-0060 | Priyanka Tanaka | DevOps Engineer | Infrastructure | L3 | Ottawa | FTE | 79.98 | 165 | 40 | E-0055 | Rohan Keller | CI/CD | 2025-02-28 | 50% | 1 | 20 | Under-utilized | 829.2 | 829.2 | 100%
E-0061 | Jonah Lee | DevOps Engineer | Infrastructure | L4 | Vancouver | FTE | 86 | 175 | 40 | E-0055 | Rohan Keller | Kubernetes | 2023-03-10 | 50% | 1 | 20 | Under-utilized | 695.3 | 695.3 | 100%
E-0062 | Mariam Brooks | Change Manager | Delivery | L6 | Ottawa | FTE | 83.52 | 175 | 40 | E-0015 | Zara Vasquez | Training | 2024-08-02 | 50% | 2 | 20 | Under-utilized | 391.6 | 391.6 | 100%
E-0063 | Callum Dubois | Change Manager | Delivery | L5 | Toronto | FTE | 77.76 | 160 | 32 | E-0015 | Zara Vasquez | Comms | 2016-10-22 | 50% | 2 | 16 | Under-utilized | 307.1 | 307.1 | 100%

## Allocations
AllocationID | ProjectID | ProjectName | EmployeeID | EmployeeName | ProjectRole | Billable | StartDate | EndDate | AllocationPct | IsActive | WorkingDays | PlannedHours | CostRateHr | BillRateHr | PlannedCost | PlannedRevenue | ActualHours | HoursBurnPct
A-0001 | P-1001 | Patient Portal Modernization | E-0003 | Aisha Tremblay | Delivery Lead | Yes | 2025-11-03 | 2026-11-03 | 50% | Yes | 262 | 1048 | 102.08 | 205 | 106979.84 | 214840 | 829.1 | 79.11%
A-0002 | P-1001 | Patient Portal Modernization | E-0020 | Diego Costa | UX Designer | Yes | 2025-11-03 | 2026-05-20 | 75% | No | 143 | 858 | 85.84 | 175 | 73650.72 | 150150 | 847.6 | 98.79%
A-0003 | P-1001 | Patient Portal Modernization | E-0023 | Yuki Wright | Tech Lead | Yes | 2025-11-03 | 2026-11-03 | 75% | Yes | 262 | 1572 | 106.72 | 215 | 167763.84 | 337980 | 1262 | 80.28%
A-0004 | P-1001 | Patient Portal Modernization | E-0031 | Jin Alvarez | Developer | Yes | 2025-11-03 | 2026-11-03 | 100% | Yes | 262 | 2096 | 74.24 | 150 | 155607.04 | 314400 | 1670 | 79.68%
A-0005 | P-1001 | Patient Portal Modernization | E-0042 | Nina Yilmaz | QA Analyst | Yes | 2026-04-14 | 2026-11-03 | 50% | Yes | 146 | 584 | 64.96 | 135 | 37936.64 | 78840 | 413.1 | 70.74%
A-0006 | P-1001 | Patient Portal Modernization | E-0015 | Zara Vasquez | Business Analyst | Yes | 2025-11-03 | 2026-05-20 | 50% | No | 143 | 572 | 78.88 | 160 | 45119.36 | 91520 | 563.2 | 98.46%
A-0007 | P-1002 | Claims Automation Engine | E-0004 | Liam Roy | Delivery Lead | Yes | 2026-01-12 | 2027-01-04 | 25% | Yes | 256 | 512 | 102.08 | 205 | 52264.96 | 104960 | 463.3 | 90.49%
A-0008 | P-1002 | Claims Automation Engine | E-0016 | Owen Bennett | Business Analyst | Yes | 2026-01-12 | 2027-01-04 | 50% | Yes | 256 | 1024 | 73.44 | 150 | 75202.56 | 153600 | 964.5 | 94.19%
A-0009 | P-1002 | Claims Automation Engine | E-0024 | Isabel Gill | Tech Lead | Yes | 2026-01-12 | 2027-01-04 | 50% | Yes | 256 | 1024 | 99.36 | 200 | 101744.64 | 204800 | 936.1 | 91.42%
A-0010 | P-1002 | Claims Automation Engine | E-0032 | Maya Osei | Developer | Yes | 2026-01-12 | 2027-01-04 | 75% | Yes | 256 | 1536 | 59.52 | 120 | 91422.72 | 184320 | 1410.3 | 91.82%
A-0011 | P-1002 | Claims Automation Engine | E-0043 | Victor Chen | QA Analyst | Yes | 2026-06-14 | 2027-01-04 | 25% | Yes | 146 | 292 | 81.2 | 135 | 23710.4 | 39420 | 158.7 | 54.35%
A-0012 | P-1002 | Claims Automation Engine | E-0062 | Mariam Brooks | Change Manager | Yes | 2026-06-14 | 2027-01-04 | 25% | Yes | 146 | 292 | 83.52 | 175 | 24387.84 | 51100 | 153.5 | 52.57%
A-0013 | P-1003 | Enterprise Data Lakehouse | E-0005 | Mei Fraser | Delivery Lead | No | 2025-09-08 | 2027-01-07 | 25% | Yes | 349 | 698 | 74.8 | 150 | 52210.4 | 0 | 557.9 | 79.93%
A-0014 | P-1003 | Enterprise Data Lakehouse | E-0048 | Tessa Rossi | Data Engineer | Yes | 2025-09-08 | 2027-01-07 | 100% | Yes | 349 | 2792 | 104.4 | 210 | 291484.8 | 586320 | 2291.4 | 82.07%
A-0015 | P-1003 | Enterprise Data Lakehouse | E-0052 | Ayesha Schmidt | Data Scientist | Yes | 2025-12-06 | 2026-09-21 | 50% | Yes | 206 | 824 | 113.68 | 230 | 93672.32 | 189520 | 838.2 | 101.7%
A-0016 | P-1003 | Enterprise Data Lakehouse | E-0013 | Hana Clarke | Solution Architect | Yes | 2025-09-08 | 2026-05-10 | 25% | No | 175 | 350 | 120.96 | 245 | 42336 | 85750 | 383.1 | 109.5%
A-0017 | P-1003 | Enterprise Data Lakehouse | E-0033 | Elijah Adeyemi | Developer | Yes | 2025-09-08 | 2027-01-07 | 50% | Yes | 349 | 1396 | 59.52 | 120 | 83089.92 | 167520 | 1161.6 | 83.21%
A-0018 | P-1003 | Enterprise Data Lakehouse | E-0044 | Simran Patel | QA Analyst | Yes | 2026-03-27 | 2027-01-07 | 50% | Yes | 205 | 820 | 70 | 115 | 57400 | 94300 | 490.2 | 59.78%
A-0019 | P-1004 | Cloud Migration Wave 2 | E-0006 | Noah Rahimi | Delivery Lead | Yes | 2026-02-02 | 2027-02-04 | 25% | Yes | 264 | 528 | 88 | 175 | 46464 | 92400 | 303.8 | 57.54%
A-0020 | P-1004 | Cloud Migration Wave 2 | E-0055 | Rohan Keller | Cloud Engineer | Yes | 2026-02-02 | 2027-02-04 | 100% | Yes | 264 | 2112 | 109.04 | 220 | 230292.48 | 464640 | 1186.9 | 56.2%
A-0021 | P-1004 | Cloud Migration Wave 2 | E-0059 | Adrian Kapoor | DevOps Engineer | Yes | 2026-02-02 | 2027-02-04 | 50% | Yes | 264 | 1056 | 99.76 | 205 | 105346.56 | 216480 | 605.4 | 57.33%
A-0022 | P-1004 | Cloud Migration Wave 2 | E-0011 | Chloe Reyes | Solution Architect | Yes | 2026-02-02 | 2026-08-19 | 25% | No | 143 | 286 | 129.92 | 260 | 37157.12 | 74360 | 282.6 | 98.81%
A-0023 | P-1004 | Cloud Migration Wave 2 | E-0025 | Kwame Malik | Tech Lead | Yes | 2026-02-02 | 2027-02-04 | 50% | Yes | 264 | 1056 | 106.95 | 170 | 112939.2 | 179520 | 593.8 | 56.23%
A-0024 | P-1005 | Fraud Detection ML Platform | E-0007 | Fatima Cohen | Delivery Lead | Yes | 2026-03-02 | 2027-05-03 | 25% | Yes | 306 | 612 | 102.08 | 205 | 62472.96 | 125460 | 364.3 | 59.53%
A-0025 | P-1005 | Fraud Detection ML Platform | E-0049 | Bilal Novak | Data Engineer | Yes | 2026-03-02 | 2027-05-03 | 75% | Yes | 306 | 1836 | 76.5 | 155 | 140454 | 284580 | 1102.6 | 60.05%
A-0026 | P-1005 | Fraud Detection ML Platform | E-0052 | Ayesha Schmidt | Data Scientist | Yes | 2026-05-13 | 2027-01-02 | 50% | Yes | 168 | 672 | 113.68 | 230 | 76392.96 | 154560 | 426.2 | 63.42%
A-0027 | P-1005 | Fraud Detection ML Platform | E-0012 | Mateo Bianchi | Solution Architect | Yes | 2026-03-02 | 2026-09-16 | 25% | Yes | 143 | 286 | 129.92 | 260 | 37157.12 | 74360 | 370.1 | 129.4%
A-0028 | P-1005 | Fraud Detection ML Platform | E-0034 | Anika Farouk | Developer | Yes | 2026-03-02 | 2027-05-03 | 50% | Yes | 306 | 979.2 | 54.4 | 110 | 53268.48 | 107712 | 599.5 | 61.22%
A-0029 | P-1005 | Fraud Detection ML Platform | E-0046 | Ines Morales | QA Analyst | Yes | 2026-08-11 | 2027-05-03 | 50% | Yes | 190 | 760 | 56 | 115 | 42560 | 87400 | 79.4 | 10.45%
A-0030 | P-1006 | Omnichannel Commerce Replatform | E-0009 | Olivia Silva | Delivery Lead | Yes | 2025-10-06 | 2026-10-05 | 50% | Yes | 261 | 1044 | 74.8 | 150 | 78091.2 | 156600 | 1193.8 | 114.3%
A-0031 | P-1006 | Omnichannel Commerce Replatform | E-0021 | Nadia Aziz | UX Designer | Yes | 2025-10-06 | 2026-04-18 | 75% | No | 140 | 840 | 68.82 | 140 | 57808.8 | 117600 | 1068.4 | 127.2%
A-0032 | P-1006 | Omnichannel Commerce Replatform | E-0026 | Leah Haddad | Tech Lead | Yes | 2025-10-06 | 2026-10-05 | 75% | Yes | 261 | 1566 | 85.56 | 170 | 133986.96 | 266220 | 1767.3 | 112.9%
A-0033 | P-1006 | Omnichannel Commerce Replatform | E-0035 | Felix Singh | Developer | Yes | 2025-10-06 | 2026-10-05 | 100% | Yes | 261 | 2088 | 59.52 | 120 | 124277.76 | 250560 | 2393.6 | 114.6%
A-0034 | P-1006 | Omnichannel Commerce Replatform | E-0045 | Hugo Ahmed | QA Analyst | Yes | 2026-03-14 | 2026-10-05 | 50% | Yes | 146 | 584 | 52.08 | 105 | 30414.72 | 61320 | 631.8 | 108.2%
A-0035 | P-1006 | Omnichannel Commerce Replatform | E-0019 | Emma Leblanc | Business Analyst | Yes | 2025-10-06 | 2026-04-18 | 50% | No | 140 | 560 | 72.25 | 120 | 40460 | 67200 | 714.5 | 127.6%
A-0036 | P-1007 | Student Information System Upgrade | E-0008 | Ethan Park | Delivery Lead | Yes | 2026-04-06 | 2027-03-29 | 50% | Yes | 256 | 1024 | 95.04 | 190 | 97320.96 | 194560 | 419.5 | 40.97%
A-0037 | P-1007 | Student Information System Upgrade | E-0017 | Amara Martin | Business Analyst | Yes | 2026-04-06 | 2027-03-29 | 50% | Yes | 256 | 1024 | 63.24 | 130 | 64757.76 | 133120 | 446.5 | 43.6%
A-0038 | P-1007 | Student Information System Upgrade | E-0014 | Lucas Okoro | Solution Architect | Yes | 2026-04-06 | 2026-10-17 | 50% | Yes | 140 | 560 | 104.16 | 210 | 58329.6 | 117600 | 429.7 | 76.73%
A-0039 | P-1007 | Student Information System Upgrade | E-0027 | Omar Bose | Tech Lead | Yes | 2026-04-06 | 2027-03-29 | 75% | Yes | 256 | 1536 | 99.36 | 200 | 152616.96 | 307200 | 622.7 | 40.54%
A-0040 | P-1007 | Student Information System Upgrade | E-0036 | Rosa Qureshi | Developer | Yes | 2026-04-06 | 2027-03-29 | 50% | Yes | 256 | 1024 | 59.52 | 120 | 60948.48 | 122880 | 388.6 | 37.95%
A-0041 | P-1007 | Student Information System Upgrade | E-0045 | Hugo Ahmed | QA Analyst | Yes | 2026-09-12 | 2027-03-29 | 50% | No | 141 | 564 | 52.08 | 105 | 29373.12 | 59220 | 0 | 0%
A-0042 | P-1007 | Student Information System Upgrade | E-0063 | Callum Dubois | Change Manager | Yes | 2026-09-12 | 2027-03-29 | 25% | No | 141 | 225.6 | 77.76 | 160 | 17542.656 | 36096 | 0 | 0%
A-0043 | P-1008 | Network Operations Centre Refresh | E-0010 | Arjun Baptiste | Delivery Lead | No | 2026-01-05 | 2026-11-02 | 25% | Yes | 216 | 432 | 88 | 175 | 38016 | 0 | 417.7 | 96.69%
A-0044 | P-1008 | Network Operations Centre Refresh | E-0056 | Esme Khan | Cloud Engineer | Yes | 2026-01-05 | 2026-11-02 | 75% | Yes | 216 | 1296 | 117.5 | 190 | 152280 | 246240 | 1231.5 | 95.02%
A-0045 | P-1008 | Network Operations Centre Refresh | E-0060 | Priyanka Tanaka | DevOps Engineer | Yes | 2026-01-05 | 2026-11-02 | 50% | Yes | 216 | 864 | 79.98 | 165 | 69102.72 | 142560 | 829.2 | 95.97%
A-0046 | P-1008 | Network Operations Centre Refresh | E-0012 | Mateo Bianchi | Solution Architect | Yes | 2026-01-05 | 2026-06-10 | 25% | No | 113 | 226 | 129.92 | 260 | 29361.92 | 58760 | 274.4 | 121.4%
A-0047 | P-1008 | Network Operations Centre Refresh | E-0029 | Tariq Obi | Tech Lead | Yes | 2026-01-05 | 2026-11-02 | 50% | Yes | 216 | 864 | 99.36 | 200 | 85847.04 | 172800 | 828.5 | 95.89%
A-0048 | P-1009 | Smart Factory IoT Pilot | E-0005 | Mei Fraser | Delivery Lead | Yes | 2026-05-04 | 2026-12-14 | 50% | Yes | 161 | 644 | 74.8 | 150 | 48171.2 | 96600 | 343.5 | 53.34%
A-0049 | P-1009 | Smart Factory IoT Pilot | E-0018 | Ravi Gagnon | Business Analyst | Yes | 2026-05-04 | 2026-12-14 | 50% | Yes | 161 | 644 | 73.44 | 150 | 47295.36 | 96600 | 332 | 51.55%
A-0050 | P-1009 | Smart Factory IoT Pilot | E-0028 | Grace Chowdhury | Tech Lead | Yes | 2026-05-04 | 2026-12-14 | 75% | Yes | 161 | 966 | 85.56 | 170 | 82650.96 | 164220 | 523.2 | 54.16%
A-0051 | P-1009 | Smart Factory IoT Pilot | E-0037 | Imran Ivanova | Developer | Yes | 2026-05-04 | 2026-12-14 | 75% | Yes | 161 | 966 | 68 | 110 | 65688 | 106260 | 507.7 | 52.56%
A-0052 | P-1009 | Smart Factory IoT Pilot | E-0047 | Kofi Mensah | QA Analyst | Yes | 2026-08-11 | 2026-12-14 | 50% | Yes | 90 | 360 | 64.96 | 135 | 23385.6 | 48600 | 65.6 | 18.22%
A-0053 | P-1009 | Smart Factory IoT Pilot | E-0063 | Callum Dubois | Change Manager | Yes | 2026-08-11 | 2026-12-14 | 25% | Yes | 90 | 144 | 77.76 | 160 | 11197.44 | 23040 | 26 | 18.06%
A-0054 | P-1010 | 311 Citizen Services App | E-0007 | Fatima Cohen | Delivery Lead | Yes | 2025-12-01 | 2026-10-16 | 50% | Yes | 230 | 920 | 102.08 | 205 | 93913.6 | 188600 | 975.2 | 106%
A-0055 | P-1010 | 311 Citizen Services App | E-0022 | Samuel Mehta | UX Designer | Yes | 2025-12-01 | 2026-04-28 | 50% | No | 107 | 428 | 62.9 | 130 | 26921.2 | 55640 | 538.1 | 125.7%
A-0056 | P-1010 | 311 Citizen Services App | E-0030 | Sofia Hassan | Tech Lead | Yes | 2025-12-01 | 2026-10-16 | 100% | Yes | 230 | 1840 | 85.56 | 170 | 157430.4 | 312800 | 1909.9 | 103.8%
A-0057 | P-1010 | 311 Citizen Services App | E-0038 | Clara Boateng | Developer | Yes | 2025-12-01 | 2026-10-16 | 50% | Yes | 230 | 920 | 74.24 | 150 | 68300.8 | 138000 | 1011.7 | 110%
A-0058 | P-1010 | 311 Citizen Services App | E-0046 | Ines Morales | QA Analyst | Yes | 2026-04-01 | 2026-10-16 | 50% | Yes | 143 | 572 | 56 | 115 | 32032 | 65780 | 547.2 | 95.66%
A-0059 | P-1010 | 311 Citizen Services App | E-0018 | Ravi Gagnon | Business Analyst | Yes | 2025-12-01 | 2026-04-28 | 50% | No | 107 | 428 | 73.44 | 150 | 31432.32 | 64200 | 540.2 | 126.2%
A-0060 | P-1011 | Clinical Trials Data Hub | E-0006 | Noah Rahimi | Delivery Lead | No | 2026-02-16 | 2027-04-30 | 25% | Yes | 315 | 630 | 88 | 175 | 55440 | 0 | 286.4 | 45.46%
A-0061 | P-1011 | Clinical Trials Data Hub | E-0050 | Julia Karimi | Data Engineer | Yes | 2026-02-16 | 2027-04-30 | 75% | Yes | 315 | 1512 | 104.4 | 210 | 157852.8 | 317520 | 679.4 | 44.93%
A-0062 | P-1011 | Clinical Trials Data Hub | E-0053 | Declan Iyer | Data Scientist | Yes | 2026-05-14 | 2027-02-23 | 75% | Yes | 204 | 1224 | 98 | 200 | 119952 | 244800 | 494.5 | 40.4%
A-0063 | P-1011 | Clinical Trials Data Hub | E-0013 | Hana Clarke | Solution Architect | Yes | 2026-02-16 | 2026-10-14 | 25% | Yes | 173 | 346 | 120.96 | 245 | 41852.16 | 84770 | 288.9 | 83.5%
A-0064 | P-1011 | Clinical Trials Data Hub | E-0039 | Theo Siddiqui | Developer | Yes | 2026-02-16 | 2027-04-30 | 50% | Yes | 315 | 1260 | 54.4 | 110 | 68544 | 138600 | 547.1 | 43.42%
A-0065 | P-1011 | Clinical Trials Data Hub | E-0043 | Victor Chen | QA Analyst | Yes | 2026-09-01 | 2027-04-30 | 50% | Yes | 174 | 696 | 81.2 | 135 | 56515.2 | 93960 | 0 | 0%
A-0066 | P-1012 | Grid Analytics Dashboard | E-0010 | Arjun Baptiste | Delivery Lead | Yes | 2026-06-01 | 2026-12-18 | 50% | Yes | 145 | 580 | 88 | 175 | 51040 | 101500 | 271.1 | 46.74%
A-0067 | P-1012 | Grid Analytics Dashboard | E-0051 | Marco Laurent | Data Engineer | Yes | 2026-06-01 | 2026-12-18 | 75% | Yes | 145 | 870 | 97.2 | 195 | 84564 | 169650 | 402.1 | 46.22%
A-0068 | P-1012 | Grid Analytics Dashboard | E-0054 | Lina Lindgren | Data Scientist | Yes | 2026-07-11 | 2026-11-18 | 75% | Yes | 93 | 558 | 113.68 | 230 | 63433.44 | 128340 | 206 | 36.92%
A-0069 | P-1012 | Grid Analytics Dashboard | E-0011 | Chloe Reyes | Solution Architect | Yes | 2026-06-01 | 2026-09-19 | 25% | Yes | 80 | 160 | 129.92 | 260 | 20787.2 | 41600 | 129.1 | 80.69%
A-0070 | P-1012 | Grid Analytics Dashboard | E-0040 | Leila Nguyen | Developer | Yes | 2026-06-01 | 2026-12-18 | 50% | Yes | 145 | 580 | 64 | 130 | 37120 | 75400 | 277.2 | 47.79%
A-0071 | P-1012 | Grid Analytics Dashboard | E-0042 | Nina Yilmaz | QA Analyst | Yes | 2026-08-30 | 2026-12-18 | 50% | Yes | 80 | 320 | 64.96 | 135 | 20787.2 | 43200 | 3.7 | 1.156%
A-0072 | P-1013 | Core Banking API Layer | E-0004 | Liam Roy | Delivery Lead | Yes | 2025-08-04 | 2026-11-16 | 50% | Yes | 336 | 1344 | 102.08 | 205 | 137195.52 | 275520 | 1434.5 | 106.7%
A-0073 | P-1013 | Core Banking API Layer | E-0019 | Emma Leblanc | Business Analyst | Yes | 2025-08-04 | 2026-11-16 | 75% | Yes | 336 | 2016 | 72.25 | 120 | 145656 | 241920 | 2149.6 | 106.6%
A-0074 | P-1013 | Core Banking API Layer | E-0014 | Lucas Okoro | Solution Architect | Yes | 2025-08-04 | 2026-04-09 | 50% | No | 179 | 716 | 104.16 | 210 | 74578.56 | 150360 | 893.9 | 124.8%
A-0075 | P-1013 | Core Banking API Layer | E-0028 | Grace Chowdhury | Tech Lead | Yes | 2025-08-04 | 2026-11-16 | 75% | Yes | 336 | 2016 | 85.56 | 170 | 172488.96 | 342720 | 2188.4 | 108.6%
A-0076 | P-1013 | Core Banking API Layer | E-0041 | Andre Fontaine | Developer | Yes | 2025-08-04 | 2026-11-16 | 50% | Yes | 336 | 1344 | 64 | 130 | 86016 | 174720 | 1438.4 | 107%
A-0077 | P-1013 | Core Banking API Layer | E-0047 | Kofi Mensah | QA Analyst | Yes | 2026-02-23 | 2026-11-16 | 50% | Yes | 191 | 764 | 64.96 | 135 | 49629.44 | 103140 | 711.2 | 93.09%
A-0078 | P-1013 | Core Banking API Layer | E-0063 | Callum Dubois | Change Manager | Yes | 2026-02-23 | 2026-11-16 | 25% | Yes | 191 | 305.6 | 77.76 | 160 | 23763.456 | 48896 | 281.1 | 91.98%
A-0079 | P-1014 | Managed Cloud Operations | E-0008 | Ethan Park | Delivery Lead | Yes | 2025-07-01 | 2027-01-04 | 25% | Yes | 395 | 790 | 95.04 | 190 | 75081.6 | 150100 | 620 | 78.48%
A-0080 | P-1014 | Managed Cloud Operations | E-0057 | Caleb Walsh | Cloud Engineer | Yes | 2025-07-01 | 2027-01-04 | 75% | Yes | 395 | 2370 | 109.04 | 220 | 258424.8 | 521400 | 1790.5 | 75.55%
A-0081 | P-1014 | Managed Cloud Operations | E-0061 | Jonah Lee | DevOps Engineer | Yes | 2025-07-01 | 2027-01-04 | 50% | Yes | 395 | 1580 | 86 | 175 | 135880 | 276500 | 1244.5 | 78.77%
A-0082 | P-1014 | Managed Cloud Operations | E-0011 | Chloe Reyes | Solution Architect | Yes | 2025-07-01 | 2026-04-28 | 25% | No | 216 | 432 | 129.92 | 260 | 56125.44 | 112320 | 447.5 | 103.6%
A-0083 | P-1014 | Managed Cloud Operations | E-0029 | Tariq Obi | Tech Lead | Yes | 2025-07-01 | 2027-01-04 | 50% | Yes | 395 | 1580 | 99.36 | 200 | 156988.8 | 316000 | 1248.4 | 79.01%
A-0084 | P-1015 | Policy Admin Consolidation | E-0009 | Olivia Silva | Delivery Lead | Yes | 2026-03-16 | 2027-07-05 | 50% | Yes | 341 | 1364 | 74.8 | 150 | 102027.2 | 204600 | 582.2 | 42.68%
A-0085 | P-1015 | Policy Admin Consolidation | E-0015 | Zara Vasquez | Business Analyst | Yes | 2026-03-16 | 2027-07-05 | 50% | Yes | 341 | 1364 | 78.88 | 160 | 107592.32 | 218240 | 585.9 | 42.95%
A-0086 | P-1015 | Policy Admin Consolidation | E-0013 | Hana Clarke | Solution Architect | Yes | 2026-03-16 | 2026-11-27 | 25% | Yes | 185 | 370 | 120.96 | 245 | 44755.2 | 90650 | 299.6 | 80.97%
A-0087 | P-1015 | Policy Admin Consolidation | E-0024 | Isabel Gill | Tech Lead | Yes | 2026-03-16 | 2027-07-05 | 75% | Yes | 341 | 2046 | 99.36 | 200 | 203290.56 | 409200 | 922 | 45.06%
A-0088 | P-1015 | Policy Admin Consolidation | E-0040 | Leila Nguyen | Developer | Yes | 2026-03-16 | 2027-07-05 | 75% | Yes | 341 | 2046 | 64 | 130 | 130944 | 265980 | 864 | 42.23%
A-0089 | P-1015 | Policy Admin Consolidation | E-0044 | Simran Patel | QA Analyst | Yes | 2026-10-11 | 2027-07-05 | 50% | No | 191 | 764 | 70 | 115 | 53480 | 87860 | 0 | 0%
A-0090 | P-1015 | Policy Admin Consolidation | E-0062 | Mariam Brooks | Change Manager | Yes | 2026-10-11 | 2027-07-05 | 25% | No | 191 | 382 | 83.52 | 175 | 31904.64 | 66850 | 0 | 0%
A-0091 | P-1016 | Warehouse Robotics Integration | E-0003 | Aisha Tremblay | Delivery Lead | No | 2026-04-13 | 2026-11-23 | 25% | Yes | 161 | 322 | 102.08 | 205 | 32869.76 | 0 | 203.6 | 63.23%
A-0092 | P-1016 | Warehouse Robotics Integration | E-0018 | Ravi Gagnon | Business Analyst | Yes | 2026-04-13 | 2026-11-23 | 50% | Yes | 161 | 644 | 73.44 | 150 | 47295.36 | 96600 | 415.9 | 64.58%
A-0093 | P-1016 | Warehouse Robotics Integration | E-0025 | Kwame Malik | Tech Lead | Yes | 2026-04-13 | 2026-11-23 | 50% | Yes | 161 | 644 | 106.95 | 170 | 68875.8 | 109480 | 400.3 | 62.16%
A-0094 | P-1016 | Warehouse Robotics Integration | E-0038 | Clara Boateng | Developer | Yes | 2026-04-13 | 2026-11-23 | 50% | Yes | 161 | 644 | 74.24 | 150 | 47810.56 | 96600 | 408.7 | 63.46%
A-0095 | P-1016 | Warehouse Robotics Integration | E-0043 | Victor Chen | QA Analyst | Yes | 2026-07-21 | 2026-11-23 | 25% | Yes | 90 | 180 | 81.2 | 135 | 14616 | 24300 | 63.7 | 35.39%
A-0096 | P-1016 | Warehouse Robotics Integration | E-0062 | Mariam Brooks | Change Manager | Yes | 2026-07-21 | 2026-11-23 | 25% | Yes | 90 | 180 | 83.52 | 175 | 15033.6 | 31500 | 60.8 | 33.78%
A-0097 | P-1017 | Loyalty Program Relaunch | E-0005 | Mei Fraser | Delivery Lead | Yes | 2026-01-19 | 2026-11-24 | 50% | Yes | 222 | 888 | 74.8 | 150 | 66422.4 | 133200 | 904.9 | 101.9%
A-0098 | P-1017 | Loyalty Program Relaunch | E-0022 | Samuel Mehta | UX Designer | Yes | 2026-01-19 | 2026-06-07 | 50% | No | 100 | 400 | 62.9 | 130 | 25160 | 52000 | 583.3 | 145.8%
A-0099 | P-1017 | Loyalty Program Relaunch | E-0027 | Omar Bose | Tech Lead | Yes | 2026-01-19 | 2026-11-24 | 50% | Yes | 222 | 888 | 99.36 | 200 | 88231.68 | 177600 | 917.5 | 103.3%
A-0100 | P-1017 | Loyalty Program Relaunch | E-0036 | Rosa Qureshi | Developer | Yes | 2026-01-19 | 2026-11-24 | 50% | Yes | 222 | 888 | 59.52 | 120 | 52853.76 | 106560 | 905 | 101.9%
A-0101 | P-1017 | Loyalty Program Relaunch | E-0043 | Victor Chen | QA Analyst | Yes | 2026-05-13 | 2026-11-24 | 50% | Yes | 140 | 560 | 81.2 | 135 | 45472 | 75600 | 467.4 | 83.46%
A-0102 | P-1017 | Loyalty Program Relaunch | E-0017 | Amara Martin | Business Analyst | Yes | 2026-01-19 | 2026-06-07 | 50% | No | 100 | 400 | 63.24 | 130 | 25296 | 52000 | 573.7 | 143.4%
A-0103 | P-1018 | Cybersecurity Posture Assessment | E-0006 | Noah Rahimi | Delivery Lead | Yes | 2025-06-02 | 2025-12-19 | 50% | No | 145 | 580 | 88 | 175 | 51040 | 101500 | 549.4 | 94.72%
A-0104 | P-1018 | Cybersecurity Posture Assessment | E-0055 | Rohan Keller | Cloud Engineer | Yes | 2025-06-02 | 2025-12-19 | 100% | No | 145 | 1160 | 109.04 | 220 | 126486.4 | 255200 | 1126.3 | 97.09%
A-0105 | P-1018 | Cybersecurity Posture Assessment | E-0061 | Jonah Lee | DevOps Engineer | Yes | 2025-06-02 | 2025-12-19 | 50% | No | 145 | 580 | 86 | 175 | 49880 | 101500 | 567.9 | 97.91%
A-0106 | P-1018 | Cybersecurity Posture Assessment | E-0012 | Mateo Bianchi | Solution Architect | Yes | 2025-06-02 | 2025-09-20 | 25% | No | 80 | 160 | 129.92 | 260 | 20787.2 | 41600 | 157.1 | 98.19%
A-0107 | P-1018 | Cybersecurity Posture Assessment | E-0027 | Omar Bose | Tech Lead | Yes | 2025-06-02 | 2025-12-19 | 50% | No | 145 | 580 | 99.36 | 200 | 57628.8 | 116000 | 570.7 | 98.4%
A-0108 | P-1019 | HR Self-Service Portal | E-0010 | Arjun Baptiste | Delivery Lead | Yes | 2025-05-05 | 2026-04-10 | 50% | No | 245 | 980 | 88 | 175 | 86240 | 171500 | 1065.4 | 108.7%
A-0109 | P-1019 | HR Self-Service Portal | E-0017 | Amara Martin | Business Analyst | Yes | 2025-05-05 | 2026-04-10 | 75% | No | 245 | 1470 | 63.24 | 130 | 92962.8 | 191100 | 1592.3 | 108.3%
A-0110 | P-1019 | HR Self-Service Portal | E-0013 | Hana Clarke | Solution Architect | Yes | 2025-05-05 | 2025-10-15 | 25% | No | 118 | 236 | 120.96 | 245 | 28546.56 | 57820 | 256.2 | 108.6%
A-0111 | P-1019 | HR Self-Service Portal | E-0025 | Kwame Malik | Tech Lead | Yes | 2025-05-05 | 2026-04-10 | 75% | No | 245 | 1470 | 106.95 | 170 | 157216.5 | 249900 | 1588.2 | 108%
A-0112 | P-1019 | HR Self-Service Portal | E-0034 | Anika Farouk | Developer | Yes | 2025-05-05 | 2026-04-10 | 100% | No | 245 | 1568 | 54.4 | 110 | 85299.2 | 172480 | 1747.6 | 111.5%
A-0113 | P-1019 | HR Self-Service Portal | E-0042 | Nina Yilmaz | QA Analyst | Yes | 2025-09-16 | 2026-04-10 | 50% | No | 149 | 596 | 64.96 | 135 | 38716.16 | 80460 | 644.2 | 108.1%
A-0114 | P-1019 | HR Self-Service Portal | E-0062 | Mariam Brooks | Change Manager | Yes | 2025-09-16 | 2026-04-10 | 25% | No | 149 | 298 | 83.52 | 175 | 24888.96 | 52150 | 313.4 | 105.2%
A-0115 | P-1020 | Demand Forecasting Model | E-0006 | Noah Rahimi | Delivery Lead | No | 2025-10-13 | 2026-06-01 | 50% | No | 166 | 664 | 88 | 175 | 58432 | 0 | 625.3 | 94.17%
A-0116 | P-1020 | Demand Forecasting Model | E-0051 | Marco Laurent | Data Engineer | Yes | 2025-10-13 | 2026-06-01 | 100% | No | 166 | 1328 | 97.2 | 195 | 129081.6 | 258960 | 1282.3 | 96.56%
A-0117 | P-1020 | Demand Forecasting Model | E-0053 | Declan Iyer | Data Scientist | Yes | 2025-11-27 | 2026-04-24 | 75% | No | 107 | 642 | 98 | 200 | 62916 | 128400 | 607.7 | 94.66%
A-0118 | P-1020 | Demand Forecasting Model | E-0012 | Mateo Bianchi | Solution Architect | Yes | 2025-10-13 | 2026-02-15 | 25% | No | 90 | 180 | 129.92 | 260 | 23385.6 | 46800 | 178.6 | 99.22%
A-0119 | P-1020 | Demand Forecasting Model | E-0037 | Imran Ivanova | Developer | Yes | 2025-10-13 | 2026-06-01 | 50% | No | 166 | 664 | 68 | 110 | 45152 | 73040 | 667.2 | 100.5%
A-0120 | P-1020 | Demand Forecasting Model | E-0043 | Victor Chen | QA Analyst | Yes | 2026-01-23 | 2026-06-01 | 25% | No | 92 | 184 | 81.2 | 135 | 14940.8 | 24840 | 185.3 | 100.7%
A-0121 | P-1021 | Field Service Mobile App | E-0010 | Arjun Baptiste | Delivery Lead | Yes | 2026-02-09 | 2026-07-10 | 25% | No | 110 | 220 | 88 | 175 | 19360 | 38500 | 242.1 | 110%
A-0122 | P-1021 | Field Service Mobile App | E-0016 | Owen Bennett | Business Analyst | Yes | 2026-02-09 | 2026-07-10 | 50% | No | 110 | 440 | 73.44 | 150 | 32313.6 | 66000 | 448.5 | 101.9%
A-0123 | P-1021 | Field Service Mobile App | E-0026 | Leah Haddad | Tech Lead | Yes | 2026-02-09 | 2026-07-10 | 75% | No | 110 | 660 | 85.56 | 170 | 56469.6 | 112200 | 717.7 | 108.7%
A-0124 | P-1021 | Field Service Mobile App | E-0033 | Elijah Adeyemi | Developer | Yes | 2026-02-09 | 2026-07-10 | 50% | No | 110 | 440 | 59.52 | 120 | 26188.8 | 52800 | 464.2 | 105.5%
A-0125 | P-1021 | Field Service Mobile App | E-0045 | Hugo Ahmed | QA Analyst | Yes | 2026-06-23 | 2026-07-10 | 50% | No | 14 | 56 | 52.08 | 105 | 2916.48 | 5880 | 61 | 108.9%
A-0126 | P-1021 | Field Service Mobile App | E-0062 | Mariam Brooks | Change Manager | Yes | 2026-06-23 | 2026-07-10 | 25% | No | 14 | 28 | 83.52 | 175 | 2338.56 | 4900 | 28.5 | 101.8%
A-0127 | P-1022 | Regulatory Reporting Automation | E-0003 | Aisha Tremblay | Delivery Lead | Yes | 2026-10-05 | 2027-05-28 | 50% | No | 170 | 680 | 102.08 | 205 | 69414.4 | 139400 | 0 | 0%
A-0128 | P-1022 | Regulatory Reporting Automation | E-0019 | Emma Leblanc | Business Analyst | Yes | 2026-10-05 | 2027-05-28 | 50% | No | 170 | 680 | 72.25 | 120 | 49130 | 81600 | 0 | 0%
A-0129 | P-1022 | Regulatory Reporting Automation | E-0026 | Leah Haddad | Tech Lead | Yes | 2026-10-05 | 2027-05-28 | 50% | No | 170 | 680 | 85.56 | 170 | 58180.8 | 115600 | 0 | 0%
A-0130 | P-1022 | Regulatory Reporting Automation | E-0035 | Felix Singh | Developer | Yes | 2026-10-05 | 2027-05-28 | 75% | No | 170 | 1020 | 59.52 | 120 | 60710.4 | 122400 | 0 | 0%
A-0131 | P-1022 | Regulatory Reporting Automation | E-0042 | Nina Yilmaz | QA Analyst | Yes | 2027-01-18 | 2027-05-28 | 25% | No | 95 | 190 | 64.96 | 135 | 12342.4 | 25650 | 0 | 0%
A-0132 | P-1022 | Regulatory Reporting Automation | E-0063 | Callum Dubois | Change Manager | Yes | 2027-01-18 | 2027-05-28 | 25% | No | 95 | 152 | 77.76 | 160 | 11819.52 | 24320 | 0 | 0%
A-0133 | P-1023 | GenAI Knowledge Assistant | E-0004 | Liam Roy | Delivery Lead | No | 2026-11-02 | 2027-06-25 | 25% | No | 170 | 340 | 102.08 | 205 | 34707.2 | 0 | 0 | 0%
A-0134 | P-1023 | GenAI Knowledge Assistant | E-0051 | Marco Laurent | Data Engineer | Yes | 2026-11-02 | 2027-06-25 | 75% | No | 170 | 1020 | 97.2 | 195 | 99144 | 198900 | 0 | 0%
A-0135 | P-1023 | GenAI Knowledge Assistant | E-0054 | Lina Lindgren | Data Scientist | Yes | 2026-12-19 | 2027-05-20 | 50% | No | 109 | 436 | 113.68 | 230 | 49564.48 | 100280 | 0 | 0%
A-0136 | P-1023 | GenAI Knowledge Assistant | E-0011 | Chloe Reyes | Solution Architect | Yes | 2026-11-02 | 2027-03-11 | 25% | No | 94 | 188 | 129.92 | 260 | 24424.96 | 48880 | 0 | 0%
A-0137 | P-1023 | GenAI Knowledge Assistant | E-0031 | Jin Alvarez | Developer | Yes | 2026-11-02 | 2027-06-25 | 50% | No | 170 | 680 | 74.24 | 150 | 50483.2 | 102000 | 0 | 0%
A-0138 | P-1023 | GenAI Knowledge Assistant | E-0047 | Kofi Mensah | QA Analyst | Yes | 2027-02-15 | 2027-06-25 | 25% | No | 95 | 190 | 64.96 | 135 | 12342.4 | 25650 | 0 | 0%
A-0139 | P-1024 | Municipal Asset Management | E-0005 | Mei Fraser | Delivery Lead | Yes | 2027-01-11 | 2027-10-29 | 50% | No | 210 | 840 | 74.8 | 150 | 62832 | 126000 | 0 | 0%
A-0140 | P-1024 | Municipal Asset Management | E-0018 | Ravi Gagnon | Business Analyst | Yes | 2027-01-11 | 2027-10-29 | 50% | No | 210 | 840 | 73.44 | 150 | 61689.6 | 126000 | 0 | 0%
A-0141 | P-1024 | Municipal Asset Management | E-0012 | Mateo Bianchi | Solution Architect | Yes | 2027-01-11 | 2027-06-20 | 50% | No | 115 | 460 | 129.92 | 260 | 59763.2 | 119600 | 0 | 0%
A-0142 | P-1024 | Municipal Asset Management | E-0023 | Yuki Wright | Tech Lead | Yes | 2027-01-11 | 2027-10-29 | 100% | No | 210 | 1680 | 106.72 | 215 | 179289.6 | 361200 | 0 | 0%
A-0143 | P-1024 | Municipal Asset Management | E-0032 | Maya Osei | Developer | Yes | 2027-01-11 | 2027-10-29 | 100% | No | 210 | 1680 | 59.52 | 120 | 99993.6 | 201600 | 0 | 0%
A-0144 | P-1024 | Municipal Asset Management | E-0043 | Victor Chen | QA Analyst | Yes | 2027-05-21 | 2027-10-29 | 50% | No | 116 | 464 | 81.2 | 135 | 37676.8 | 62640 | 0 | 0%
A-0145 | P-1024 | Municipal Asset Management | E-0063 | Callum Dubois | Change Manager | Yes | 2027-05-21 | 2027-10-29 | 25% | No | 116 | 185.6 | 77.76 | 160 | 14432.256 | 29696 | 0 | 0%
Formulas:
WorkingDays = NETWORKDAYS([StartDate],[EndDate])

## Estimates
EstimateLineID | ProjectID | EstimateVersion | IsCurrent | WBSCode | Phase | Workstream | EstimatedHours | BlendedCostRate | Confidence | EstimatedByID | EstimateDate | EstimatedBy | ContingencyPct | BaseCost | ContingencyAmt | TotalEstimate
EST-0001 | P-1001 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 624 | 87.23 | High | E-0003 | 2025-09-29 | Aisha Tremblay | 5% | 54431.52 | 2721.576 | 57153.096
EST-0002 | P-1001 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 1164 | 87.23 | High | E-0003 | 2025-09-29 | Aisha Tremblay | 5% | 101535.72 | 5076.786 | 106612.506
EST-0003 | P-1001 | v1 Baseline | Yes | 3.0 | Build | Engineering | 2968 | 87.23 | Medium | E-0003 | 2025-09-29 | Aisha Tremblay | 10% | 258898.64 | 25889.864 | 284788.504
EST-0004 | P-1001 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1265 | 87.23 | High | E-0003 | 2025-09-29 | Aisha Tremblay | 5% | 110345.95 | 5517.2975 | 115863.2475
EST-0005 | P-1001 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 665 | 87.23 | High | E-0003 | 2025-09-29 | Aisha Tremblay | 5% | 58007.95 | 2900.3975 | 60908.3475
EST-0006 | P-1002 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 492 | 78.77 | Low | E-0004 | 2025-12-01 | Liam Roy | 15% | 38754.84 | 5813.226 | 44568.066
EST-0007 | P-1002 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 776 | 78.77 | Low | E-0004 | 2025-12-01 | Liam Roy | 15% | 61125.52 | 9168.828 | 70294.348
EST-0008 | P-1002 | v1 Baseline | No | 3.0 | Build | Engineering | 1906 | 78.77 | Low | E-0004 | 2025-12-01 | Liam Roy | 15% | 150135.62 | 22520.343 | 172655.963
EST-0009 | P-1002 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 850 | 78.77 | Low | E-0004 | 2025-12-01 | Liam Roy | 15% | 66954.5 | 10043.175 | 76997.675
EST-0010 | P-1002 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 436 | 78.77 | Low | E-0004 | 2025-12-01 | Liam Roy | 15% | 34343.72 | 5151.558 | 39495.278
EST-0011 | P-1002 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 583 | 80.35 | Medium | E-0004 | 2026-07-15 | Liam Roy | 10% | 46844.05 | 4684.405 | 51528.455
EST-0012 | P-1002 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1062 | 80.35 | Medium | E-0004 | 2026-07-15 | Liam Roy | 10% | 85331.7 | 8533.17 | 93864.87
EST-0013 | P-1002 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 3198 | 80.35 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 256959.3 | 38543.895 | 295503.195
EST-0014 | P-1002 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1531 | 80.35 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 123015.85 | 18452.3775 | 141468.2275
EST-0015 | P-1002 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 758 | 80.35 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 60905.3 | 9135.795 | 70041.095
EST-0016 | P-1003 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 657 | 90.69 | Low | E-0005 | 2025-08-03 | Mei Fraser | 15% | 59583.33 | 8937.4995 | 68520.8295
EST-0017 | P-1003 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 1130 | 90.69 | Low | E-0005 | 2025-08-03 | Mei Fraser | 15% | 102479.7 | 15371.955 | 117851.655
EST-0018 | P-1003 | v1 Baseline | No | 3.0 | Build | Engineering | 2711 | 90.69 | Low | E-0005 | 2025-08-03 | Mei Fraser | 15% | 245860.59 | 36879.0885 | 282739.6785
EST-0019 | P-1003 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 1218 | 90.69 | Low | E-0005 | 2025-08-03 | Mei Fraser | 15% | 110460.42 | 16569.063 | 127029.483
EST-0020 | P-1003 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 642 | 90.69 | Low | E-0005 | 2025-08-03 | Mei Fraser | 15% | 58222.98 | 8733.447 | 66956.427
EST-0021 | P-1003 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 731 | 92.5 | Medium | E-0005 | 2026-07-15 | Mei Fraser | 10% | 67617.5 | 6761.75 | 74379.25
EST-0022 | P-1003 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1387 | 92.5 | Medium | E-0005 | 2026-07-15 | Mei Fraser | 10% | 128297.5 | 12829.75 | 141127.25
EST-0023 | P-1003 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 3839 | 92.5 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 355107.5 | 53266.125 | 408373.625
EST-0024 | P-1003 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1817 | 92.5 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 168072.5 | 25210.875 | 193283.375
EST-0025 | P-1003 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 933 | 92.5 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 86302.5 | 12945.375 | 99247.875
EST-0026 | P-1004 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 517 | 105.66 | High | E-0006 | 2025-12-24 | Noah Rahimi | 5% | 54626.22 | 2731.311 | 57357.531
EST-0027 | P-1004 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 793 | 105.66 | High | E-0006 | 2025-12-24 | Noah Rahimi | 5% | 83788.38 | 4189.419 | 87977.799
EST-0028 | P-1004 | v1 Baseline | Yes | 3.0 | Build | Engineering | 2127 | 105.66 | Medium | E-0006 | 2025-12-24 | Noah Rahimi | 10% | 224738.82 | 22473.882 | 247212.702
EST-0029 | P-1004 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1040 | 105.66 | High | E-0006 | 2025-12-24 | Noah Rahimi | 5% | 109886.4 | 5494.32 | 115380.72
EST-0030 | P-1004 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 488 | 105.66 | High | E-0006 | 2025-12-24 | Noah Rahimi | 5% | 51562.08 | 2578.104 | 54140.184
EST-0031 | P-1005 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 463 | 81.76 | Medium | E-0007 | 2026-02-03 | Fatima Cohen | 10% | 37854.88 | 3785.488 | 41640.368
EST-0032 | P-1005 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 716 | 81.76 | Medium | E-0007 | 2026-02-03 | Fatima Cohen | 10% | 58540.16 | 5854.016 | 64394.176
EST-0033 | P-1005 | v1 Baseline | No | 3.0 | Build | Engineering | 1866 | 81.76 | Medium | E-0007 | 2026-02-03 | Fatima Cohen | 10% | 152564.16 | 15256.416 | 167820.576
EST-0034 | P-1005 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 901 | 81.76 | Medium | E-0007 | 2026-02-03 | Fatima Cohen | 10% | 73665.76 | 7366.576 | 81032.336
EST-0035 | P-1005 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 500 | 81.76 | Medium | E-0007 | 2026-02-03 | Fatima Cohen | 10% | 40880 | 4088 | 44968
EST-0036 | P-1005 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 573 | 83.4 | Medium | E-0007 | 2026-07-15 | Fatima Cohen | 10% | 47788.2 | 4778.82 | 52567.02
EST-0037 | P-1005 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1054 | 83.4 | Medium | E-0007 | 2026-07-15 | Fatima Cohen | 10% | 87903.6 | 8790.36 | 96693.96
EST-0038 | P-1005 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 3483 | 83.4 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 290482.2 | 43572.33 | 334054.53
EST-0039 | P-1005 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1822 | 83.4 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 151954.8 | 22793.22 | 174748.02
EST-0040 | P-1005 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 971 | 83.4 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 80981.4 | 12147.21 | 93128.61
EST-0041 | P-1006 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 736 | 69.63 | Medium | E-0009 | 2025-09-07 | Olivia Silva | 10% | 51247.68 | 5124.768 | 56372.448
EST-0042 | P-1006 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 1076 | 69.63 | Medium | E-0009 | 2025-09-07 | Olivia Silva | 10% | 74921.88 | 7492.188 | 82414.068
EST-0043 | P-1006 | v1 Baseline | No | 3.0 | Build | Engineering | 2790 | 69.63 | Medium | E-0009 | 2025-09-07 | Olivia Silva | 10% | 194267.7 | 19426.77 | 213694.47
EST-0044 | P-1006 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 1336 | 69.63 | Medium | E-0009 | 2025-09-07 | Olivia Silva | 10% | 93025.68 | 9302.568 | 102328.248
EST-0045 | P-1006 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 613 | 69.63 | Medium | E-0009 | 2025-09-07 | Olivia Silva | 10% | 42683.19 | 4268.319 | 46951.509
EST-0046 | P-1006 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 798 | 71.02 | Medium | E-0009 | 2026-07-15 | Olivia Silva | 10% | 56673.96 | 5667.396 | 62341.356
EST-0047 | P-1006 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1257 | 71.02 | Medium | E-0009 | 2026-07-15 | Olivia Silva | 10% | 89272.14 | 8927.214 | 98199.354
EST-0048 | P-1006 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 3654 | 71.02 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 259507.08 | 38926.062 | 298433.142
EST-0049 | P-1006 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1826 | 71.02 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 129682.52 | 19452.378 | 149134.898
EST-0050 | P-1006 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 820 | 71.02 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 58236.4 | 8735.46 | 66971.86
EST-0051 | P-1007 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 551 | 80.74 | High | E-0008 | 2026-02-21 | Ethan Park | 5% | 44487.74 | 2224.387 | 46712.127
EST-0052 | P-1007 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 969 | 80.74 | High | E-0008 | 2026-02-21 | Ethan Park | 5% | 78237.06 | 3911.853 | 82148.913
EST-0053 | P-1007 | v1 Baseline | Yes | 3.0 | Build | Engineering | 2694 | 80.74 | Medium | E-0008 | 2026-02-21 | Ethan Park | 10% | 217513.56 | 21751.356 | 239264.916
EST-0054 | P-1007 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1166 | 80.74 | High | E-0008 | 2026-02-21 | Ethan Park | 5% | 94142.84 | 4707.142 | 98849.982
EST-0055 | P-1007 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 554 | 80.74 | High | E-0008 | 2026-02-21 | Ethan Park | 5% | 44729.96 | 2236.498 | 46966.458
EST-0056 | P-1008 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 366 | 101.83 | Medium | E-0010 | 2025-12-14 | Arjun Baptiste | 10% | 37269.78 | 3726.978 | 40996.758
EST-0057 | P-1008 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 596 | 101.83 | Medium | E-0010 | 2025-12-14 | Arjun Baptiste | 10% | 60690.68 | 6069.068 | 66759.748
EST-0058 | P-1008 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1443 | 101.83 | Medium | E-0010 | 2025-12-14 | Arjun Baptiste | 10% | 146940.69 | 14694.069 | 161634.759
EST-0059 | P-1008 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 712 | 101.83 | Medium | E-0010 | 2025-12-14 | Arjun Baptiste | 10% | 72502.96 | 7250.296 | 79753.256
EST-0060 | P-1008 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 389 | 101.83 | Medium | E-0010 | 2025-12-14 | Arjun Baptiste | 10% | 39611.87 | 3961.187 | 43573.057
EST-0061 | P-1009 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 345 | 74.76 | High | E-0005 | 2026-04-03 | Mei Fraser | 5% | 25792.2 | 1289.61 | 27081.81
EST-0062 | P-1009 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 588 | 74.76 | High | E-0005 | 2026-04-03 | Mei Fraser | 5% | 43958.88 | 2197.944 | 46156.824
EST-0063 | P-1009 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1543 | 74.76 | Medium | E-0005 | 2026-04-03 | Mei Fraser | 10% | 115354.68 | 11535.468 | 126890.148
EST-0064 | P-1009 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 812 | 74.76 | High | E-0005 | 2026-04-03 | Mei Fraser | 5% | 60705.12 | 3035.256 | 63740.376
EST-0065 | P-1009 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 411 | 74.76 | High | E-0005 | 2026-04-03 | Mei Fraser | 5% | 30726.36 | 1536.318 | 32262.678
EST-0066 | P-1010 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 408 | 80.21 | Medium | E-0007 | 2025-11-08 | Fatima Cohen | 10% | 32725.68 | 3272.568 | 35998.248
EST-0067 | P-1010 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 723 | 80.21 | Medium | E-0007 | 2025-11-08 | Fatima Cohen | 10% | 57991.83 | 5799.183 | 63791.013
EST-0068 | P-1010 | v1 Baseline | No | 3.0 | Build | Engineering | 1878 | 80.21 | Medium | E-0007 | 2025-11-08 | Fatima Cohen | 10% | 150634.38 | 15063.438 | 165697.818
EST-0069 | P-1010 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 967 | 80.21 | Medium | E-0007 | 2025-11-08 | Fatima Cohen | 10% | 77563.07 | 7756.307 | 85319.377
EST-0070 | P-1010 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 431 | 80.21 | Medium | E-0007 | 2025-11-08 | Fatima Cohen | 10% | 34570.51 | 3457.051 | 38027.561
EST-0071 | P-1010 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 465 | 81.81 | Medium | E-0007 | 2026-07-15 | Fatima Cohen | 10% | 38041.65 | 3804.165 | 41845.815
EST-0072 | P-1010 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 924 | 81.81 | Medium | E-0007 | 2026-07-15 | Fatima Cohen | 10% | 75592.44 | 7559.244 | 83151.684
EST-0073 | P-1010 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 2833 | 81.81 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 231767.73 | 34765.1595 | 266532.8895
EST-0074 | P-1010 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1548 | 81.81 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 126641.88 | 18996.282 | 145638.162
EST-0075 | P-1010 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 671 | 81.81 | Low | E-0007 | 2026-07-15 | Fatima Cohen | 15% | 54894.51 | 8234.1765 | 63128.6865
EST-0076 | P-1011 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 594 | 88.24 | High | E-0006 | 2026-01-04 | Noah Rahimi | 5% | 52414.56 | 2620.728 | 55035.288
EST-0077 | P-1011 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 888 | 88.24 | High | E-0006 | 2026-01-04 | Noah Rahimi | 5% | 78357.12 | 3917.856 | 82274.976
EST-0078 | P-1011 | v1 Baseline | Yes | 3.0 | Build | Engineering | 2324 | 88.24 | Medium | E-0006 | 2026-01-04 | Noah Rahimi | 10% | 205069.76 | 20506.976 | 225576.736
EST-0079 | P-1011 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1238 | 88.24 | High | E-0006 | 2026-01-04 | Noah Rahimi | 5% | 109241.12 | 5462.056 | 114703.176
EST-0080 | P-1011 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 624 | 88.24 | High | E-0006 | 2026-01-04 | Noah Rahimi | 5% | 55061.76 | 2753.088 | 57814.848
EST-0081 | P-1012 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 322 | 90.53 | High | E-0010 | 2026-04-18 | Arjun Baptiste | 5% | 29150.66 | 1457.533 | 30608.193
EST-0082 | P-1012 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 502 | 90.53 | High | E-0010 | 2026-04-18 | Arjun Baptiste | 5% | 45446.06 | 2272.303 | 47718.363
EST-0083 | P-1012 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1314 | 90.53 | Medium | E-0010 | 2026-04-18 | Arjun Baptiste | 10% | 118956.42 | 11895.642 | 130852.062
EST-0084 | P-1012 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 627 | 90.53 | High | E-0010 | 2026-04-18 | Arjun Baptiste | 5% | 56762.31 | 2838.1155 | 59600.4255
EST-0085 | P-1012 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 303 | 90.53 | High | E-0010 | 2026-04-18 | Arjun Baptiste | 5% | 27430.59 | 1371.5295 | 28802.1195
EST-0086 | P-1013 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 821 | 81.15 | Low | E-0004 | 2025-07-12 | Liam Roy | 15% | 66624.15 | 9993.6225 | 76617.7725
EST-0087 | P-1013 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 1390 | 81.15 | Low | E-0004 | 2025-07-12 | Liam Roy | 15% | 112798.5 | 16919.775 | 129718.275
EST-0088 | P-1013 | v1 Baseline | No | 3.0 | Build | Engineering | 3415 | 81.15 | Low | E-0004 | 2025-07-12 | Liam Roy | 15% | 277127.25 | 41569.0875 | 318696.3375
EST-0089 | P-1013 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 1767 | 81.15 | Low | E-0004 | 2025-07-12 | Liam Roy | 15% | 143392.05 | 21508.8075 | 164900.8575
EST-0090 | P-1013 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 831 | 81.15 | Low | E-0004 | 2025-07-12 | Liam Roy | 15% | 67435.65 | 10115.3475 | 77550.9975
EST-0091 | P-1013 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 906 | 82.77 | Medium | E-0004 | 2026-07-15 | Liam Roy | 10% | 74989.62 | 7498.962 | 82488.582
EST-0092 | P-1013 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1681 | 82.77 | Medium | E-0004 | 2026-07-15 | Liam Roy | 10% | 139136.37 | 13913.637 | 153050.007
EST-0093 | P-1013 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 4723 | 82.77 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 390922.71 | 58638.4065 | 449561.1165
EST-0094 | P-1013 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 2567 | 82.77 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 212470.59 | 31870.5885 | 244341.1785
EST-0095 | P-1013 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 1178 | 82.77 | Low | E-0004 | 2026-07-15 | Liam Roy | 15% | 97503.06 | 14625.459 | 112128.519
EST-0096 | P-1014 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 685 | 101.09 | High | E-0008 | 2025-05-27 | Ethan Park | 5% | 69246.65 | 3462.3325 | 72708.9825
EST-0097 | P-1014 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 1124 | 101.09 | High | E-0008 | 2025-05-27 | Ethan Park | 5% | 113625.16 | 5681.258 | 119306.418
EST-0098 | P-1014 | v1 Baseline | Yes | 3.0 | Build | Engineering | 3031 | 101.09 | Medium | E-0008 | 2025-05-27 | Ethan Park | 10% | 306403.79 | 30640.379 | 337044.169
EST-0099 | P-1014 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1238 | 101.09 | High | E-0008 | 2025-05-27 | Ethan Park | 5% | 125149.42 | 6257.471 | 131406.891
EST-0100 | P-1014 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 642 | 101.09 | High | E-0008 | 2025-05-27 | Ethan Park | 5% | 64899.78 | 3244.989 | 68144.769
EST-0101 | P-1015 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 742 | 80.9 | Medium | E-0009 | 2026-02-20 | Olivia Silva | 10% | 60027.8 | 6002.78 | 66030.58
EST-0102 | P-1015 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 1303 | 80.9 | Medium | E-0009 | 2026-02-20 | Olivia Silva | 10% | 105412.7 | 10541.27 | 115953.97
EST-0103 | P-1015 | v1 Baseline | No | 3.0 | Build | Engineering | 3718 | 80.9 | Medium | E-0009 | 2026-02-20 | Olivia Silva | 10% | 300786.2 | 30078.62 | 330864.82
EST-0104 | P-1015 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 1674 | 80.9 | Medium | E-0009 | 2026-02-20 | Olivia Silva | 10% | 135426.6 | 13542.66 | 148969.26
EST-0105 | P-1015 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 743 | 80.9 | Medium | E-0009 | 2026-02-20 | Olivia Silva | 10% | 60108.7 | 6010.87 | 66119.57
EST-0106 | P-1015 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 799 | 82.52 | Medium | E-0009 | 2026-07-15 | Olivia Silva | 10% | 65933.48 | 6593.348 | 72526.828
EST-0107 | P-1015 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1501 | 82.52 | Medium | E-0009 | 2026-07-15 | Olivia Silva | 10% | 123862.52 | 12386.252 | 136248.772
EST-0108 | P-1015 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 4758 | 82.52 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 392630.16 | 58894.524 | 451524.684
EST-0109 | P-1015 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 2227 | 82.52 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 183772.04 | 27565.806 | 211337.846
EST-0110 | P-1015 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 969 | 82.52 | Low | E-0009 | 2026-07-15 | Olivia Silva | 15% | 79961.88 | 11994.282 | 91956.162
EST-0111 | P-1016 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 260 | 86.65 | High | E-0003 | 2026-03-17 | Aisha Tremblay | 5% | 22529 | 1126.45 | 23655.45
EST-0112 | P-1016 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 435 | 86.65 | High | E-0003 | 2026-03-17 | Aisha Tremblay | 5% | 37692.75 | 1884.6375 | 39577.3875
EST-0113 | P-1016 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1179 | 86.65 | Medium | E-0003 | 2026-03-17 | Aisha Tremblay | 10% | 102160.35 | 10216.035 | 112376.385
EST-0114 | P-1016 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 473 | 86.65 | High | E-0003 | 2026-03-17 | Aisha Tremblay | 5% | 40985.45 | 2049.2725 | 43034.7225
EST-0115 | P-1016 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 248 | 86.65 | High | E-0003 | 2026-03-17 | Aisha Tremblay | 5% | 21489.2 | 1074.46 | 22563.66
EST-0116 | P-1017 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 346 | 74.8 | Medium | E-0005 | 2025-12-19 | Mei Fraser | 10% | 25880.8 | 2588.08 | 28468.88
EST-0117 | P-1017 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 593 | 74.8 | Medium | E-0005 | 2025-12-19 | Mei Fraser | 10% | 44356.4 | 4435.64 | 48792.04
EST-0118 | P-1017 | v1 Baseline | No | 3.0 | Build | Engineering | 1438 | 74.8 | Medium | E-0005 | 2025-12-19 | Mei Fraser | 10% | 107562.4 | 10756.24 | 118318.64
EST-0119 | P-1017 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 642 | 74.8 | Medium | E-0005 | 2025-12-19 | Mei Fraser | 10% | 48021.6 | 4802.16 | 52823.76
EST-0120 | P-1017 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 381 | 74.8 | Medium | E-0005 | 2025-12-19 | Mei Fraser | 10% | 28498.8 | 2849.88 | 31348.68
EST-0121 | P-1017 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 431 | 76.3 | Medium | E-0005 | 2026-07-15 | Mei Fraser | 10% | 32885.3 | 3288.53 | 36173.83
EST-0122 | P-1017 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 883 | 76.3 | Medium | E-0005 | 2026-07-15 | Mei Fraser | 10% | 67372.9 | 6737.29 | 74110.19
EST-0123 | P-1017 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 2724 | 76.3 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 207841.2 | 31176.18 | 239017.38
EST-0124 | P-1017 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1321 | 76.3 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 100792.3 | 15118.845 | 115911.145
EST-0125 | P-1017 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 752 | 76.3 | Low | E-0005 | 2026-07-15 | Mei Fraser | 15% | 57377.6 | 8606.64 | 65984.24
EST-0126 | P-1018 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 341 | 99.94 | High | E-0006 | 2025-05-12 | Noah Rahimi | 5% | 34079.54 | 1703.977 | 35783.517
EST-0127 | P-1018 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 468 | 99.94 | High | E-0006 | 2025-05-12 | Noah Rahimi | 5% | 46771.92 | 2338.596 | 49110.516
EST-0128 | P-1018 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1307 | 99.94 | Medium | E-0006 | 2025-05-12 | Noah Rahimi | 10% | 130621.58 | 13062.158 | 143683.738
EST-0129 | P-1018 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 611 | 99.94 | High | E-0006 | 2025-05-12 | Noah Rahimi | 5% | 61063.34 | 3053.167 | 64116.507
EST-0130 | P-1018 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 332 | 99.94 | High | E-0006 | 2025-05-12 | Noah Rahimi | 5% | 33180.08 | 1659.004 | 34839.084
EST-0131 | P-1019 | v1 Baseline | No | 1.0 | Discovery | Business & Analysis | 589 | 77.94 | Medium | E-0010 | 2025-04-15 | Arjun Baptiste | 10% | 45906.66 | 4590.666 | 50497.326
EST-0132 | P-1019 | v1 Baseline | No | 2.0 | Design | Experience & Architecture | 955 | 77.94 | Medium | E-0010 | 2025-04-15 | Arjun Baptiste | 10% | 74432.7 | 7443.27 | 81875.97
EST-0133 | P-1019 | v1 Baseline | No | 3.0 | Build | Engineering | 2579 | 77.94 | Medium | E-0010 | 2025-04-15 | Arjun Baptiste | 10% | 201007.26 | 20100.726 | 221107.986
EST-0134 | P-1019 | v1 Baseline | No | 4.0 | Test | Quality Assurance | 1124 | 77.94 | Medium | E-0010 | 2025-04-15 | Arjun Baptiste | 10% | 87604.56 | 8760.456 | 96365.016
EST-0135 | P-1019 | v1 Baseline | No | 5.0 | Deploy | Release & Change | 520 | 77.94 | Medium | E-0010 | 2025-04-15 | Arjun Baptiste | 10% | 40528.8 | 4052.88 | 44581.68
EST-0136 | P-1019 | v2 Re-forecast | Yes | 1.0 | Discovery | Business & Analysis | 603 | 79.5 | Medium | E-0010 | 2026-07-15 | Arjun Baptiste | 10% | 47938.5 | 4793.85 | 52732.35
EST-0137 | P-1019 | v2 Re-forecast | Yes | 2.0 | Design | Experience & Architecture | 1002 | 79.5 | Medium | E-0010 | 2026-07-15 | Arjun Baptiste | 10% | 79659 | 7965.9 | 87624.9
EST-0138 | P-1019 | v2 Re-forecast | Yes | 3.0 | Build | Engineering | 2809 | 79.5 | Low | E-0010 | 2026-07-15 | Arjun Baptiste | 15% | 223315.5 | 33497.325 | 256812.825
EST-0139 | P-1019 | v2 Re-forecast | Yes | 4.0 | Test | Quality Assurance | 1242 | 79.5 | Low | E-0010 | 2026-07-15 | Arjun Baptiste | 15% | 98739 | 14810.85 | 113549.85
EST-0140 | P-1019 | v2 Re-forecast | Yes | 5.0 | Deploy | Release & Change | 570 | 79.5 | Low | E-0010 | 2026-07-15 | Arjun Baptiste | 15% | 45315 | 6797.25 | 52112.25
EST-0141 | P-1020 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 328 | 91.2 | High | E-0006 | 2025-09-06 | Noah Rahimi | 5% | 29913.6 | 1495.68 | 31409.28
EST-0142 | P-1020 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 537 | 91.2 | High | E-0006 | 2025-09-06 | Noah Rahimi | 5% | 48974.4 | 2448.72 | 51423.12
EST-0143 | P-1020 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1690 | 91.2 | Medium | E-0006 | 2025-09-06 | Noah Rahimi | 10% | 154128 | 15412.8 | 169540.8
EST-0144 | P-1020 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 747 | 91.2 | High | E-0006 | 2025-09-06 | Noah Rahimi | 5% | 68126.4 | 3406.32 | 71532.72
EST-0145 | P-1020 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 342 | 91.2 | High | E-0006 | 2025-09-06 | Noah Rahimi | 5% | 31190.4 | 1559.52 | 32749.92
EST-0146 | P-1021 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 427 | 73.96 | Medium | E-0010 | 2026-01-20 | Arjun Baptiste | 10% | 31580.92 | 3158.092 | 34739.012
EST-0147 | P-1021 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 606 | 73.96 | Medium | E-0010 | 2026-01-20 | Arjun Baptiste | 10% | 44819.76 | 4481.976 | 49301.736
EST-0148 | P-1021 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1977 | 73.96 | Medium | E-0010 | 2026-01-20 | Arjun Baptiste | 10% | 146218.92 | 14621.892 | 160840.812
EST-0149 | P-1021 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 767 | 73.96 | Medium | E-0010 | 2026-01-20 | Arjun Baptiste | 10% | 56727.32 | 5672.732 | 62400.052
EST-0150 | P-1021 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 377 | 73.96 | Medium | E-0010 | 2026-01-20 | Arjun Baptiste | 10% | 27882.92 | 2788.292 | 30671.212
EST-0151 | P-1022 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 345 | 76.9 | Medium | E-0003 | 2026-08-21 | Aisha Tremblay | 10% | 26530.5 | 2653.05 | 29183.55
EST-0152 | P-1022 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 550 | 76.9 | Medium | E-0003 | 2026-08-21 | Aisha Tremblay | 10% | 42295 | 4229.5 | 46524.5
EST-0153 | P-1022 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1411 | 76.9 | Medium | E-0003 | 2026-08-21 | Aisha Tremblay | 10% | 108505.9 | 10850.59 | 119356.49
EST-0154 | P-1022 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 718 | 76.9 | Medium | E-0003 | 2026-08-21 | Aisha Tremblay | 10% | 55214.2 | 5521.42 | 60735.62
EST-0155 | P-1022 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 378 | 76.9 | Medium | E-0003 | 2026-08-21 | Aisha Tremblay | 10% | 29068.2 | 2906.82 | 31975.02
EST-0156 | P-1023 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 284 | 94.84 | Medium | E-0004 | 2026-09-30 | Liam Roy | 10% | 26934.56 | 2693.456 | 29628.016
EST-0157 | P-1023 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 467 | 94.84 | Medium | E-0004 | 2026-09-30 | Liam Roy | 10% | 44290.28 | 4429.028 | 48719.308
EST-0158 | P-1023 | v1 Baseline | Yes | 3.0 | Build | Engineering | 1250 | 94.84 | Medium | E-0004 | 2026-09-30 | Liam Roy | 10% | 118550 | 11855 | 130405
EST-0159 | P-1023 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 583 | 94.84 | Medium | E-0004 | 2026-09-30 | Liam Roy | 10% | 55291.72 | 5529.172 | 60820.892
EST-0160 | P-1023 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 271 | 94.84 | Medium | E-0004 | 2026-09-30 | Liam Roy | 10% | 25701.64 | 2570.164 | 28271.804
EST-0161 | P-1024 | v1 Baseline | Yes | 1.0 | Discovery | Business & Analysis | 575 | 83.86 | Medium | E-0005 | 2026-12-04 | Mei Fraser | 10% | 48219.5 | 4821.95 | 53041.45
EST-0162 | P-1024 | v1 Baseline | Yes | 2.0 | Design | Experience & Architecture | 1064 | 83.86 | Medium | E-0005 | 2026-12-04 | Mei Fraser | 10% | 89227.04 | 8922.704 | 98149.744
EST-0163 | P-1024 | v1 Baseline | Yes | 3.0 | Build | Engineering | 2711 | 83.86 | Medium | E-0005 | 2026-12-04 | Mei Fraser | 10% | 227344.46 | 22734.446 | 250078.906
EST-0164 | P-1024 | v1 Baseline | Yes | 4.0 | Test | Quality Assurance | 1187 | 83.86 | Medium | E-0005 | 2026-12-04 | Mei Fraser | 10% | 99541.82 | 9954.182 | 109496.002
EST-0165 | P-1024 | v1 Baseline | Yes | 5.0 | Deploy | Release & Change | 613 | 83.86 | Medium | E-0005 | 2026-12-04 | Mei Fraser | 10% | 51406.18 | 5140.618 | 56546.798

## Budget
BudgetLineID | ProjectID | ProjectName | CostCategory | BudgetAmount | ApprovedDate | ApprovedBy | Notes | ActualToDate | Remaining | BurnPct | LineStatus
B-0001 | P-1001 | Patient Portal Modernization | Labour | 583200 | 2025-10-09 | Gordon Achebe | From v1 baseline estimate | 487314.13 | 95885.87 | 83.56% | Within budget
B-0002 | P-1001 | Patient Portal Modernization | Software & Licences | 36100 | 2025-10-09 | Gordon Achebe |  | 29669.4 | 6430.6 | 82.19% | Within budget
B-0003 | P-1001 | Patient Portal Modernization | Subcontractors | 53200 | 2025-10-09 | Gordon Achebe |  | 42535.38 | 10664.62 | 79.95% | Within budget
B-0004 | P-1001 | Patient Portal Modernization | Travel & Expenses | 11900 | 2025-10-09 | Gordon Achebe |  | 10170.37 | 1729.63 | 85.47% | Within budget
B-0005 | P-1001 | Patient Portal Modernization | Contingency | 42100 | 2025-10-09 | Gordon Achebe | Management reserve; drawn via CR | 0 | 42100 | 0% | Reserve
B-0006 | P-1002 | Claims Automation Engine | Labour | 351300 | 2025-12-11 | Helena Marsh | From v1 baseline estimate | 320785.27 | 30514.73 | 91.31% | Near limit
B-0007 | P-1002 | Claims Automation Engine | Hardware | 28300 | 2025-12-11 | Helena Marsh |  | 35530.14 | -7230.14 | 125.5% | Overspent
B-0008 | P-1002 | Claims Automation Engine | Software & Licences | 18200 | 2025-12-11 | Helena Marsh |  | 14042.27 | 4157.73 | 77.16% | Within budget
B-0009 | P-1002 | Claims Automation Engine | Training | 9000 | 2025-12-11 | Helena Marsh |  | 7170.74 | 1829.26 | 79.67% | Within budget
B-0010 | P-1002 | Claims Automation Engine | Travel & Expenses | 6600 | 2025-12-11 | Helena Marsh |  | 5026.16 | 1573.84 | 76.15% | Within budget
B-0011 | P-1002 | Claims Automation Engine | Contingency | 52700 | 2025-12-11 | Helena Marsh | Management reserve; drawn via CR | 0 | 52700 | 0% | Reserve
B-0012 | P-1003 | Enterprise Data Lakehouse | Labour | 576600 | 2025-08-15 | Gordon Achebe | From v1 baseline estimate | 526031.85 | 50568.15 | 91.23% | Near limit
B-0013 | P-1003 | Enterprise Data Lakehouse | Cloud Hosting | 59300 | 2025-08-15 | Gordon Achebe |  | 49511.47 | 9788.53 | 83.49% | Within budget
B-0014 | P-1003 | Enterprise Data Lakehouse | Software & Licences | 39100 | 2025-08-15 | Gordon Achebe |  | 32748.66 | 6351.34 | 83.76% | Within budget
B-0015 | P-1003 | Enterprise Data Lakehouse | Travel & Expenses | 8100 | 2025-08-15 | Gordon Achebe |  | 6516.17 | 1583.83 | 80.45% | Within budget
B-0016 | P-1003 | Enterprise Data Lakehouse | Contingency | 86500 | 2025-08-15 | Gordon Achebe | Management reserve; drawn via CR | 0 | 86500 | 0% | Reserve
B-0017 | P-1004 | Cloud Migration Wave 2 | Labour | 524600 | 2026-01-07 | Gordon Achebe | From v1 baseline estimate | 316771 | 207829 | 60.38% | Within budget
B-0018 | P-1004 | Cloud Migration Wave 2 | Cloud Hosting | 80300 | 2026-01-07 | Gordon Achebe |  | 46125.84 | 34174.16 | 57.44% | Within budget
B-0019 | P-1004 | Cloud Migration Wave 2 | Hardware | 55800 | 2026-01-07 | Gordon Achebe |  | 54839.11 | 960.89 | 98.28% | Near limit
B-0020 | P-1004 | Cloud Migration Wave 2 | Software & Licences | 29500 | 2026-01-07 | Gordon Achebe |  | 16733.21 | 12766.79 | 56.72% | Within budget
B-0021 | P-1004 | Cloud Migration Wave 2 | Travel & Expenses | 10800 | 2026-01-07 | Gordon Achebe |  | 6368.56 | 4431.44 | 58.97% | Within budget
B-0022 | P-1004 | Cloud Migration Wave 2 | Contingency | 37500 | 2026-01-07 | Gordon Achebe | Management reserve; drawn via CR | 0 | 37500 | 0% | Reserve
B-0023 | P-1005 | Fraud Detection ML Platform | Labour | 363500 | 2026-02-20 | Helena Marsh | From v1 baseline estimate | 255129.66 | 108370.34 | 70.19% | Within budget
B-0024 | P-1005 | Fraud Detection ML Platform | Cloud Hosting | 32500 | 2026-02-20 | Helena Marsh |  | 18578.25 | 13921.75 | 57.16% | Within budget
B-0025 | P-1005 | Fraud Detection ML Platform | Software & Licences | 21800 | 2026-02-20 | Helena Marsh |  | 12550.75 | 9249.25 | 57.57% | Within budget
B-0026 | P-1005 | Fraud Detection ML Platform | Travel & Expenses | 5000 | 2026-02-20 | Helena Marsh |  | 3045.04 | 1954.96 | 60.9% | Within budget
B-0027 | P-1005 | Fraud Detection ML Platform | Contingency | 36400 | 2026-02-20 | Helena Marsh | Management reserve; drawn via CR | 0 | 36400 | 0% | Reserve
B-0028 | P-1006 | Omnichannel Commerce Replatform | Labour | 456100 | 2025-09-17 | Gordon Achebe | From v1 baseline estimate | 541027.58 | -84927.58 | 118.6% | Overspent
B-0029 | P-1006 | Omnichannel Commerce Replatform | Software & Licences | 27700 | 2025-09-17 | Gordon Achebe |  | 27669.73 | 30.27 | 99.89% | Near limit
B-0030 | P-1006 | Omnichannel Commerce Replatform | Subcontractors | 44700 | 2025-09-17 | Gordon Achebe |  | 45403.06 | -703.06 | 101.6% | Overspent
B-0031 | P-1006 | Omnichannel Commerce Replatform | Travel & Expenses | 8200 | 2025-09-17 | Gordon Achebe |  | 8297.12 | -97.12 | 101.2% | Overspent
B-0032 | P-1006 | Omnichannel Commerce Replatform | Contingency | 45600 | 2025-09-17 | Gordon Achebe | Management reserve; drawn via CR | 0 | 45600 | 0% | Reserve
B-0033 | P-1007 | Student Information System Upgrade | Labour | 479100 | 2026-03-02 | Gordon Achebe | From v1 baseline estimate | 197864.45 | 281235.55 | 41.3% | Within budget
B-0034 | P-1007 | Student Information System Upgrade | Software & Licences | 42800 | 2026-03-02 | Gordon Achebe |  | 18377.24 | 24422.76 | 42.94% | Within budget
B-0035 | P-1007 | Student Information System Upgrade | Subcontractors | 57600 | 2026-03-02 | Gordon Achebe |  | 23055.89 | 34544.11 | 40.03% | Within budget
B-0036 | P-1007 | Student Information System Upgrade | Training | 15400 | 2026-03-02 | Gordon Achebe |  | 6712.26 | 8687.74 | 43.59% | Within budget
B-0037 | P-1007 | Student Information System Upgrade | Travel & Expenses | 9700 | 2026-03-02 | Gordon Achebe |  | 3944.09 | 5755.91 | 40.66% | Within budget
B-0038 | P-1007 | Student Information System Upgrade | Contingency | 34800 | 2026-03-02 | Gordon Achebe | Management reserve; drawn via CR | 0 | 34800 | 0% | Reserve
B-0039 | P-1008 | Network Operations Centre Refresh | Labour | 357000 | 2025-12-28 | Gordon Achebe | From v1 baseline estimate | 365748.08 | -8748.08 | 102.5% | Overspent
B-0040 | P-1008 | Network Operations Centre Refresh | Cloud Hosting | 47200 | 2025-12-28 | Gordon Achebe |  | 39491.94 | 7708.06 | 83.67% | Within budget
B-0041 | P-1008 | Network Operations Centre Refresh | Hardware | 30700 | 2025-12-28 | Gordon Achebe |  | 34396.08 | -3696.08 | 112% | Overspent
B-0042 | P-1008 | Network Operations Centre Refresh | Software & Licences | 20000 | 2025-12-28 | Gordon Achebe |  | 17751.31 | 2248.69 | 88.76% | Within budget
B-0043 | P-1008 | Network Operations Centre Refresh | Travel & Expenses | 7900 | 2025-12-28 | Gordon Achebe |  | 7062.45 | 837.55 | 89.4% | Within budget
B-0044 | P-1008 | Network Operations Centre Refresh | Contingency | 35700 | 2025-12-28 | Gordon Achebe | Management reserve; drawn via CR | 0 | 35700 | 0% | Reserve
B-0045 | P-1009 | Smart Factory IoT Pilot | Labour | 276500 | 2026-04-21 | Helena Marsh | From v1 baseline estimate | 135647.6 | 140852.4 | 49.06% | Within budget
B-0046 | P-1009 | Smart Factory IoT Pilot | Hardware | 22100 | 2026-04-21 | Helena Marsh |  | 13460.95 | 8639.05 | 60.91% | Within budget
B-0047 | P-1009 | Smart Factory IoT Pilot | Software & Licences | 11800 | 2026-04-21 | Helena Marsh |  | 5465.55 | 6334.45 | 46.32% | Within budget
B-0048 | P-1009 | Smart Factory IoT Pilot | Training | 7100 | 2026-04-21 | Helena Marsh |  | 3505.57 | 3594.43 | 49.37% | Within budget
B-0049 | P-1009 | Smart Factory IoT Pilot | Travel & Expenses | 5600 | 2026-04-21 | Helena Marsh |  | 2675.86 | 2924.14 | 47.78% | Within budget
B-0050 | P-1009 | Smart Factory IoT Pilot | Contingency | 19600 | 2026-04-21 | Helena Marsh | Management reserve; drawn via CR | 0 | 19600 | 0% | Reserve
B-0051 | P-1010 | 311 Citizen Services App | Labour | 353500 | 2025-11-20 | Helena Marsh | From v1 baseline estimate | 442230.06 | -88730.06 | 125.1% | Overspent
B-0052 | P-1010 | 311 Citizen Services App | Software & Licences | 27700 | 2025-11-20 | Helena Marsh |  | 29598.47 | -1898.47 | 106.9% | Overspent
B-0053 | P-1010 | 311 Citizen Services App | Subcontractors | 31700 | 2025-11-20 | Helena Marsh |  | 34686.34 | -2986.34 | 109.4% | Overspent
B-0054 | P-1010 | 311 Citizen Services App | Travel & Expenses | 6800 | 2025-11-20 | Helena Marsh |  | 7327.43 | -527.43 | 107.8% | Overspent
B-0055 | P-1010 | 311 Citizen Services App | Contingency | 35300 | 2025-11-20 | Helena Marsh | Management reserve; drawn via CR | 0 | 35300 | 0% | Reserve
B-0056 | P-1011 | Clinical Trials Data Hub | Labour | 500100 | 2026-01-17 | Gordon Achebe | From v1 baseline estimate | 209301.16 | 290798.84 | 41.85% | Within budget
B-0057 | P-1011 | Clinical Trials Data Hub | Cloud Hosting | 43900 | 2026-01-17 | Gordon Achebe |  | 20246.91 | 23653.09 | 46.12% | Within budget
B-0058 | P-1011 | Clinical Trials Data Hub | Software & Licences | 34200 | 2026-01-17 | Gordon Achebe |  | 15413.36 | 18786.64 | 45.07% | Within budget
B-0059 | P-1011 | Clinical Trials Data Hub | Travel & Expenses | 7200 | 2026-01-17 | Gordon Achebe |  | 3335.98 | 3864.02 | 46.33% | Within budget
B-0060 | P-1011 | Clinical Trials Data Hub | Contingency | 35300 | 2026-01-17 | Gordon Achebe | Management reserve; drawn via CR | 0 | 35300 | 0% | Reserve
B-0061 | P-1012 | Grid Analytics Dashboard | Labour | 277700 | 2026-05-06 | Gordon Achebe | From v1 baseline estimate | 121112.82 | 156587.18 | 43.61% | Within budget
B-0062 | P-1012 | Grid Analytics Dashboard | Cloud Hosting | 28600 | 2026-05-06 | Gordon Achebe |  | 12344.9 | 16255.1 | 43.16% | Within budget
B-0063 | P-1012 | Grid Analytics Dashboard | Software & Licences | 16100 | 2026-05-06 | Gordon Achebe |  | 7072.57 | 9027.43 | 43.93% | Within budget
B-0064 | P-1012 | Grid Analytics Dashboard | Travel & Expenses | 4300 | 2026-05-06 | Gordon Achebe |  | 1730.53 | 2569.47 | 40.24% | Within budget
B-0065 | P-1012 | Grid Analytics Dashboard | Contingency | 19800 | 2026-05-06 | Gordon Achebe | Management reserve; drawn via CR | 0 | 19800 | 0% | Reserve
B-0066 | P-1013 | Core Banking API Layer | Labour | 667400 | 2025-07-28 | Gordon Achebe | From v1 baseline estimate | 742205.97 | -74805.97 | 111.2% | Overspent
B-0067 | P-1013 | Core Banking API Layer | Software & Licences | 56000 | 2025-07-28 | Gordon Achebe |  | 52279.5 | 3720.5 | 93.36% | Near limit
B-0068 | P-1013 | Core Banking API Layer | Subcontractors | 77000 | 2025-07-28 | Gordon Achebe |  | 72540.8 | 4459.2 | 94.21% | Near limit
B-0069 | P-1013 | Core Banking API Layer | Training | 19500 | 2025-07-28 | Gordon Achebe |  | 18815.52 | 684.48 | 96.49% | Near limit
B-0070 | P-1013 | Core Banking API Layer | Travel & Expenses | 14500 | 2025-07-28 | Gordon Achebe |  | 13958.69 | 541.31 | 96.27% | Near limit
B-0071 | P-1013 | Core Banking API Layer | Contingency | 100100 | 2025-07-28 | Gordon Achebe | Management reserve; drawn via CR | 0 | 100100 | 0% | Reserve
B-0072 | P-1014 | Managed Cloud Operations | Labour | 679300 | 2025-06-12 | Helena Marsh | From v1 baseline estimate | 543368.13 | 135931.87 | 79.99% | Within budget
B-0073 | P-1014 | Managed Cloud Operations | Cloud Hosting | 93200 | 2025-06-12 | Helena Marsh |  | 72602.16 | 20597.84 | 77.9% | Within budget
B-0074 | P-1014 | Managed Cloud Operations | Hardware | 75600 | 2025-06-12 | Helena Marsh |  | 75398.73 | 201.27 | 99.73% | Near limit
B-0075 | P-1014 | Managed Cloud Operations | Software & Licences | 33100 | 2025-06-12 | Helena Marsh |  | 24630.91 | 8469.09 | 74.41% | Within budget
B-0076 | P-1014 | Managed Cloud Operations | Travel & Expenses | 13400 | 2025-06-12 | Helena Marsh |  | 10209.65 | 3190.35 | 76.19% | Within budget
B-0077 | P-1014 | Managed Cloud Operations | Contingency | 49300 | 2025-06-12 | Helena Marsh | Management reserve; drawn via CR | 0 | 49300 | 0% | Reserve
B-0078 | P-1015 | Policy Admin Consolidation | Labour | 661800 | 2026-03-03 | Gordon Achebe | From v1 baseline estimate | 272909.89 | 388890.11 | 41.24% | Within budget
B-0079 | P-1015 | Policy Admin Consolidation | Software & Licences | 60200 | 2026-03-03 | Gordon Achebe |  | 24291.8 | 35908.2 | 40.35% | Within budget
B-0080 | P-1015 | Policy Admin Consolidation | Subcontractors | 71100 | 2026-03-03 | Gordon Achebe |  | 28461.26 | 42638.74 | 40.03% | Within budget
B-0081 | P-1015 | Policy Admin Consolidation | Training | 19100 | 2026-03-03 | Gordon Achebe |  | 8001.7 | 11098.3 | 41.89% | Within budget
B-0082 | P-1015 | Policy Admin Consolidation | Travel & Expenses | 14400 | 2026-03-03 | Gordon Achebe |  | 6086.18 | 8313.82 | 42.27% | Within budget
B-0083 | P-1015 | Policy Admin Consolidation | Contingency | 66200 | 2026-03-03 | Gordon Achebe | Management reserve; drawn via CR | 0 | 66200 | 0% | Reserve
B-0084 | P-1016 | Warehouse Robotics Integration | Labour | 224900 | 2026-03-25 | Helena Marsh | From v1 baseline estimate | 134731.62 | 90168.38 | 59.91% | Within budget
B-0085 | P-1016 | Warehouse Robotics Integration | Hardware | 20600 | 2026-03-25 | Helena Marsh |  | 20222.4 | 377.6 | 98.17% | Near limit
B-0086 | P-1016 | Warehouse Robotics Integration | Software & Licences | 11100 | 2026-03-25 | Helena Marsh |  | 7017.05 | 4082.95 | 63.22% | Within budget
B-0087 | P-1016 | Warehouse Robotics Integration | Training | 6100 | 2026-03-25 | Helena Marsh |  | 3771.52 | 2328.48 | 61.83% | Within budget
B-0088 | P-1016 | Warehouse Robotics Integration | Travel & Expenses | 4600 | 2026-03-25 | Helena Marsh |  | 2869.44 | 1730.56 | 62.38% | Within budget
B-0089 | P-1016 | Warehouse Robotics Integration | Contingency | 16400 | 2026-03-25 | Helena Marsh | Management reserve; drawn via CR | 0 | 16400 | 0% | Reserve
B-0090 | P-1017 | Loyalty Program Relaunch | Labour | 254300 | 2026-01-02 | Helena Marsh | From v1 baseline estimate | 323638.17 | -69338.17 | 127.3% | Overspent
B-0091 | P-1017 | Loyalty Program Relaunch | Software & Licences | 17200 | 2026-01-02 | Helena Marsh |  | 17904.88 | -704.88 | 104.1% | Overspent
B-0092 | P-1017 | Loyalty Program Relaunch | Subcontractors | 22400 | 2026-01-02 | Helena Marsh |  | 24550.03 | -2150.03 | 109.6% | Overspent
B-0093 | P-1017 | Loyalty Program Relaunch | Travel & Expenses | 4700 | 2026-01-02 | Helena Marsh |  | 5102.35 | -402.35 | 108.6% | Overspent
B-0094 | P-1017 | Loyalty Program Relaunch | Contingency | 25400 | 2026-01-02 | Helena Marsh | Management reserve; drawn via CR | 0 | 25400 | 0% | Reserve
B-0095 | P-1018 | Cybersecurity Posture Assessment | Labour | 305700 | 2025-05-26 | Helena Marsh | From v1 baseline estimate | 297113.52 | 8586.48 | 97.19% | Near limit
B-0096 | P-1018 | Cybersecurity Posture Assessment | Cloud Hosting | 42200 | 2025-05-26 | Helena Marsh |  | 39781.05 | 2418.95 | 94.27% | Near limit
B-0097 | P-1018 | Cybersecurity Posture Assessment | Hardware | 32700 | 2025-05-26 | Helena Marsh |  | 31326.96 | 1373.04 | 95.8% | Near limit
B-0098 | P-1018 | Cybersecurity Posture Assessment | Software & Licences | 13800 | 2025-05-26 | Helena Marsh |  | 12874.54 | 925.46 | 93.29% | Near limit
B-0099 | P-1018 | Cybersecurity Posture Assessment | Travel & Expenses | 5700 | 2025-05-26 | Helena Marsh |  | 5454.26 | 245.74 | 95.69% | Near limit
B-0100 | P-1018 | Cybersecurity Posture Assessment | Contingency | 21800 | 2025-05-26 | Helena Marsh | Management reserve; drawn via CR | 0 | 21800 | 0% | Reserve
B-0101 | P-1019 | HR Self-Service Portal | Labour | 449500 | 2025-04-26 | Helena Marsh | From v1 baseline estimate | 558392.05 | -108892.05 | 124.2% | Overspent
B-0102 | P-1019 | HR Self-Service Portal | Software & Licences | 33900 | 2025-04-26 | Helena Marsh |  | 41866.73 | -7966.73 | 123.5% | Overspent
B-0103 | P-1019 | HR Self-Service Portal | Subcontractors | 57500 | 2025-04-26 | Helena Marsh |  | 71179.99 | -13679.99 | 123.8% | Overspent
B-0104 | P-1019 | HR Self-Service Portal | Training | 14200 | 2025-04-26 | Helena Marsh |  | 17158.41 | -2958.41 | 120.8% | Overspent
B-0105 | P-1019 | HR Self-Service Portal | Travel & Expenses | 9200 | 2025-04-26 | Helena Marsh |  | 11228.8 | -2028.8 | 122.1% | Overspent
B-0106 | P-1019 | HR Self-Service Portal | Contingency | 44900 | 2025-04-26 | Helena Marsh | Management reserve; drawn via CR | 0 | 44900 | 0% | Reserve
B-0107 | P-1020 | Demand Forecasting Model | Labour | 332300 | 2025-09-17 | Helena Marsh | From v1 baseline estimate | 322840.23 | 9459.77 | 97.15% | Near limit
B-0108 | P-1020 | Demand Forecasting Model | Cloud Hosting | 31000 | 2025-09-17 | Helena Marsh |  | 29657.05 | 1342.95 | 95.67% | Near limit
B-0109 | P-1020 | Demand Forecasting Model | Software & Licences | 20600 | 2025-09-17 | Helena Marsh |  | 19352.68 | 1247.32 | 93.95% | Near limit
B-0110 | P-1020 | Demand Forecasting Model | Travel & Expenses | 4700 | 2025-09-17 | Helena Marsh |  | 4706.94 | -6.94 | 100.1% | Overspent
B-0111 | P-1020 | Demand Forecasting Model | Contingency | 24300 | 2025-09-17 | Helena Marsh | Management reserve; drawn via CR | 0 | 24300 | 0% | Reserve
B-0112 | P-1021 | Field Service Mobile App | Labour | 307200 | 2026-01-27 | Gordon Achebe | From v1 baseline estimate | 148835.43 | 158364.57 | 48.45% | Within budget
B-0113 | P-1021 | Field Service Mobile App | Hardware | 30500 | 2026-01-27 | Gordon Achebe |  | 18097.28 | 12402.72 | 59.34% | Within budget
B-0114 | P-1021 | Field Service Mobile App | Software & Licences | 15200 | 2026-01-27 | Gordon Achebe |  | 8362.39 | 6837.61 | 55.02% | Within budget
B-0115 | P-1021 | Field Service Mobile App | Training | 8300 | 2026-01-27 | Gordon Achebe |  | 4724.28 | 3575.72 | 56.92% | Within budget
B-0116 | P-1021 | Field Service Mobile App | Travel & Expenses | 6700 | 2026-01-27 | Gordon Achebe |  | 3576.49 | 3123.51 | 53.38% | Within budget
B-0117 | P-1021 | Field Service Mobile App | Contingency | 30700 | 2026-01-27 | Gordon Achebe | Management reserve; drawn via CR | 0 | 30700 | 0% | Reserve
B-0118 | P-1022 | Regulatory Reporting Automation | Labour | 261600 | 2026-09-01 | Gordon Achebe | From v1 baseline estimate | 0 | 261600 | 0% | Within budget
B-0119 | P-1022 | Regulatory Reporting Automation | Hardware | 26000 | 2026-09-01 | Gordon Achebe |  | 0 | 26000 | 0% | Within budget
B-0120 | P-1022 | Regulatory Reporting Automation | Software & Licences | 12700 | 2026-09-01 | Gordon Achebe |  | 0 | 12700 | 0% | Within budget
B-0121 | P-1022 | Regulatory Reporting Automation | Training | 8400 | 2026-09-01 | Gordon Achebe |  | 0 | 8400 | 0% | Within budget
B-0122 | P-1022 | Regulatory Reporting Automation | Travel & Expenses | 5600 | 2026-09-01 | Gordon Achebe |  | 0 | 5600 | 0% | Within budget
B-0123 | P-1022 | Regulatory Reporting Automation | Contingency | 26200 | 2026-09-01 | Gordon Achebe | Management reserve; drawn via CR | 0 | 26200 | 0% | Reserve
B-0124 | P-1023 | GenAI Knowledge Assistant | Labour | 270800 | 2026-10-12 | Gordon Achebe | From v1 baseline estimate | 0 | 270800 | 0% | Within budget
B-0125 | P-1023 | GenAI Knowledge Assistant | Cloud Hosting | 22000 | 2026-10-12 | Gordon Achebe |  | 0 | 22000 | 0% | Within budget
B-0126 | P-1023 | GenAI Knowledge Assistant | Software & Licences | 15400 | 2026-10-12 | Gordon Achebe |  | 0 | 15400 | 0% | Within budget
B-0127 | P-1023 | GenAI Knowledge Assistant | Travel & Expenses | 4700 | 2026-10-12 | Gordon Achebe |  | 0 | 4700 | 0% | Within budget
B-0128 | P-1023 | GenAI Knowledge Assistant | Contingency | 27100 | 2026-10-12 | Gordon Achebe | Management reserve; drawn via CR | 0 | 27100 | 0% | Reserve
B-0129 | P-1024 | Municipal Asset Management | Labour | 515700 | 2026-12-19 | Gordon Achebe | From v1 baseline estimate | 0 | 515700 | 0% | Within budget
B-0130 | P-1024 | Municipal Asset Management | Software & Licences | 37100 | 2026-12-19 | Gordon Achebe |  | 0 | 37100 | 0% | Within budget
B-0131 | P-1024 | Municipal Asset Management | Subcontractors | 66800 | 2026-12-19 | Gordon Achebe |  | 0 | 66800 | 0% | Within budget
B-0132 | P-1024 | Municipal Asset Management | Training | 15500 | 2026-12-19 | Gordon Achebe |  | 0 | 15500 | 0% | Within budget
B-0133 | P-1024 | Municipal Asset Management | Travel & Expenses | 11800 | 2026-12-19 | Gordon Achebe |  | 0 | 11800 | 0% | Within budget
B-0134 | P-1024 | Municipal Asset Management | Contingency | 51600 | 2026-12-19 | Gordon Achebe | Management reserve; drawn via CR | 0 | 51600 | 0% | Reserve

## Actuals
ActualID | Period | ProjectID | CostCategory | EmployeeID | Vendor | Source | Hours | Billable | Amount | PeriodLabel | Portfolio | BillableValue
ACT-00001 | 2025-05-31 | P-1019 | Labour | E-0010 |  | Timesheet | 86.5 | Yes | 7612 | 2025-05 | Digital Transformation | 15137.5
ACT-00002 | 2025-05-31 | P-1019 | Labour | E-0013 |  | Timesheet | 41.9 | Yes | 5068.22 | 2025-05 | Digital Transformation | 10265.5
ACT-00003 | 2025-05-31 | P-1019 | Labour | E-0017 |  | Timesheet | 131.6 | Yes | 8322.38 | 2025-05 | Digital Transformation | 17108
ACT-00004 | 2025-05-31 | P-1019 | Labour | E-0025 |  | Timesheet | 133.3 | Yes | 14256.44 | 2025-05 | Digital Transformation | 22661
ACT-00005 | 2025-05-31 | P-1019 | Labour | E-0034 |  | Timesheet | 133.7 | Yes | 7273.28 | 2025-05 | Digital Transformation | 14707
ACT-00006 | 2025-05-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3056.49 | 2025-05 | Digital Transformation | 0
ACT-00007 | 2025-05-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5410.8 | 2025-05 | Digital Transformation | 0
ACT-00008 | 2025-05-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1502.46 | 2025-05 | Digital Transformation | 0
ACT-00009 | 2025-05-31 | P-1019 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1069.75 | 2025-05 | Digital Transformation | 0
ACT-00010 | 2025-06-30 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5405.35 | 2025-06 | Cloud & Infrastructure | 0
ACT-00011 | 2025-06-30 | P-1018 | Labour | E-0006 |  | Timesheet | 75.7 | Yes | 6661.6 | 2025-06 | Cloud & Infrastructure | 13247.5
ACT-00012 | 2025-06-30 | P-1018 | Labour | E-0012 |  | Timesheet | 37.9 | Yes | 4923.97 | 2025-06 | Cloud & Infrastructure | 9854
ACT-00013 | 2025-06-30 | P-1018 | Labour | E-0027 |  | Timesheet | 83.2 | Yes | 8266.75 | 2025-06 | Cloud & Infrastructure | 16640
ACT-00014 | 2025-06-30 | P-1018 | Labour | E-0055 |  | Timesheet | 157.3 | Yes | 17151.99 | 2025-06 | Cloud & Infrastructure | 34606
ACT-00015 | 2025-06-30 | P-1018 | Labour | E-0061 |  | Timesheet | 80.7 | Yes | 6940.2 | 2025-06 | Cloud & Infrastructure | 14122.5
ACT-00016 | 2025-06-30 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1862.73 | 2025-06 | Cloud & Infrastructure | 0
ACT-00017 | 2025-06-30 | P-1018 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 903.53 | 2025-06 | Cloud & Infrastructure | 0
ACT-00018 | 2025-06-30 | P-1019 | Labour | E-0010 |  | Timesheet | 88.4 | Yes | 7779.2 | 2025-06 | Digital Transformation | 15470
ACT-00019 | 2025-06-30 | P-1019 | Labour | E-0013 |  | Timesheet | 45.1 | Yes | 5455.3 | 2025-06 | Digital Transformation | 11049.5
ACT-00020 | 2025-06-30 | P-1019 | Labour | E-0017 |  | Timesheet | 145.4 | Yes | 9195.1 | 2025-06 | Digital Transformation | 18902
ACT-00021 | 2025-06-30 | P-1019 | Labour | E-0025 |  | Timesheet | 147.8 | Yes | 15807.21 | 2025-06 | Digital Transformation | 25126
ACT-00022 | 2025-06-30 | P-1019 | Labour | E-0034 |  | Timesheet | 148.7 | Yes | 8089.28 | 2025-06 | Digital Transformation | 16357
ACT-00023 | 2025-06-30 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3700.14 | 2025-06 | Digital Transformation | 0
ACT-00024 | 2025-06-30 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 6708.67 | 2025-06 | Digital Transformation | 0
ACT-00025 | 2025-06-30 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1339.38 | 2025-06 | Digital Transformation | 0
ACT-00026 | 2025-06-30 | P-1019 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 864.28 | 2025-06 | Digital Transformation | 0
ACT-00027 | 2025-07-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4907.02 | 2025-07 | Cloud & Infrastructure | 0
ACT-00028 | 2025-07-31 | P-1014 | Labour | E-0008 |  | Timesheet | 48.3 | Yes | 4590.43 | 2025-07 | Cloud & Infrastructure | 9177
ACT-00029 | 2025-07-31 | P-1014 | Labour | E-0011 |  | Timesheet | 49.9 | Yes | 6483.01 | 2025-07 | Cloud & Infrastructure | 12974
ACT-00030 | 2025-07-31 | P-1014 | Labour | E-0029 |  | Timesheet | 93.3 | Yes | 9270.29 | 2025-07 | Cloud & Infrastructure | 18660
ACT-00031 | 2025-07-31 | P-1014 | Labour | E-0057 |  | Timesheet | 143 | Yes | 15592.72 | 2025-07 | Cloud & Infrastructure | 31460
ACT-00032 | 2025-07-31 | P-1014 | Labour | E-0061 |  | Timesheet | 97.9 | Yes | 8419.4 | 2025-07 | Cloud & Infrastructure | 17132.5
ACT-00033 | 2025-07-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1861.53 | 2025-07 | Cloud & Infrastructure | 0
ACT-00034 | 2025-07-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 631.86 | 2025-07 | Cloud & Infrastructure | 0
ACT-00035 | 2025-07-31 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6094.71 | 2025-07 | Cloud & Infrastructure | 0
ACT-00036 | 2025-07-31 | P-1018 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 18858.49 | 2025-07 | Cloud & Infrastructure | 0
ACT-00037 | 2025-07-31 | P-1018 | Labour | E-0006 |  | Timesheet | 86.6 | Yes | 7620.8 | 2025-07 | Cloud & Infrastructure | 15155
ACT-00038 | 2025-07-31 | P-1018 | Labour | E-0012 |  | Timesheet | 45.1 | Yes | 5859.39 | 2025-07 | Cloud & Infrastructure | 11726
ACT-00039 | 2025-07-31 | P-1018 | Labour | E-0027 |  | Timesheet | 92.2 | Yes | 9160.99 | 2025-07 | Cloud & Infrastructure | 18440
ACT-00040 | 2025-07-31 | P-1018 | Labour | E-0055 |  | Timesheet | 175.2 | Yes | 19103.81 | 2025-07 | Cloud & Infrastructure | 38544
ACT-00041 | 2025-07-31 | P-1018 | Labour | E-0061 |  | Timesheet | 96.6 | Yes | 8307.6 | 2025-07 | Cloud & Infrastructure | 16905
ACT-00042 | 2025-07-31 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1829.07 | 2025-07 | Cloud & Infrastructure | 0
ACT-00043 | 2025-07-31 | P-1018 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 706.69 | 2025-07 | Cloud & Infrastructure | 0
ACT-00044 | 2025-07-31 | P-1019 | Labour | E-0010 |  | Timesheet | 95.9 | Yes | 8439.2 | 2025-07 | Digital Transformation | 16782.5
ACT-00045 | 2025-07-31 | P-1019 | Labour | E-0013 |  | Timesheet | 44.9 | Yes | 5431.1 | 2025-07 | Digital Transformation | 11000.5
ACT-00046 | 2025-07-31 | P-1019 | Labour | E-0017 |  | Timesheet | 164.1 | Yes | 10377.68 | 2025-07 | Digital Transformation | 21333
ACT-00047 | 2025-07-31 | P-1019 | Labour | E-0025 |  | Timesheet | 156.6 | Yes | 16748.37 | 2025-07 | Digital Transformation | 26622
ACT-00048 | 2025-07-31 | P-1019 | Labour | E-0034 |  | Timesheet | 174.6 | Yes | 9498.24 | 2025-07 | Digital Transformation | 19206
ACT-00049 | 2025-07-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3818.71 | 2025-07 | Digital Transformation | 0
ACT-00050 | 2025-07-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5951.93 | 2025-07 | Digital Transformation | 0
ACT-00051 | 2025-07-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1438.15 | 2025-07 | Digital Transformation | 0
ACT-00052 | 2025-07-31 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 939.92 | 2025-07 | Digital Transformation | 0
ACT-00053 | 2025-08-31 | P-1013 | Labour | E-0004 |  | Timesheet | 94 | Yes | 9595.52 | 2025-08 | Digital Transformation | 19270
ACT-00054 | 2025-08-31 | P-1013 | Labour | E-0014 |  | Timesheet | 98.8 | Yes | 10291.01 | 2025-08 | Digital Transformation | 20748
ACT-00055 | 2025-08-31 | P-1013 | Labour | E-0019 |  | Timesheet | 155.9 | Yes | 11263.77 | 2025-08 | Digital Transformation | 18708
ACT-00056 | 2025-08-31 | P-1013 | Labour | E-0028 |  | Timesheet | 139.7 | Yes | 11952.73 | 2025-08 | Digital Transformation | 23749
ACT-00057 | 2025-08-31 | P-1013 | Labour | E-0041 |  | Timesheet | 106.7 | Yes | 6828.8 | 2025-08 | Digital Transformation | 13871
ACT-00058 | 2025-08-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3984.55 | 2025-08 | Digital Transformation | 0
ACT-00059 | 2025-08-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5706.99 | 2025-08 | Digital Transformation | 0
ACT-00060 | 2025-08-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1509.96 | 2025-08 | Digital Transformation | 0
ACT-00061 | 2025-08-31 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 993.27 | 2025-08 | Digital Transformation | 0
ACT-00062 | 2025-08-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5249.87 | 2025-08 | Cloud & Infrastructure | 0
ACT-00063 | 2025-08-31 | P-1014 | Labour | E-0008 |  | Timesheet | 42.1 | Yes | 4001.18 | 2025-08 | Cloud & Infrastructure | 7999
ACT-00064 | 2025-08-31 | P-1014 | Labour | E-0011 |  | Timesheet | 44.5 | Yes | 5781.44 | 2025-08 | Cloud & Infrastructure | 11570
ACT-00065 | 2025-08-31 | P-1014 | Labour | E-0029 |  | Timesheet | 88.9 | Yes | 8833.1 | 2025-08 | Cloud & Infrastructure | 17780
ACT-00066 | 2025-08-31 | P-1014 | Labour | E-0057 |  | Timesheet | 119.3 | Yes | 13008.47 | 2025-08 | Cloud & Infrastructure | 26246
ACT-00067 | 2025-08-31 | P-1014 | Labour | E-0061 |  | Timesheet | 88.8 | Yes | 7636.8 | 2025-08 | Cloud & Infrastructure | 15540
ACT-00068 | 2025-08-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1866.04 | 2025-08 | Cloud & Infrastructure | 0
ACT-00069 | 2025-08-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 793.61 | 2025-08 | Cloud & Infrastructure | 0
ACT-00070 | 2025-08-31 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5215.63 | 2025-08 | Cloud & Infrastructure | 0
ACT-00071 | 2025-08-31 | P-1018 | Labour | E-0006 |  | Timesheet | 79.5 | Yes | 6996 | 2025-08 | Cloud & Infrastructure | 13912.5
ACT-00072 | 2025-08-31 | P-1018 | Labour | E-0012 |  | Timesheet | 43.9 | Yes | 5703.49 | 2025-08 | Cloud & Infrastructure | 11414
ACT-00073 | 2025-08-31 | P-1018 | Labour | E-0027 |  | Timesheet | 76 | Yes | 7551.36 | 2025-08 | Cloud & Infrastructure | 15200
ACT-00074 | 2025-08-31 | P-1018 | Labour | E-0055 |  | Timesheet | 157.5 | Yes | 17173.8 | 2025-08 | Cloud & Infrastructure | 34650
ACT-00075 | 2025-08-31 | P-1018 | Labour | E-0061 |  | Timesheet | 74.7 | Yes | 6424.2 | 2025-08 | Cloud & Infrastructure | 13072.5
ACT-00076 | 2025-08-31 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1906.29 | 2025-08 | Cloud & Infrastructure | 0
ACT-00077 | 2025-08-31 | P-1018 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 879.18 | 2025-08 | Cloud & Infrastructure | 0
ACT-00078 | 2025-08-31 | P-1019 | Labour | E-0010 |  | Timesheet | 91.7 | Yes | 8069.6 | 2025-08 | Digital Transformation | 16047.5
ACT-00079 | 2025-08-31 | P-1019 | Labour | E-0013 |  | Timesheet | 49.7 | Yes | 6011.71 | 2025-08 | Digital Transformation | 12176.5
ACT-00080 | 2025-08-31 | P-1019 | Labour | E-0017 |  | Timesheet | 132.4 | Yes | 8372.98 | 2025-08 | Digital Transformation | 17212
ACT-00081 | 2025-08-31 | P-1019 | Labour | E-0025 |  | Timesheet | 132.8 | Yes | 14202.96 | 2025-08 | Digital Transformation | 22576
ACT-00082 | 2025-08-31 | P-1019 | Labour | E-0034 |  | Timesheet | 140.1 | Yes | 7621.44 | 2025-08 | Digital Transformation | 15411
ACT-00083 | 2025-08-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3006.99 | 2025-08 | Digital Transformation | 0
ACT-00084 | 2025-08-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 6514.26 | 2025-08 | Digital Transformation | 0
ACT-00085 | 2025-08-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1330.84 | 2025-08 | Digital Transformation | 0
ACT-00086 | 2025-08-31 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 845.42 | 2025-08 | Digital Transformation | 0
ACT-00087 | 2025-09-30 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4487.92 | 2025-09 | Data & AI | 0
ACT-00088 | 2025-09-30 | P-1003 | Labour | E-0005 |  | Timesheet | 38.8 | No | 2902.24 | 2025-09 | Data & AI | 0
ACT-00089 | 2025-09-30 | P-1003 | Labour | E-0013 |  | Timesheet | 38.8 | Yes | 4693.25 | 2025-09 | Data & AI | 9506
ACT-00090 | 2025-09-30 | P-1003 | Labour | E-0033 |  | Timesheet | 72 | Yes | 4285.44 | 2025-09 | Data & AI | 8640
ACT-00091 | 2025-09-30 | P-1003 | Labour | E-0048 |  | Timesheet | 164 | Yes | 17121.6 | 2025-09 | Data & AI | 34440
ACT-00092 | 2025-09-30 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2781.28 | 2025-09 | Data & AI | 0
ACT-00093 | 2025-09-30 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 503.25 | 2025-09 | Data & AI | 0
ACT-00094 | 2025-09-30 | P-1013 | Labour | E-0004 |  | Timesheet | 108.5 | Yes | 11075.68 | 2025-09 | Digital Transformation | 22242.5
ACT-00095 | 2025-09-30 | P-1013 | Labour | E-0014 |  | Timesheet | 106.4 | Yes | 11082.62 | 2025-09 | Digital Transformation | 22344
ACT-00096 | 2025-09-30 | P-1013 | Labour | E-0019 |  | Timesheet | 170.4 | Yes | 12311.4 | 2025-09 | Digital Transformation | 20448
ACT-00097 | 2025-09-30 | P-1013 | Labour | E-0028 |  | Timesheet | 179.7 | Yes | 15375.13 | 2025-09 | Digital Transformation | 30549
ACT-00098 | 2025-09-30 | P-1013 | Labour | E-0041 |  | Timesheet | 117.6 | Yes | 7526.4 | 2025-09 | Digital Transformation | 15288
ACT-00099 | 2025-09-30 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3850.29 | 2025-09 | Digital Transformation | 0
ACT-00100 | 2025-09-30 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5763.65 | 2025-09 | Digital Transformation | 0
ACT-00101 | 2025-09-30 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1635.56 | 2025-09 | Digital Transformation | 0
ACT-00102 | 2025-09-30 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1051.87 | 2025-09 | Digital Transformation | 0
ACT-00103 | 2025-09-30 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5254.37 | 2025-09 | Cloud & Infrastructure | 0
ACT-00104 | 2025-09-30 | P-1014 | Labour | E-0008 |  | Timesheet | 47.7 | Yes | 4533.41 | 2025-09 | Cloud & Infrastructure | 9063
ACT-00105 | 2025-09-30 | P-1014 | Labour | E-0011 |  | Timesheet | 45.7 | Yes | 5937.34 | 2025-09 | Cloud & Infrastructure | 11882
ACT-00106 | 2025-09-30 | P-1014 | Labour | E-0029 |  | Timesheet | 94.7 | Yes | 9409.39 | 2025-09 | Cloud & Infrastructure | 18940
ACT-00107 | 2025-09-30 | P-1014 | Labour | E-0057 |  | Timesheet | 130.3 | Yes | 14207.91 | 2025-09 | Cloud & Infrastructure | 28666
ACT-00108 | 2025-09-30 | P-1014 | Labour | E-0061 |  | Timesheet | 93.3 | Yes | 8023.8 | 2025-09 | Cloud & Infrastructure | 16327.5
ACT-00109 | 2025-09-30 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1584.03 | 2025-09 | Cloud & Infrastructure | 0
ACT-00110 | 2025-09-30 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 656.46 | 2025-09 | Cloud & Infrastructure | 0
ACT-00111 | 2025-09-30 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5766.39 | 2025-09 | Cloud & Infrastructure | 0
ACT-00112 | 2025-09-30 | P-1018 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 12468.47 | 2025-09 | Cloud & Infrastructure | 0
ACT-00113 | 2025-09-30 | P-1018 | Labour | E-0006 |  | Timesheet | 85.3 | Yes | 7506.4 | 2025-09 | Cloud & Infrastructure | 14927.5
ACT-00114 | 2025-09-30 | P-1018 | Labour | E-0012 |  | Timesheet | 30.2 | Yes | 3923.58 | 2025-09 | Cloud & Infrastructure | 7852
ACT-00115 | 2025-09-30 | P-1018 | Labour | E-0027 |  | Timesheet | 90.5 | Yes | 8992.08 | 2025-09 | Cloud & Infrastructure | 18100
ACT-00116 | 2025-09-30 | P-1018 | Labour | E-0055 |  | Timesheet | 189.2 | Yes | 20630.37 | 2025-09 | Cloud & Infrastructure | 41624
ACT-00117 | 2025-09-30 | P-1018 | Labour | E-0061 |  | Timesheet | 85.5 | Yes | 7353 | 2025-09 | Cloud & Infrastructure | 14962.5
ACT-00118 | 2025-09-30 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1981.18 | 2025-09 | Cloud & Infrastructure | 0
ACT-00119 | 2025-09-30 | P-1018 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 706.33 | 2025-09 | Cloud & Infrastructure | 0
ACT-00120 | 2025-09-30 | P-1019 | Labour | E-0010 |  | Timesheet | 90.1 | Yes | 7928.8 | 2025-09 | Digital Transformation | 15767.5
ACT-00121 | 2025-09-30 | P-1019 | Labour | E-0013 |  | Timesheet | 48.6 | Yes | 5878.66 | 2025-09 | Digital Transformation | 11907
ACT-00122 | 2025-09-30 | P-1019 | Labour | E-0017 |  | Timesheet | 129.2 | Yes | 8170.61 | 2025-09 | Digital Transformation | 16796
ACT-00123 | 2025-09-30 | P-1019 | Labour | E-0025 |  | Timesheet | 139.4 | Yes | 14908.83 | 2025-09 | Digital Transformation | 23698
ACT-00124 | 2025-09-30 | P-1019 | Labour | E-0034 |  | Timesheet | 137.5 | Yes | 7480 | 2025-09 | Digital Transformation | 15125
ACT-00125 | 2025-09-30 | P-1019 | Labour | E-0042 |  | Timesheet | 51.7 | Yes | 3358.43 | 2025-09 | Digital Transformation | 6979.5
ACT-00126 | 2025-09-30 | P-1019 | Labour | E-0062 |  | Timesheet | 23 | Yes | 1920.96 | 2025-09 | Digital Transformation | 4025
ACT-00127 | 2025-09-30 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3922.38 | 2025-09 | Digital Transformation | 0
ACT-00128 | 2025-09-30 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 6260.32 | 2025-09 | Digital Transformation | 0
ACT-00129 | 2025-09-30 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1336.84 | 2025-09 | Digital Transformation | 0
ACT-00130 | 2025-09-30 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 868.2 | 2025-09 | Digital Transformation | 0
ACT-00131 | 2025-10-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3956.49 | 2025-10 | Data & AI | 0
ACT-00132 | 2025-10-31 | P-1003 | Labour | E-0005 |  | Timesheet | 52 | No | 3889.6 | 2025-10 | Data & AI | 0
ACT-00133 | 2025-10-31 | P-1003 | Labour | E-0013 |  | Timesheet | 48.1 | Yes | 5818.18 | 2025-10 | Data & AI | 11784.5
ACT-00134 | 2025-10-31 | P-1003 | Labour | E-0033 |  | Timesheet | 100.1 | Yes | 5957.95 | 2025-10 | Data & AI | 12012
ACT-00135 | 2025-10-31 | P-1003 | Labour | E-0048 |  | Timesheet | 184.2 | Yes | 19230.48 | 2025-10 | Data & AI | 38682
ACT-00136 | 2025-10-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3060.98 | 2025-10 | Data & AI | 0
ACT-00137 | 2025-10-31 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 511.23 | 2025-10 | Data & AI | 0
ACT-00138 | 2025-10-31 | P-1006 | Labour | E-0009 |  | Timesheet | 108.2 | Yes | 8093.36 | 2025-10 | Customer Experience | 16230
ACT-00139 | 2025-10-31 | P-1006 | Labour | E-0019 |  | Timesheet | 104.1 | Yes | 7521.22 | 2025-10 | Customer Experience | 12492
ACT-00140 | 2025-10-31 | P-1006 | Labour | E-0021 |  | Timesheet | 145.3 | Yes | 9999.55 | 2025-10 | Customer Experience | 20342
ACT-00141 | 2025-10-31 | P-1006 | Labour | E-0026 |  | Timesheet | 138.4 | Yes | 11841.5 | 2025-10 | Customer Experience | 23528
ACT-00142 | 2025-10-31 | P-1006 | Labour | E-0035 |  | Timesheet | 204.2 | Yes | 12153.98 | 2025-10 | Customer Experience | 24504
ACT-00143 | 2025-10-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2379.1 | 2025-10 | Customer Experience | 0
ACT-00144 | 2025-10-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4401.28 | 2025-10 | Customer Experience | 0
ACT-00145 | 2025-10-31 | P-1006 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 757.24 | 2025-10 | Customer Experience | 0
ACT-00146 | 2025-10-31 | P-1013 | Labour | E-0004 |  | Timesheet | 119 | Yes | 12147.52 | 2025-10 | Digital Transformation | 24395
ACT-00147 | 2025-10-31 | P-1013 | Labour | E-0014 |  | Timesheet | 109.5 | Yes | 11405.52 | 2025-10 | Digital Transformation | 22995
ACT-00148 | 2025-10-31 | P-1013 | Labour | E-0019 |  | Timesheet | 176.7 | Yes | 12766.57 | 2025-10 | Digital Transformation | 21204
ACT-00149 | 2025-10-31 | P-1013 | Labour | E-0028 |  | Timesheet | 167.2 | Yes | 14305.63 | 2025-10 | Digital Transformation | 28424
ACT-00150 | 2025-10-31 | P-1013 | Labour | E-0041 |  | Timesheet | 128.5 | Yes | 8224 | 2025-10 | Digital Transformation | 16705
ACT-00151 | 2025-10-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3866.43 | 2025-10 | Digital Transformation | 0
ACT-00152 | 2025-10-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5103.55 | 2025-10 | Digital Transformation | 0
ACT-00153 | 2025-10-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1259.95 | 2025-10 | Digital Transformation | 0
ACT-00154 | 2025-10-31 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1184.87 | 2025-10 | Digital Transformation | 0
ACT-00155 | 2025-10-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5564.28 | 2025-10 | Cloud & Infrastructure | 0
ACT-00156 | 2025-10-31 | P-1014 | Labour | E-0008 |  | Timesheet | 45.4 | Yes | 4314.82 | 2025-10 | Cloud & Infrastructure | 8626
ACT-00157 | 2025-10-31 | P-1014 | Labour | E-0011 |  | Timesheet | 47.7 | Yes | 6197.18 | 2025-10 | Cloud & Infrastructure | 12402
ACT-00158 | 2025-10-31 | P-1014 | Labour | E-0029 |  | Timesheet | 93.8 | Yes | 9319.97 | 2025-10 | Cloud & Infrastructure | 18760
ACT-00159 | 2025-10-31 | P-1014 | Labour | E-0057 |  | Timesheet | 127.5 | Yes | 13902.6 | 2025-10 | Cloud & Infrastructure | 28050
ACT-00160 | 2025-10-31 | P-1014 | Labour | E-0061 |  | Timesheet | 87.8 | Yes | 7550.8 | 2025-10 | Cloud & Infrastructure | 15365
ACT-00161 | 2025-10-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1826.85 | 2025-10 | Cloud & Infrastructure | 0
ACT-00162 | 2025-10-31 | P-1014 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 678.71 | 2025-10 | Cloud & Infrastructure | 0
ACT-00163 | 2025-10-31 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6011.47 | 2025-10 | Cloud & Infrastructure | 0
ACT-00164 | 2025-10-31 | P-1018 | Labour | E-0006 |  | Timesheet | 85.5 | Yes | 7524 | 2025-10 | Cloud & Infrastructure | 14962.5
ACT-00165 | 2025-10-31 | P-1018 | Labour | E-0027 |  | Timesheet | 83.2 | Yes | 8266.75 | 2025-10 | Cloud & Infrastructure | 16640
ACT-00166 | 2025-10-31 | P-1018 | Labour | E-0055 |  | Timesheet | 182.8 | Yes | 19932.51 | 2025-10 | Cloud & Infrastructure | 40216
ACT-00167 | 2025-10-31 | P-1018 | Labour | E-0061 |  | Timesheet | 97.4 | Yes | 8376.4 | 2025-10 | Cloud & Infrastructure | 17045
ACT-00168 | 2025-10-31 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1748.32 | 2025-10 | Cloud & Infrastructure | 0
ACT-00169 | 2025-10-31 | P-1018 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 735.45 | 2025-10 | Cloud & Infrastructure | 0
ACT-00170 | 2025-10-31 | P-1019 | Labour | E-0010 |  | Timesheet | 101.6 | Yes | 8940.8 | 2025-10 | Digital Transformation | 17780
ACT-00171 | 2025-10-31 | P-1019 | Labour | E-0013 |  | Timesheet | 26 | Yes | 3144.96 | 2025-10 | Digital Transformation | 6370
ACT-00172 | 2025-10-31 | P-1019 | Labour | E-0017 |  | Timesheet | 149.7 | Yes | 9467.03 | 2025-10 | Digital Transformation | 19461
ACT-00173 | 2025-10-31 | P-1019 | Labour | E-0025 |  | Timesheet | 148.3 | Yes | 15860.69 | 2025-10 | Digital Transformation | 25211
ACT-00174 | 2025-10-31 | P-1019 | Labour | E-0034 |  | Timesheet | 167.4 | Yes | 9106.56 | 2025-10 | Digital Transformation | 18414
ACT-00175 | 2025-10-31 | P-1019 | Labour | E-0042 |  | Timesheet | 91.2 | Yes | 5924.35 | 2025-10 | Digital Transformation | 12312
ACT-00176 | 2025-10-31 | P-1019 | Labour | E-0062 |  | Timesheet | 50.2 | Yes | 4192.7 | 2025-10 | Digital Transformation | 8785
ACT-00177 | 2025-10-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3146.58 | 2025-10 | Digital Transformation | 0
ACT-00178 | 2025-10-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5250.91 | 2025-10 | Digital Transformation | 0
ACT-00179 | 2025-10-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1477.95 | 2025-10 | Digital Transformation | 0
ACT-00180 | 2025-10-31 | P-1019 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 841.38 | 2025-10 | Digital Transformation | 0
ACT-00181 | 2025-10-31 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3448.91 | 2025-10 | Data & AI | 0
ACT-00182 | 2025-10-31 | P-1020 | Labour | E-0006 |  | Timesheet | 57.2 | No | 5033.6 | 2025-10 | Data & AI | 0
ACT-00183 | 2025-10-31 | P-1020 | Labour | E-0012 |  | Timesheet | 29.9 | Yes | 3884.61 | 2025-10 | Data & AI | 7774
ACT-00184 | 2025-10-31 | P-1020 | Labour | E-0037 |  | Timesheet | 62.2 | Yes | 4229.6 | 2025-10 | Data & AI | 6842
ACT-00185 | 2025-10-31 | P-1020 | Labour | E-0051 |  | Timesheet | 107.3 | Yes | 10429.56 | 2025-10 | Data & AI | 20923.5
ACT-00186 | 2025-10-31 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2225.23 | 2025-10 | Data & AI | 0
ACT-00187 | 2025-10-31 | P-1020 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 584.53 | 2025-10 | Data & AI | 0
ACT-00188 | 2025-11-30 | P-1001 | Labour | E-0003 |  | Timesheet | 73.4 | Yes | 7492.67 | 2025-11 | Customer Experience | 15047
ACT-00189 | 2025-11-30 | P-1001 | Labour | E-0015 |  | Timesheet | 79.9 | Yes | 6302.51 | 2025-11 | Customer Experience | 12784
ACT-00190 | 2025-11-30 | P-1001 | Labour | E-0020 |  | Timesheet | 112.2 | Yes | 9631.25 | 2025-11 | Customer Experience | 19635
ACT-00191 | 2025-11-30 | P-1001 | Labour | E-0023 |  | Timesheet | 117.2 | Yes | 12507.58 | 2025-11 | Customer Experience | 25198
ACT-00192 | 2025-11-30 | P-1001 | Labour | E-0031 |  | Timesheet | 148.6 | Yes | 11032.06 | 2025-11 | Customer Experience | 22290
ACT-00193 | 2025-11-30 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2598.74 | 2025-11 | Customer Experience | 0
ACT-00194 | 2025-11-30 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4045.6 | 2025-11 | Customer Experience | 0
ACT-00195 | 2025-11-30 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 950.02 | 2025-11 | Customer Experience | 0
ACT-00196 | 2025-11-30 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4070.52 | 2025-11 | Data & AI | 0
ACT-00197 | 2025-11-30 | P-1003 | Labour | E-0005 |  | Timesheet | 42 | No | 3141.6 | 2025-11 | Data & AI | 0
ACT-00198 | 2025-11-30 | P-1003 | Labour | E-0013 |  | Timesheet | 43.5 | Yes | 5261.76 | 2025-11 | Data & AI | 10657.5
ACT-00199 | 2025-11-30 | P-1003 | Labour | E-0033 |  | Timesheet | 95.5 | Yes | 5684.16 | 2025-11 | Data & AI | 11460
ACT-00200 | 2025-11-30 | P-1003 | Labour | E-0048 |  | Timesheet | 182.8 | Yes | 19084.32 | 2025-11 | Data & AI | 38388
ACT-00201 | 2025-11-30 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2648.45 | 2025-11 | Data & AI | 0
ACT-00202 | 2025-11-30 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 615.33 | 2025-11 | Data & AI | 0
ACT-00203 | 2025-11-30 | P-1006 | Labour | E-0009 |  | Timesheet | 97.5 | Yes | 7293 | 2025-11 | Customer Experience | 14625
ACT-00204 | 2025-11-30 | P-1006 | Labour | E-0019 |  | Timesheet | 110.3 | Yes | 7969.18 | 2025-11 | Customer Experience | 13236
ACT-00205 | 2025-11-30 | P-1006 | Labour | E-0021 |  | Timesheet | 151.3 | Yes | 10412.47 | 2025-11 | Customer Experience | 21182
ACT-00206 | 2025-11-30 | P-1006 | Labour | E-0026 |  | Timesheet | 153.8 | Yes | 13159.13 | 2025-11 | Customer Experience | 26146
ACT-00207 | 2025-11-30 | P-1006 | Labour | E-0035 |  | Timesheet | 194.4 | Yes | 11570.69 | 2025-11 | Customer Experience | 23328
ACT-00208 | 2025-11-30 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2489.39 | 2025-11 | Customer Experience | 0
ACT-00209 | 2025-11-30 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3723.13 | 2025-11 | Customer Experience | 0
ACT-00210 | 2025-11-30 | P-1006 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 691.88 | 2025-11 | Customer Experience | 0
ACT-00211 | 2025-11-30 | P-1013 | Labour | E-0004 |  | Timesheet | 99.4 | Yes | 10146.75 | 2025-11 | Digital Transformation | 20377
ACT-00212 | 2025-11-30 | P-1013 | Labour | E-0014 |  | Timesheet | 108.7 | Yes | 11322.19 | 2025-11 | Digital Transformation | 22827
ACT-00213 | 2025-11-30 | P-1013 | Labour | E-0019 |  | Timesheet | 157 | Yes | 11343.25 | 2025-11 | Digital Transformation | 18840
ACT-00214 | 2025-11-30 | P-1013 | Labour | E-0028 |  | Timesheet | 153.4 | Yes | 13124.9 | 2025-11 | Digital Transformation | 26078
ACT-00215 | 2025-11-30 | P-1013 | Labour | E-0041 |  | Timesheet | 94 | Yes | 6016 | 2025-11 | Digital Transformation | 12220
ACT-00216 | 2025-11-30 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 4180.8 | 2025-11 | Digital Transformation | 0
ACT-00217 | 2025-11-30 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5402.52 | 2025-11 | Digital Transformation | 0
ACT-00218 | 2025-11-30 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1299.06 | 2025-11 | Digital Transformation | 0
ACT-00219 | 2025-11-30 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1171.85 | 2025-11 | Digital Transformation | 0
ACT-00220 | 2025-11-30 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5296.53 | 2025-11 | Cloud & Infrastructure | 0
ACT-00221 | 2025-11-30 | P-1014 | Hardware |  | Dell Technologies | AP Invoice | 0 | No | 45081.33 | 2025-11 | Cloud & Infrastructure | 0
ACT-00222 | 2025-11-30 | P-1014 | Labour | E-0008 |  | Timesheet | 42.9 | Yes | 4077.22 | 2025-11 | Cloud & Infrastructure | 8151
ACT-00223 | 2025-11-30 | P-1014 | Labour | E-0011 |  | Timesheet | 41.2 | Yes | 5352.7 | 2025-11 | Cloud & Infrastructure | 10712
ACT-00224 | 2025-11-30 | P-1014 | Labour | E-0029 |  | Timesheet | 84.2 | Yes | 8366.11 | 2025-11 | Cloud & Infrastructure | 16840
ACT-00225 | 2025-11-30 | P-1014 | Labour | E-0057 |  | Timesheet | 120.5 | Yes | 13139.32 | 2025-11 | Cloud & Infrastructure | 26510
ACT-00226 | 2025-11-30 | P-1014 | Labour | E-0061 |  | Timesheet | 85.7 | Yes | 7370.2 | 2025-11 | Cloud & Infrastructure | 14997.5
ACT-00227 | 2025-11-30 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1733.83 | 2025-11 | Cloud & Infrastructure | 0
ACT-00228 | 2025-11-30 | P-1014 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 690.22 | 2025-11 | Cloud & Infrastructure | 0
ACT-00229 | 2025-11-30 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6118.98 | 2025-11 | Cloud & Infrastructure | 0
ACT-00230 | 2025-11-30 | P-1018 | Labour | E-0006 |  | Timesheet | 81.4 | Yes | 7163.2 | 2025-11 | Cloud & Infrastructure | 14245
ACT-00231 | 2025-11-30 | P-1018 | Labour | E-0027 |  | Timesheet | 86.4 | Yes | 8584.7 | 2025-11 | Cloud & Infrastructure | 17280
ACT-00232 | 2025-11-30 | P-1018 | Labour | E-0055 |  | Timesheet | 146.6 | Yes | 15985.26 | 2025-11 | Cloud & Infrastructure | 32252
ACT-00233 | 2025-11-30 | P-1018 | Labour | E-0061 |  | Timesheet | 77.2 | Yes | 6639.2 | 2025-11 | Cloud & Infrastructure | 13510
ACT-00234 | 2025-11-30 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1789.88 | 2025-11 | Cloud & Infrastructure | 0
ACT-00235 | 2025-11-30 | P-1018 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 757.14 | 2025-11 | Cloud & Infrastructure | 0
ACT-00236 | 2025-11-30 | P-1019 | Labour | E-0010 |  | Timesheet | 88.5 | Yes | 7788 | 2025-11 | Digital Transformation | 15487.5
ACT-00237 | 2025-11-30 | P-1019 | Labour | E-0017 |  | Timesheet | 137.1 | Yes | 8670.2 | 2025-11 | Digital Transformation | 17823
ACT-00238 | 2025-11-30 | P-1019 | Labour | E-0025 |  | Timesheet | 125.3 | Yes | 13400.84 | 2025-11 | Digital Transformation | 21301
ACT-00239 | 2025-11-30 | P-1019 | Labour | E-0034 |  | Timesheet | 137.8 | Yes | 7496.32 | 2025-11 | Digital Transformation | 15158
ACT-00240 | 2025-11-30 | P-1019 | Labour | E-0042 |  | Timesheet | 89.1 | Yes | 5787.94 | 2025-11 | Digital Transformation | 12028.5
ACT-00241 | 2025-11-30 | P-1019 | Labour | E-0062 |  | Timesheet | 40.5 | Yes | 3382.56 | 2025-11 | Digital Transformation | 7087.5
ACT-00242 | 2025-11-30 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3480.75 | 2025-11 | Digital Transformation | 0
ACT-00243 | 2025-11-30 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5911.68 | 2025-11 | Digital Transformation | 0
ACT-00244 | 2025-11-30 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1303.34 | 2025-11 | Digital Transformation | 0
ACT-00245 | 2025-11-30 | P-1019 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1029.42 | 2025-11 | Digital Transformation | 0
ACT-00246 | 2025-11-30 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3519.7 | 2025-11 | Data & AI | 0
ACT-00247 | 2025-11-30 | P-1020 | Labour | E-0006 |  | Timesheet | 75 | No | 6600 | 2025-11 | Data & AI | 0
ACT-00248 | 2025-11-30 | P-1020 | Labour | E-0012 |  | Timesheet | 35.5 | Yes | 4612.16 | 2025-11 | Data & AI | 9230
ACT-00249 | 2025-11-30 | P-1020 | Labour | E-0037 |  | Timesheet | 82.7 | Yes | 5623.6 | 2025-11 | Data & AI | 9097
ACT-00250 | 2025-11-30 | P-1020 | Labour | E-0051 |  | Timesheet | 152.4 | Yes | 14813.28 | 2025-11 | Data & AI | 29718
ACT-00251 | 2025-11-30 | P-1020 | Labour | E-0053 |  | Timesheet | 12 | Yes | 1176 | 2025-11 | Data & AI | 2400
ACT-00252 | 2025-11-30 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2715.46 | 2025-11 | Data & AI | 0
ACT-00253 | 2025-11-30 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 563.35 | 2025-11 | Data & AI | 0
ACT-00254 | 2025-12-31 | P-1001 | Labour | E-0003 |  | Timesheet | 82.6 | Yes | 8431.81 | 2025-12 | Customer Experience | 16933
ACT-00255 | 2025-12-31 | P-1001 | Labour | E-0015 |  | Timesheet | 92.3 | Yes | 7280.62 | 2025-12 | Customer Experience | 14768
ACT-00256 | 2025-12-31 | P-1001 | Labour | E-0020 |  | Timesheet | 129.5 | Yes | 11116.28 | 2025-12 | Customer Experience | 22662.5
ACT-00257 | 2025-12-31 | P-1001 | Labour | E-0023 |  | Timesheet | 150.8 | Yes | 16093.38 | 2025-12 | Customer Experience | 32422
ACT-00258 | 2025-12-31 | P-1001 | Labour | E-0031 |  | Timesheet | 166.3 | Yes | 12346.11 | 2025-12 | Customer Experience | 24945
ACT-00259 | 2025-12-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3302.95 | 2025-12 | Customer Experience | 0
ACT-00260 | 2025-12-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4760.19 | 2025-12 | Customer Experience | 0
ACT-00261 | 2025-12-31 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 980.74 | 2025-12 | Customer Experience | 0
ACT-00262 | 2025-12-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3742.39 | 2025-12 | Data & AI | 0
ACT-00263 | 2025-12-31 | P-1003 | Labour | E-0005 |  | Timesheet | 52.4 | No | 3919.52 | 2025-12 | Data & AI | 0
ACT-00264 | 2025-12-31 | P-1003 | Labour | E-0013 |  | Timesheet | 51.2 | Yes | 6193.15 | 2025-12 | Data & AI | 12544
ACT-00265 | 2025-12-31 | P-1003 | Labour | E-0033 |  | Timesheet | 108.8 | Yes | 6475.78 | 2025-12 | Data & AI | 13056
ACT-00266 | 2025-12-31 | P-1003 | Labour | E-0048 |  | Timesheet | 221.7 | Yes | 23145.48 | 2025-12 | Data & AI | 46557
ACT-00267 | 2025-12-31 | P-1003 | Labour | E-0052 |  | Timesheet | 84.2 | Yes | 9571.86 | 2025-12 | Data & AI | 19366
ACT-00268 | 2025-12-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2702.39 | 2025-12 | Data & AI | 0
ACT-00269 | 2025-12-31 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 636.38 | 2025-12 | Data & AI | 0
ACT-00270 | 2025-12-31 | P-1006 | Labour | E-0009 |  | Timesheet | 125.6 | Yes | 9394.88 | 2025-12 | Customer Experience | 18840
ACT-00271 | 2025-12-31 | P-1006 | Labour | E-0019 |  | Timesheet | 119.4 | Yes | 8626.65 | 2025-12 | Customer Experience | 14328
ACT-00272 | 2025-12-31 | P-1006 | Labour | E-0021 |  | Timesheet | 158.5 | Yes | 10907.97 | 2025-12 | Customer Experience | 22190
ACT-00273 | 2025-12-31 | P-1006 | Labour | E-0026 |  | Timesheet | 160.8 | Yes | 13758.05 | 2025-12 | Customer Experience | 27336
ACT-00274 | 2025-12-31 | P-1006 | Labour | E-0035 |  | Timesheet | 219.8 | Yes | 13082.5 | 2025-12 | Customer Experience | 26376
ACT-00275 | 2025-12-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2276.39 | 2025-12 | Customer Experience | 0
ACT-00276 | 2025-12-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4108.81 | 2025-12 | Customer Experience | 0
ACT-00277 | 2025-12-31 | P-1006 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 721.24 | 2025-12 | Customer Experience | 0
ACT-00278 | 2025-12-31 | P-1010 | Labour | E-0007 |  | Timesheet | 110.2 | Yes | 11249.22 | 2025-12 | Customer Experience | 22591
ACT-00279 | 2025-12-31 | P-1010 | Labour | E-0018 |  | Timesheet | 125.2 | Yes | 9194.69 | 2025-12 | Customer Experience | 18780
ACT-00280 | 2025-12-31 | P-1010 | Labour | E-0022 |  | Timesheet | 120.2 | Yes | 7560.58 | 2025-12 | Customer Experience | 15626
ACT-00281 | 2025-12-31 | P-1010 | Labour | E-0030 |  | Timesheet | 222.4 | Yes | 19028.54 | 2025-12 | Customer Experience | 37808
ACT-00282 | 2025-12-31 | P-1010 | Labour | E-0038 |  | Timesheet | 123 | Yes | 9131.52 | 2025-12 | Customer Experience | 18450
ACT-00283 | 2025-12-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3837.96 | 2025-12 | Customer Experience | 0
ACT-00284 | 2025-12-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3774.07 | 2025-12 | Customer Experience | 0
ACT-00285 | 2025-12-31 | P-1010 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 743.59 | 2025-12 | Customer Experience | 0
ACT-00286 | 2025-12-31 | P-1013 | Labour | E-0004 |  | Timesheet | 118.8 | Yes | 12127.1 | 2025-12 | Digital Transformation | 24354
ACT-00287 | 2025-12-31 | P-1013 | Labour | E-0014 |  | Timesheet | 125.1 | Yes | 13030.42 | 2025-12 | Digital Transformation | 26271
ACT-00288 | 2025-12-31 | P-1013 | Labour | E-0019 |  | Timesheet | 177.9 | Yes | 12853.27 | 2025-12 | Digital Transformation | 21348
ACT-00289 | 2025-12-31 | P-1013 | Labour | E-0028 |  | Timesheet | 193.6 | Yes | 16564.42 | 2025-12 | Digital Transformation | 32912
ACT-00290 | 2025-12-31 | P-1013 | Labour | E-0041 |  | Timesheet | 110.2 | Yes | 7052.8 | 2025-12 | Digital Transformation | 14326
ACT-00291 | 2025-12-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3735.87 | 2025-12 | Digital Transformation | 0
ACT-00292 | 2025-12-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4999.88 | 2025-12 | Digital Transformation | 0
ACT-00293 | 2025-12-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1485.3 | 2025-12 | Digital Transformation | 0
ACT-00294 | 2025-12-31 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1092.57 | 2025-12 | Digital Transformation | 0
ACT-00295 | 2025-12-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4907.76 | 2025-12 | Cloud & Infrastructure | 0
ACT-00296 | 2025-12-31 | P-1014 | Labour | E-0008 |  | Timesheet | 46.5 | Yes | 4419.36 | 2025-12 | Cloud & Infrastructure | 8835
ACT-00297 | 2025-12-31 | P-1014 | Labour | E-0011 |  | Timesheet | 46.6 | Yes | 6054.27 | 2025-12 | Cloud & Infrastructure | 12116
ACT-00298 | 2025-12-31 | P-1014 | Labour | E-0029 |  | Timesheet | 97 | Yes | 9637.92 | 2025-12 | Cloud & Infrastructure | 19400
ACT-00299 | 2025-12-31 | P-1014 | Labour | E-0057 |  | Timesheet | 133.8 | Yes | 14589.55 | 2025-12 | Cloud & Infrastructure | 29436
ACT-00300 | 2025-12-31 | P-1014 | Labour | E-0061 |  | Timesheet | 95.7 | Yes | 8230.2 | 2025-12 | Cloud & Infrastructure | 16747.5
ACT-00301 | 2025-12-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1843.13 | 2025-12 | Cloud & Infrastructure | 0
ACT-00302 | 2025-12-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 797.35 | 2025-12 | Cloud & Infrastructure | 0
ACT-00303 | 2025-12-31 | P-1018 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5168.52 | 2025-12 | Cloud & Infrastructure | 0
ACT-00304 | 2025-12-31 | P-1018 | Labour | E-0006 |  | Timesheet | 55.4 | Yes | 4875.2 | 2025-12 | Cloud & Infrastructure | 9695
ACT-00305 | 2025-12-31 | P-1018 | Labour | E-0027 |  | Timesheet | 59.2 | Yes | 5882.11 | 2025-12 | Cloud & Infrastructure | 11840
ACT-00306 | 2025-12-31 | P-1018 | Labour | E-0055 |  | Timesheet | 117.7 | Yes | 12834.01 | 2025-12 | Cloud & Infrastructure | 25894
ACT-00307 | 2025-12-31 | P-1018 | Labour | E-0061 |  | Timesheet | 55.8 | Yes | 4798.8 | 2025-12 | Cloud & Infrastructure | 9765
ACT-00308 | 2025-12-31 | P-1018 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1757.07 | 2025-12 | Cloud & Infrastructure | 0
ACT-00309 | 2025-12-31 | P-1018 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 765.94 | 2025-12 | Cloud & Infrastructure | 0
ACT-00310 | 2025-12-31 | P-1019 | Labour | E-0010 |  | Timesheet | 97.5 | Yes | 8580 | 2025-12 | Digital Transformation | 17062.5
ACT-00311 | 2025-12-31 | P-1019 | Labour | E-0017 |  | Timesheet | 160.8 | Yes | 10168.99 | 2025-12 | Digital Transformation | 20904
ACT-00312 | 2025-12-31 | P-1019 | Labour | E-0025 |  | Timesheet | 135 | Yes | 14438.25 | 2025-12 | Digital Transformation | 22950
ACT-00313 | 2025-12-31 | P-1019 | Labour | E-0034 |  | Timesheet | 175.4 | Yes | 9541.76 | 2025-12 | Digital Transformation | 19294
ACT-00314 | 2025-12-31 | P-1019 | Labour | E-0042 |  | Timesheet | 93.2 | Yes | 6054.27 | 2025-12 | Digital Transformation | 12582
ACT-00315 | 2025-12-31 | P-1019 | Labour | E-0062 |  | Timesheet | 50.9 | Yes | 4251.17 | 2025-12 | Digital Transformation | 8907.5
ACT-00316 | 2025-12-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3892.99 | 2025-12 | Digital Transformation | 0
ACT-00317 | 2025-12-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5877.74 | 2025-12 | Digital Transformation | 0
ACT-00318 | 2025-12-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1325.25 | 2025-12 | Digital Transformation | 0
ACT-00319 | 2025-12-31 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1035.36 | 2025-12 | Digital Transformation | 0
ACT-00320 | 2025-12-31 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3678.37 | 2025-12 | Data & AI | 0
ACT-00321 | 2025-12-31 | P-1020 | Labour | E-0006 |  | Timesheet | 82.8 | No | 7286.4 | 2025-12 | Data & AI | 0
ACT-00322 | 2025-12-31 | P-1020 | Labour | E-0012 |  | Timesheet | 46.7 | Yes | 6067.26 | 2025-12 | Data & AI | 12142
ACT-00323 | 2025-12-31 | P-1020 | Labour | E-0037 |  | Timesheet | 87.5 | Yes | 5950 | 2025-12 | Data & AI | 9625
ACT-00324 | 2025-12-31 | P-1020 | Labour | E-0051 |  | Timesheet | 175.7 | Yes | 17078.04 | 2025-12 | Data & AI | 34261.5
ACT-00325 | 2025-12-31 | P-1020 | Labour | E-0053 |  | Timesheet | 129.9 | Yes | 12730.2 | 2025-12 | Data & AI | 25980
ACT-00326 | 2025-12-31 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2255.97 | 2025-12 | Data & AI | 0
ACT-00327 | 2025-12-31 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 616.02 | 2025-12 | Data & AI | 0
ACT-00328 | 2026-01-31 | P-1001 | Labour | E-0003 |  | Timesheet | 83.6 | Yes | 8533.89 | 2026-01 | Customer Experience | 17138
ACT-00329 | 2026-01-31 | P-1001 | Labour | E-0015 |  | Timesheet | 83.6 | Yes | 6594.37 | 2026-01 | Customer Experience | 13376
ACT-00330 | 2026-01-31 | P-1001 | Labour | E-0020 |  | Timesheet | 142.1 | Yes | 12197.86 | 2026-01 | Customer Experience | 24867.5
ACT-00331 | 2026-01-31 | P-1001 | Labour | E-0023 |  | Timesheet | 132.4 | Yes | 14129.73 | 2026-01 | Customer Experience | 28466
ACT-00332 | 2026-01-31 | P-1001 | Labour | E-0031 |  | Timesheet | 161.6 | Yes | 11997.18 | 2026-01 | Customer Experience | 24240
ACT-00333 | 2026-01-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3035.15 | 2026-01 | Customer Experience | 0
ACT-00334 | 2026-01-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4697.54 | 2026-01 | Customer Experience | 0
ACT-00335 | 2026-01-31 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 966.8 | 2026-01 | Customer Experience | 0
ACT-00336 | 2026-01-31 | P-1002 | Labour | E-0004 |  | Timesheet | 40.6 | Yes | 4144.45 | 2026-01 | Operational Excellence | 8323
ACT-00337 | 2026-01-31 | P-1002 | Labour | E-0016 |  | Timesheet | 78.9 | Yes | 5794.42 | 2026-01 | Operational Excellence | 11835
ACT-00338 | 2026-01-31 | P-1002 | Labour | E-0024 |  | Timesheet | 85.5 | Yes | 8495.28 | 2026-01 | Operational Excellence | 17100
ACT-00339 | 2026-01-31 | P-1002 | Labour | E-0032 |  | Timesheet | 141.1 | Yes | 8398.27 | 2026-01 | Operational Excellence | 16932
ACT-00340 | 2026-01-31 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1735.69 | 2026-01 | Operational Excellence | 0
ACT-00341 | 2026-01-31 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 979.01 | 2026-01 | Operational Excellence | 0
ACT-00342 | 2026-01-31 | P-1002 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 595.32 | 2026-01 | Operational Excellence | 0
ACT-00343 | 2026-01-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3825.66 | 2026-01 | Data & AI | 0
ACT-00344 | 2026-01-31 | P-1003 | Labour | E-0005 |  | Timesheet | 45.6 | No | 3410.88 | 2026-01 | Data & AI | 0
ACT-00345 | 2026-01-31 | P-1003 | Labour | E-0013 |  | Timesheet | 44.4 | Yes | 5370.62 | 2026-01 | Data & AI | 10878
ACT-00346 | 2026-01-31 | P-1003 | Labour | E-0033 |  | Timesheet | 104.7 | Yes | 6231.74 | 2026-01 | Data & AI | 12564
ACT-00347 | 2026-01-31 | P-1003 | Labour | E-0048 |  | Timesheet | 181.9 | Yes | 18990.36 | 2026-01 | Data & AI | 38199
ACT-00348 | 2026-01-31 | P-1003 | Labour | E-0052 |  | Timesheet | 99.5 | Yes | 11311.16 | 2026-01 | Data & AI | 22885
ACT-00349 | 2026-01-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2461.97 | 2026-01 | Data & AI | 0
ACT-00350 | 2026-01-31 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 542.53 | 2026-01 | Data & AI | 0
ACT-00351 | 2026-01-31 | P-1006 | Labour | E-0009 |  | Timesheet | 119.6 | Yes | 8946.08 | 2026-01 | Customer Experience | 17940
ACT-00352 | 2026-01-31 | P-1006 | Labour | E-0019 |  | Timesheet | 116.5 | Yes | 8417.12 | 2026-01 | Customer Experience | 13980
ACT-00353 | 2026-01-31 | P-1006 | Labour | E-0021 |  | Timesheet | 180.1 | Yes | 12394.48 | 2026-01 | Customer Experience | 25214
ACT-00354 | 2026-01-31 | P-1006 | Labour | E-0026 |  | Timesheet | 180.7 | Yes | 15460.69 | 2026-01 | Customer Experience | 30719
ACT-00355 | 2026-01-31 | P-1006 | Labour | E-0035 |  | Timesheet | 242.9 | Yes | 14457.41 | 2026-01 | Customer Experience | 29148
ACT-00356 | 2026-01-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2882.91 | 2026-01 | Customer Experience | 0
ACT-00357 | 2026-01-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3641.59 | 2026-01 | Customer Experience | 0
ACT-00358 | 2026-01-31 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 704.39 | 2026-01 | Customer Experience | 0
ACT-00359 | 2026-01-31 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 5308.31 | 2026-01 | Cloud & Infrastructure | 0
ACT-00360 | 2026-01-31 | P-1008 | Labour | E-0010 |  | Timesheet | 53.3 | No | 4690.4 | 2026-01 | Cloud & Infrastructure | 0
ACT-00361 | 2026-01-31 | P-1008 | Labour | E-0012 |  | Timesheet | 45.3 | Yes | 5885.38 | 2026-01 | Cloud & Infrastructure | 11778
ACT-00362 | 2026-01-31 | P-1008 | Labour | E-0029 |  | Timesheet | 103.9 | Yes | 10323.5 | 2026-01 | Cloud & Infrastructure | 20780
ACT-00363 | 2026-01-31 | P-1008 | Labour | E-0056 |  | Timesheet | 135.7 | Yes | 15944.75 | 2026-01 | Cloud & Infrastructure | 25783
ACT-00364 | 2026-01-31 | P-1008 | Labour | E-0060 |  | Timesheet | 91.7 | Yes | 7334.17 | 2026-01 | Cloud & Infrastructure | 15130.5
ACT-00365 | 2026-01-31 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2298.01 | 2026-01 | Cloud & Infrastructure | 0
ACT-00366 | 2026-01-31 | P-1008 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 873.45 | 2026-01 | Cloud & Infrastructure | 0
ACT-00367 | 2026-01-31 | P-1010 | Labour | E-0007 |  | Timesheet | 109.7 | Yes | 11198.18 | 2026-01 | Customer Experience | 22488.5
ACT-00368 | 2026-01-31 | P-1010 | Labour | E-0018 |  | Timesheet | 117 | Yes | 8592.48 | 2026-01 | Customer Experience | 17550
ACT-00369 | 2026-01-31 | P-1010 | Labour | E-0022 |  | Timesheet | 101.1 | Yes | 6359.19 | 2026-01 | Customer Experience | 13143
ACT-00370 | 2026-01-31 | P-1010 | Labour | E-0030 |  | Timesheet | 200.1 | Yes | 17120.56 | 2026-01 | Customer Experience | 34017
ACT-00371 | 2026-01-31 | P-1010 | Labour | E-0038 |  | Timesheet | 108 | Yes | 8017.92 | 2026-01 | Customer Experience | 16200
ACT-00372 | 2026-01-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2982.03 | 2026-01 | Customer Experience | 0
ACT-00373 | 2026-01-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3454.24 | 2026-01 | Customer Experience | 0
ACT-00374 | 2026-01-31 | P-1010 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 863.92 | 2026-01 | Customer Experience | 0
ACT-00375 | 2026-01-31 | P-1013 | Labour | E-0004 |  | Timesheet | 122.7 | Yes | 12525.22 | 2026-01 | Digital Transformation | 25153.5
ACT-00376 | 2026-01-31 | P-1013 | Labour | E-0014 |  | Timesheet | 107.1 | Yes | 11155.54 | 2026-01 | Digital Transformation | 22491
ACT-00377 | 2026-01-31 | P-1013 | Labour | E-0019 |  | Timesheet | 159.8 | Yes | 11545.55 | 2026-01 | Digital Transformation | 19176
ACT-00378 | 2026-01-31 | P-1013 | Labour | E-0028 |  | Timesheet | 164.8 | Yes | 14100.29 | 2026-01 | Digital Transformation | 28016
ACT-00379 | 2026-01-31 | P-1013 | Labour | E-0041 |  | Timesheet | 116.3 | Yes | 7443.2 | 2026-01 | Digital Transformation | 15119
ACT-00380 | 2026-01-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 4289.68 | 2026-01 | Digital Transformation | 0
ACT-00381 | 2026-01-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5902.51 | 2026-01 | Digital Transformation | 0
ACT-00382 | 2026-01-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1404.26 | 2026-01 | Digital Transformation | 0
ACT-00383 | 2026-01-31 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 968.39 | 2026-01 | Digital Transformation | 0
ACT-00384 | 2026-01-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5659.07 | 2026-01 | Cloud & Infrastructure | 0
ACT-00385 | 2026-01-31 | P-1014 | Labour | E-0008 |  | Timesheet | 43.5 | Yes | 4134.24 | 2026-01 | Cloud & Infrastructure | 8265
ACT-00386 | 2026-01-31 | P-1014 | Labour | E-0011 |  | Timesheet | 48.1 | Yes | 6249.15 | 2026-01 | Cloud & Infrastructure | 12506
ACT-00387 | 2026-01-31 | P-1014 | Labour | E-0029 |  | Timesheet | 82.8 | Yes | 8227.01 | 2026-01 | Cloud & Infrastructure | 16560
ACT-00388 | 2026-01-31 | P-1014 | Labour | E-0057 |  | Timesheet | 126.4 | Yes | 13782.66 | 2026-01 | Cloud & Infrastructure | 27808
ACT-00389 | 2026-01-31 | P-1014 | Labour | E-0061 |  | Timesheet | 87.8 | Yes | 7550.8 | 2026-01 | Cloud & Infrastructure | 15365
ACT-00390 | 2026-01-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1636.33 | 2026-01 | Cloud & Infrastructure | 0
ACT-00391 | 2026-01-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 736.66 | 2026-01 | Cloud & Infrastructure | 0
ACT-00392 | 2026-01-31 | P-1017 | Labour | E-0005 |  | Timesheet | 56.2 | Yes | 4203.76 | 2026-01 | Customer Experience | 8430
ACT-00393 | 2026-01-31 | P-1017 | Labour | E-0017 |  | Timesheet | 54.1 | Yes | 3421.28 | 2026-01 | Customer Experience | 7033
ACT-00394 | 2026-01-31 | P-1017 | Labour | E-0022 |  | Timesheet | 55.9 | Yes | 3516.11 | 2026-01 | Customer Experience | 7267
ACT-00395 | 2026-01-31 | P-1017 | Labour | E-0027 |  | Timesheet | 56.7 | Yes | 5633.71 | 2026-01 | Customer Experience | 11340
ACT-00396 | 2026-01-31 | P-1017 | Labour | E-0036 |  | Timesheet | 53.5 | Yes | 3184.32 | 2026-01 | Customer Experience | 6420
ACT-00397 | 2026-01-31 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2136.99 | 2026-01 | Customer Experience | 0
ACT-00398 | 2026-01-31 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3339.84 | 2026-01 | Customer Experience | 0
ACT-00399 | 2026-01-31 | P-1017 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 627.24 | 2026-01 | Customer Experience | 0
ACT-00400 | 2026-01-31 | P-1019 | Labour | E-0010 |  | Timesheet | 100.7 | Yes | 8861.6 | 2026-01 | Digital Transformation | 17622.5
ACT-00401 | 2026-01-31 | P-1019 | Labour | E-0017 |  | Timesheet | 130 | Yes | 8221.2 | 2026-01 | Digital Transformation | 16900
ACT-00402 | 2026-01-31 | P-1019 | Labour | E-0025 |  | Timesheet | 153.3 | Yes | 16395.44 | 2026-01 | Digital Transformation | 26061
ACT-00403 | 2026-01-31 | P-1019 | Labour | E-0034 |  | Timesheet | 159.2 | Yes | 8660.48 | 2026-01 | Digital Transformation | 17512
ACT-00404 | 2026-01-31 | P-1019 | Labour | E-0042 |  | Timesheet | 101.4 | Yes | 6586.94 | 2026-01 | Digital Transformation | 13689
ACT-00405 | 2026-01-31 | P-1019 | Labour | E-0062 |  | Timesheet | 46.9 | Yes | 3917.09 | 2026-01 | Digital Transformation | 8207.5
ACT-00406 | 2026-01-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3692.49 | 2026-01 | Digital Transformation | 0
ACT-00407 | 2026-01-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5209.24 | 2026-01 | Digital Transformation | 0
ACT-00408 | 2026-01-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1581.61 | 2026-01 | Digital Transformation | 0
ACT-00409 | 2026-01-31 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1043.8 | 2026-01 | Digital Transformation | 0
ACT-00410 | 2026-01-31 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3776.93 | 2026-01 | Data & AI | 0
ACT-00411 | 2026-01-31 | P-1020 | Labour | E-0006 |  | Timesheet | 82 | No | 7216 | 2026-01 | Data & AI | 0
ACT-00412 | 2026-01-31 | P-1020 | Labour | E-0012 |  | Timesheet | 45.3 | Yes | 5885.38 | 2026-01 | Data & AI | 11778
ACT-00413 | 2026-01-31 | P-1020 | Labour | E-0037 |  | Timesheet | 93.2 | Yes | 6337.6 | 2026-01 | Data & AI | 10252
ACT-00414 | 2026-01-31 | P-1020 | Labour | E-0043 |  | Timesheet | 11.7 | Yes | 950.04 | 2026-01 | Data & AI | 1579.5
ACT-00415 | 2026-01-31 | P-1020 | Labour | E-0051 |  | Timesheet | 163.9 | Yes | 15931.08 | 2026-01 | Data & AI | 31960.5
ACT-00416 | 2026-01-31 | P-1020 | Labour | E-0053 |  | Timesheet | 116.9 | Yes | 11456.2 | 2026-01 | Data & AI | 23380
ACT-00417 | 2026-01-31 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2717.52 | 2026-01 | Data & AI | 0
ACT-00418 | 2026-01-31 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 613.53 | 2026-01 | Data & AI | 0
ACT-00419 | 2026-02-28 | P-1001 | Labour | E-0003 |  | Timesheet | 73.5 | Yes | 7502.88 | 2026-02 | Customer Experience | 15067.5
ACT-00420 | 2026-02-28 | P-1001 | Labour | E-0015 |  | Timesheet | 81.7 | Yes | 6444.5 | 2026-02 | Customer Experience | 13072
ACT-00421 | 2026-02-28 | P-1001 | Labour | E-0020 |  | Timesheet | 110.8 | Yes | 9511.07 | 2026-02 | Customer Experience | 19390
ACT-00422 | 2026-02-28 | P-1001 | Labour | E-0023 |  | Timesheet | 111.8 | Yes | 11931.3 | 2026-02 | Customer Experience | 24037
ACT-00423 | 2026-02-28 | P-1001 | Labour | E-0031 |  | Timesheet | 158.8 | Yes | 11789.31 | 2026-02 | Customer Experience | 23820
ACT-00424 | 2026-02-28 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2739.38 | 2026-02 | Customer Experience | 0
ACT-00425 | 2026-02-28 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4118.65 | 2026-02 | Customer Experience | 0
ACT-00426 | 2026-02-28 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1096.14 | 2026-02 | Customer Experience | 0
ACT-00427 | 2026-02-28 | P-1002 | Labour | E-0004 |  | Timesheet | 60.1 | Yes | 6135.01 | 2026-02 | Operational Excellence | 12320.5
ACT-00428 | 2026-02-28 | P-1002 | Labour | E-0016 |  | Timesheet | 116.8 | Yes | 8577.79 | 2026-02 | Operational Excellence | 17520
ACT-00429 | 2026-02-28 | P-1002 | Labour | E-0024 |  | Timesheet | 109.3 | Yes | 10860.05 | 2026-02 | Operational Excellence | 21860
ACT-00430 | 2026-02-28 | P-1002 | Labour | E-0032 |  | Timesheet | 176.2 | Yes | 10487.42 | 2026-02 | Operational Excellence | 21144
ACT-00431 | 2026-02-28 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1927.24 | 2026-02 | Operational Excellence | 0
ACT-00432 | 2026-02-28 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 782.12 | 2026-02 | Operational Excellence | 0
ACT-00433 | 2026-02-28 | P-1002 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 643.47 | 2026-02 | Operational Excellence | 0
ACT-00434 | 2026-02-28 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4647.14 | 2026-02 | Data & AI | 0
ACT-00435 | 2026-02-28 | P-1003 | Labour | E-0005 |  | Timesheet | 43.6 | No | 3261.28 | 2026-02 | Data & AI | 0
ACT-00436 | 2026-02-28 | P-1003 | Labour | E-0013 |  | Timesheet | 46.9 | Yes | 5673.02 | 2026-02 | Data & AI | 11490.5
ACT-00437 | 2026-02-28 | P-1003 | Labour | E-0033 |  | Timesheet | 83.6 | Yes | 4975.87 | 2026-02 | Data & AI | 10032
ACT-00438 | 2026-02-28 | P-1003 | Labour | E-0048 |  | Timesheet | 180.6 | Yes | 18854.64 | 2026-02 | Data & AI | 37926
ACT-00439 | 2026-02-28 | P-1003 | Labour | E-0052 |  | Timesheet | 94.6 | Yes | 10754.13 | 2026-02 | Data & AI | 21758
ACT-00440 | 2026-02-28 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2881.27 | 2026-02 | Data & AI | 0
ACT-00441 | 2026-02-28 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 516.09 | 2026-02 | Data & AI | 0
ACT-00442 | 2026-02-28 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6962.64 | 2026-02 | Cloud & Infrastructure | 0
ACT-00443 | 2026-02-28 | P-1004 | Labour | E-0006 |  | Timesheet | 40.6 | Yes | 3572.8 | 2026-02 | Cloud & Infrastructure | 7105
ACT-00444 | 2026-02-28 | P-1004 | Labour | E-0011 |  | Timesheet | 38.9 | Yes | 5053.89 | 2026-02 | Cloud & Infrastructure | 10114
ACT-00445 | 2026-02-28 | P-1004 | Labour | E-0025 |  | Timesheet | 72.1 | Yes | 7711.09 | 2026-02 | Cloud & Infrastructure | 12257
ACT-00446 | 2026-02-28 | P-1004 | Labour | E-0055 |  | Timesheet | 173.7 | Yes | 18940.25 | 2026-02 | Cloud & Infrastructure | 38214
ACT-00447 | 2026-02-28 | P-1004 | Labour | E-0059 |  | Timesheet | 87.4 | Yes | 8719.02 | 2026-02 | Cloud & Infrastructure | 17917
ACT-00448 | 2026-02-28 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2528.1 | 2026-02 | Cloud & Infrastructure | 0
ACT-00449 | 2026-02-28 | P-1004 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 834.74 | 2026-02 | Cloud & Infrastructure | 0
ACT-00450 | 2026-02-28 | P-1006 | Labour | E-0009 |  | Timesheet | 110.4 | Yes | 8257.92 | 2026-02 | Customer Experience | 16560
ACT-00451 | 2026-02-28 | P-1006 | Labour | E-0019 |  | Timesheet | 95.6 | Yes | 6907.1 | 2026-02 | Customer Experience | 11472
ACT-00452 | 2026-02-28 | P-1006 | Labour | E-0021 |  | Timesheet | 163.9 | Yes | 11279.6 | 2026-02 | Customer Experience | 22946
ACT-00453 | 2026-02-28 | P-1006 | Labour | E-0026 |  | Timesheet | 155.8 | Yes | 13330.25 | 2026-02 | Customer Experience | 26486
ACT-00454 | 2026-02-28 | P-1006 | Labour | E-0035 |  | Timesheet | 196.1 | Yes | 11671.87 | 2026-02 | Customer Experience | 23532
ACT-00455 | 2026-02-28 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2698.69 | 2026-02 | Customer Experience | 0
ACT-00456 | 2026-02-28 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4586.54 | 2026-02 | Customer Experience | 0
ACT-00457 | 2026-02-28 | P-1006 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 850.76 | 2026-02 | Customer Experience | 0
ACT-00458 | 2026-02-28 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 5313.89 | 2026-02 | Cloud & Infrastructure | 0
ACT-00459 | 2026-02-28 | P-1008 | Labour | E-0010 |  | Timesheet | 45.7 | No | 4021.6 | 2026-02 | Cloud & Infrastructure | 0
ACT-00460 | 2026-02-28 | P-1008 | Labour | E-0012 |  | Timesheet | 48.4 | Yes | 6288.13 | 2026-02 | Cloud & Infrastructure | 12584
ACT-00461 | 2026-02-28 | P-1008 | Labour | E-0029 |  | Timesheet | 94.6 | Yes | 9399.46 | 2026-02 | Cloud & Infrastructure | 18920
ACT-00462 | 2026-02-28 | P-1008 | Labour | E-0056 |  | Timesheet | 144.3 | Yes | 16955.25 | 2026-02 | Cloud & Infrastructure | 27417
ACT-00463 | 2026-02-28 | P-1008 | Labour | E-0060 |  | Timesheet | 90.8 | Yes | 7262.18 | 2026-02 | Cloud & Infrastructure | 14982
ACT-00464 | 2026-02-28 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2171.73 | 2026-02 | Cloud & Infrastructure | 0
ACT-00465 | 2026-02-28 | P-1008 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 817.59 | 2026-02 | Cloud & Infrastructure | 0
ACT-00466 | 2026-02-28 | P-1010 | Labour | E-0007 |  | Timesheet | 109.8 | Yes | 11208.38 | 2026-02 | Customer Experience | 22509
ACT-00467 | 2026-02-28 | P-1010 | Labour | E-0018 |  | Timesheet | 91.4 | Yes | 6712.42 | 2026-02 | Customer Experience | 13710
ACT-00468 | 2026-02-28 | P-1010 | Labour | E-0022 |  | Timesheet | 108.1 | Yes | 6799.49 | 2026-02 | Customer Experience | 14053
ACT-00469 | 2026-02-28 | P-1010 | Labour | E-0030 |  | Timesheet | 216.6 | Yes | 18532.3 | 2026-02 | Customer Experience | 36822
ACT-00470 | 2026-02-28 | P-1010 | Labour | E-0038 |  | Timesheet | 100.7 | Yes | 7475.97 | 2026-02 | Customer Experience | 15105
ACT-00471 | 2026-02-28 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3632.44 | 2026-02 | Customer Experience | 0
ACT-00472 | 2026-02-28 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4262.85 | 2026-02 | Customer Experience | 0
ACT-00473 | 2026-02-28 | P-1010 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 767.83 | 2026-02 | Customer Experience | 0
ACT-00474 | 2026-02-28 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2873.39 | 2026-02 | Data & AI | 0
ACT-00475 | 2026-02-28 | P-1011 | Labour | E-0006 |  | Timesheet | 19.6 | No | 1724.8 | 2026-02 | Data & AI | 0
ACT-00476 | 2026-02-28 | P-1011 | Labour | E-0013 |  | Timesheet | 19.9 | Yes | 2407.1 | 2026-02 | Data & AI | 4875.5
ACT-00477 | 2026-02-28 | P-1011 | Labour | E-0039 |  | Timesheet | 42.4 | Yes | 2306.56 | 2026-02 | Data & AI | 4664
ACT-00478 | 2026-02-28 | P-1011 | Labour | E-0050 |  | Timesheet | 44.5 | Yes | 4645.8 | 2026-02 | Data & AI | 9345
ACT-00479 | 2026-02-28 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2258.19 | 2026-02 | Data & AI | 0
ACT-00480 | 2026-02-28 | P-1011 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 444.4 | 2026-02 | Data & AI | 0
ACT-00481 | 2026-02-28 | P-1013 | Labour | E-0004 |  | Timesheet | 103.9 | Yes | 10606.11 | 2026-02 | Digital Transformation | 21299.5
ACT-00482 | 2026-02-28 | P-1013 | Labour | E-0014 |  | Timesheet | 95.5 | Yes | 9947.28 | 2026-02 | Digital Transformation | 20055
ACT-00483 | 2026-02-28 | P-1013 | Labour | E-0019 |  | Timesheet | 151.2 | Yes | 10924.2 | 2026-02 | Digital Transformation | 18144
ACT-00484 | 2026-02-28 | P-1013 | Labour | E-0028 |  | Timesheet | 152.2 | Yes | 13022.23 | 2026-02 | Digital Transformation | 25874
ACT-00485 | 2026-02-28 | P-1013 | Labour | E-0041 |  | Timesheet | 103.6 | Yes | 6630.4 | 2026-02 | Digital Transformation | 13468
ACT-00486 | 2026-02-28 | P-1013 | Labour | E-0047 |  | Timesheet | 27 | Yes | 1753.92 | 2026-02 | Digital Transformation | 3645
ACT-00487 | 2026-02-28 | P-1013 | Labour | E-0063 |  | Timesheet | 11 | Yes | 855.36 | 2026-02 | Digital Transformation | 1760
ACT-00488 | 2026-02-28 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3776.21 | 2026-02 | Digital Transformation | 0
ACT-00489 | 2026-02-28 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5296.89 | 2026-02 | Digital Transformation | 0
ACT-00490 | 2026-02-28 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1472.5 | 2026-02 | Digital Transformation | 0
ACT-00491 | 2026-02-28 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 987.59 | 2026-02 | Digital Transformation | 0
ACT-00492 | 2026-02-28 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5323.43 | 2026-02 | Cloud & Infrastructure | 0
ACT-00493 | 2026-02-28 | P-1014 | Labour | E-0008 |  | Timesheet | 39.9 | Yes | 3792.1 | 2026-02 | Cloud & Infrastructure | 7581
ACT-00494 | 2026-02-28 | P-1014 | Labour | E-0011 |  | Timesheet | 41.8 | Yes | 5430.66 | 2026-02 | Cloud & Infrastructure | 10868
ACT-00495 | 2026-02-28 | P-1014 | Labour | E-0029 |  | Timesheet | 80.9 | Yes | 8038.22 | 2026-02 | Cloud & Infrastructure | 16180
ACT-00496 | 2026-02-28 | P-1014 | Labour | E-0057 |  | Timesheet | 124.8 | Yes | 13608.19 | 2026-02 | Cloud & Infrastructure | 27456
ACT-00497 | 2026-02-28 | P-1014 | Labour | E-0061 |  | Timesheet | 78.2 | Yes | 6725.2 | 2026-02 | Cloud & Infrastructure | 13685
ACT-00498 | 2026-02-28 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1883.88 | 2026-02 | Cloud & Infrastructure | 0
ACT-00499 | 2026-02-28 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 728.61 | 2026-02 | Cloud & Infrastructure | 0
ACT-00500 | 2026-02-28 | P-1017 | Labour | E-0005 |  | Timesheet | 121.3 | Yes | 9073.24 | 2026-02 | Customer Experience | 18195
ACT-00501 | 2026-02-28 | P-1017 | Labour | E-0017 |  | Timesheet | 114.4 | Yes | 7234.66 | 2026-02 | Customer Experience | 14872
ACT-00502 | 2026-02-28 | P-1017 | Labour | E-0022 |  | Timesheet | 117.4 | Yes | 7384.46 | 2026-02 | Customer Experience | 15262
ACT-00503 | 2026-02-28 | P-1017 | Labour | E-0027 |  | Timesheet | 110.5 | Yes | 10979.28 | 2026-02 | Customer Experience | 22100
ACT-00504 | 2026-02-28 | P-1017 | Labour | E-0036 |  | Timesheet | 110.9 | Yes | 6600.77 | 2026-02 | Customer Experience | 13308
ACT-00505 | 2026-02-28 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2490.17 | 2026-02 | Customer Experience | 0
ACT-00506 | 2026-02-28 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3043.8 | 2026-02 | Customer Experience | 0
ACT-00507 | 2026-02-28 | P-1017 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 683.21 | 2026-02 | Customer Experience | 0
ACT-00508 | 2026-02-28 | P-1019 | Labour | E-0010 |  | Timesheet | 82.9 | Yes | 7295.2 | 2026-02 | Digital Transformation | 14507.5
ACT-00509 | 2026-02-28 | P-1019 | Labour | E-0017 |  | Timesheet | 121.4 | Yes | 7677.34 | 2026-02 | Digital Transformation | 15782
ACT-00510 | 2026-02-28 | P-1019 | Labour | E-0025 |  | Timesheet | 117.4 | Yes | 12555.93 | 2026-02 | Digital Transformation | 19958
ACT-00511 | 2026-02-28 | P-1019 | Labour | E-0034 |  | Timesheet | 150.5 | Yes | 8187.2 | 2026-02 | Digital Transformation | 16555
ACT-00512 | 2026-02-28 | P-1019 | Labour | E-0042 |  | Timesheet | 83.1 | Yes | 5398.18 | 2026-02 | Digital Transformation | 11218.5
ACT-00513 | 2026-02-28 | P-1019 | Labour | E-0062 |  | Timesheet | 41.9 | Yes | 3499.49 | 2026-02 | Digital Transformation | 7332.5
ACT-00514 | 2026-02-28 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3612.9 | 2026-02 | Digital Transformation | 0
ACT-00515 | 2026-02-28 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5566.95 | 2026-02 | Digital Transformation | 0
ACT-00516 | 2026-02-28 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1363.29 | 2026-02 | Digital Transformation | 0
ACT-00517 | 2026-02-28 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 820.33 | 2026-02 | Digital Transformation | 0
ACT-00518 | 2026-02-28 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 4106.74 | 2026-02 | Data & AI | 0
ACT-00519 | 2026-02-28 | P-1020 | Labour | E-0006 |  | Timesheet | 73.4 | No | 6459.2 | 2026-02 | Data & AI | 0
ACT-00520 | 2026-02-28 | P-1020 | Labour | E-0012 |  | Timesheet | 21.2 | Yes | 2754.3 | 2026-02 | Data & AI | 5512
ACT-00521 | 2026-02-28 | P-1020 | Labour | E-0037 |  | Timesheet | 78.7 | Yes | 5351.6 | 2026-02 | Data & AI | 8657
ACT-00522 | 2026-02-28 | P-1020 | Labour | E-0043 |  | Timesheet | 41.9 | Yes | 3402.28 | 2026-02 | Data & AI | 5656.5
ACT-00523 | 2026-02-28 | P-1020 | Labour | E-0051 |  | Timesheet | 163.2 | Yes | 15863.04 | 2026-02 | Data & AI | 31824
ACT-00524 | 2026-02-28 | P-1020 | Labour | E-0053 |  | Timesheet | 110 | Yes | 10780 | 2026-02 | Data & AI | 22000
ACT-00525 | 2026-02-28 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2191.98 | 2026-02 | Data & AI | 0
ACT-00526 | 2026-02-28 | P-1020 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 537.61 | 2026-02 | Data & AI | 0
ACT-00527 | 2026-02-28 | P-1021 | Labour | E-0010 |  | Timesheet | 34.9 | Yes | 3071.2 | 2026-02 | Operational Excellence | 6107.5
ACT-00528 | 2026-02-28 | P-1021 | Labour | E-0016 |  | Timesheet | 65.1 | Yes | 4780.94 | 2026-02 | Operational Excellence | 9765
ACT-00529 | 2026-02-28 | P-1021 | Labour | E-0026 |  | Timesheet | 96.4 | Yes | 8247.98 | 2026-02 | Operational Excellence | 16388
ACT-00530 | 2026-02-28 | P-1021 | Labour | E-0033 |  | Timesheet | 66.8 | Yes | 3975.94 | 2026-02 | Operational Excellence | 8016
ACT-00531 | 2026-02-28 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1529.79 | 2026-02 | Operational Excellence | 0
ACT-00532 | 2026-02-28 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 825.99 | 2026-02 | Operational Excellence | 0
ACT-00533 | 2026-02-28 | P-1021 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 663.66 | 2026-02 | Operational Excellence | 0
ACT-00534 | 2026-03-31 | P-1001 | Labour | E-0003 |  | Timesheet | 88.4 | Yes | 9023.87 | 2026-03 | Customer Experience | 18122
ACT-00535 | 2026-03-31 | P-1001 | Labour | E-0015 |  | Timesheet | 80.8 | Yes | 6373.5 | 2026-03 | Customer Experience | 12928
ACT-00536 | 2026-03-31 | P-1001 | Labour | E-0020 |  | Timesheet | 129.8 | Yes | 11142.03 | 2026-03 | Customer Experience | 22715
ACT-00537 | 2026-03-31 | P-1001 | Labour | E-0023 |  | Timesheet | 127.6 | Yes | 13617.47 | 2026-03 | Customer Experience | 27434
ACT-00538 | 2026-03-31 | P-1001 | Labour | E-0031 |  | Timesheet | 163.6 | Yes | 12145.66 | 2026-03 | Customer Experience | 24540
ACT-00539 | 2026-03-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3246.02 | 2026-03 | Customer Experience | 0
ACT-00540 | 2026-03-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4073.35 | 2026-03 | Customer Experience | 0
ACT-00541 | 2026-03-31 | P-1001 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 938.44 | 2026-03 | Customer Experience | 0
ACT-00542 | 2026-03-31 | P-1002 | Labour | E-0004 |  | Timesheet | 64.5 | Yes | 6584.16 | 2026-03 | Operational Excellence | 13222.5
ACT-00543 | 2026-03-31 | P-1002 | Labour | E-0016 |  | Timesheet | 134.5 | Yes | 9877.68 | 2026-03 | Operational Excellence | 20175
ACT-00544 | 2026-03-31 | P-1002 | Labour | E-0024 |  | Timesheet | 135.5 | Yes | 13463.28 | 2026-03 | Operational Excellence | 27100
ACT-00545 | 2026-03-31 | P-1002 | Labour | E-0032 |  | Timesheet | 182.4 | Yes | 10856.45 | 2026-03 | Operational Excellence | 21888
ACT-00546 | 2026-03-31 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1771.54 | 2026-03 | Operational Excellence | 0
ACT-00547 | 2026-03-31 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 881.55 | 2026-03 | Operational Excellence | 0
ACT-00548 | 2026-03-31 | P-1002 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 568.9 | 2026-03 | Operational Excellence | 0
ACT-00549 | 2026-03-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4442.18 | 2026-03 | Data & AI | 0
ACT-00550 | 2026-03-31 | P-1003 | Labour | E-0005 |  | Timesheet | 52.8 | No | 3949.44 | 2026-03 | Data & AI | 0
ACT-00551 | 2026-03-31 | P-1003 | Labour | E-0013 |  | Timesheet | 50.6 | Yes | 6120.58 | 2026-03 | Data & AI | 12397
ACT-00552 | 2026-03-31 | P-1003 | Labour | E-0033 |  | Timesheet | 106.2 | Yes | 6321.02 | 2026-03 | Data & AI | 12744
ACT-00553 | 2026-03-31 | P-1003 | Labour | E-0044 |  | Timesheet | 14.1 | Yes | 987 | 2026-03 | Data & AI | 1621.5
ACT-00554 | 2026-03-31 | P-1003 | Labour | E-0048 |  | Timesheet | 180.4 | Yes | 18833.76 | 2026-03 | Data & AI | 37884
ACT-00555 | 2026-03-31 | P-1003 | Labour | E-0052 |  | Timesheet | 88.2 | Yes | 10026.58 | 2026-03 | Data & AI | 20286
ACT-00556 | 2026-03-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2852 | 2026-03 | Data & AI | 0
ACT-00557 | 2026-03-31 | P-1003 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 577.67 | 2026-03 | Data & AI | 0
ACT-00558 | 2026-03-31 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6237.35 | 2026-03 | Cloud & Infrastructure | 0
ACT-00559 | 2026-03-31 | P-1004 | Labour | E-0006 |  | Timesheet | 39.6 | Yes | 3484.8 | 2026-03 | Cloud & Infrastructure | 6930
ACT-00560 | 2026-03-31 | P-1004 | Labour | E-0011 |  | Timesheet | 47.9 | Yes | 6223.17 | 2026-03 | Cloud & Infrastructure | 12454
ACT-00561 | 2026-03-31 | P-1004 | Labour | E-0025 |  | Timesheet | 79.5 | Yes | 8502.52 | 2026-03 | Cloud & Infrastructure | 13515
ACT-00562 | 2026-03-31 | P-1004 | Labour | E-0055 |  | Timesheet | 179.5 | Yes | 19572.68 | 2026-03 | Cloud & Infrastructure | 39490
ACT-00563 | 2026-03-31 | P-1004 | Labour | E-0059 |  | Timesheet | 94.6 | Yes | 9437.3 | 2026-03 | Cloud & Infrastructure | 19393
ACT-00564 | 2026-03-31 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2465.87 | 2026-03 | Cloud & Infrastructure | 0
ACT-00565 | 2026-03-31 | P-1004 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 921.41 | 2026-03 | Cloud & Infrastructure | 0
ACT-00566 | 2026-03-31 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3186.24 | 2026-03 | Data & AI | 0
ACT-00567 | 2026-03-31 | P-1005 | Labour | E-0007 |  | Timesheet | 59.1 | Yes | 6032.93 | 2026-03 | Data & AI | 12115.5
ACT-00568 | 2026-03-31 | P-1005 | Labour | E-0012 |  | Timesheet | 58.1 | Yes | 7548.35 | 2026-03 | Data & AI | 15106
ACT-00569 | 2026-03-31 | P-1005 | Labour | E-0034 |  | Timesheet | 106.2 | Yes | 5777.28 | 2026-03 | Data & AI | 11682
ACT-00570 | 2026-03-31 | P-1005 | Labour | E-0049 |  | Timesheet | 179.6 | Yes | 13739.4 | 2026-03 | Data & AI | 27838
ACT-00571 | 2026-03-31 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1868.72 | 2026-03 | Data & AI | 0
ACT-00572 | 2026-03-31 | P-1005 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 442.39 | 2026-03 | Data & AI | 0
ACT-00573 | 2026-03-31 | P-1006 | Labour | E-0009 |  | Timesheet | 106.1 | Yes | 7936.28 | 2026-03 | Customer Experience | 15915
ACT-00574 | 2026-03-31 | P-1006 | Labour | E-0019 |  | Timesheet | 101 | Yes | 7297.25 | 2026-03 | Customer Experience | 12120
ACT-00575 | 2026-03-31 | P-1006 | Labour | E-0021 |  | Timesheet | 170.6 | Yes | 11740.69 | 2026-03 | Customer Experience | 23884
ACT-00576 | 2026-03-31 | P-1006 | Labour | E-0026 |  | Timesheet | 159.9 | Yes | 13681.04 | 2026-03 | Customer Experience | 27183
ACT-00577 | 2026-03-31 | P-1006 | Labour | E-0035 |  | Timesheet | 242.8 | Yes | 14451.46 | 2026-03 | Customer Experience | 29136
ACT-00578 | 2026-03-31 | P-1006 | Labour | E-0045 |  | Timesheet | 63.7 | Yes | 3317.5 | 2026-03 | Customer Experience | 6688.5
ACT-00579 | 2026-03-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2659.01 | 2026-03 | Customer Experience | 0
ACT-00580 | 2026-03-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3951 | 2026-03 | Customer Experience | 0
ACT-00581 | 2026-03-31 | P-1006 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 727.62 | 2026-03 | Customer Experience | 0
ACT-00582 | 2026-03-31 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 4475.92 | 2026-03 | Cloud & Infrastructure | 0
ACT-00583 | 2026-03-31 | P-1008 | Hardware |  | Rockwell Automation | AP Invoice | 0 | No | 21117.45 | 2026-03 | Cloud & Infrastructure | 0
ACT-00584 | 2026-03-31 | P-1008 | Labour | E-0010 |  | Timesheet | 57.7 | No | 5077.6 | 2026-03 | Cloud & Infrastructure | 0
ACT-00585 | 2026-03-31 | P-1008 | Labour | E-0012 |  | Timesheet | 53.7 | Yes | 6976.7 | 2026-03 | Cloud & Infrastructure | 13962
ACT-00586 | 2026-03-31 | P-1008 | Labour | E-0029 |  | Timesheet | 117.4 | Yes | 11664.86 | 2026-03 | Cloud & Infrastructure | 23480
ACT-00587 | 2026-03-31 | P-1008 | Labour | E-0056 |  | Timesheet | 147.6 | Yes | 17343 | 2026-03 | Cloud & Infrastructure | 28044
ACT-00588 | 2026-03-31 | P-1008 | Labour | E-0060 |  | Timesheet | 112.7 | Yes | 9013.75 | 2026-03 | Cloud & Infrastructure | 18595.5
ACT-00589 | 2026-03-31 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2150.28 | 2026-03 | Cloud & Infrastructure | 0
ACT-00590 | 2026-03-31 | P-1008 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 887.7 | 2026-03 | Cloud & Infrastructure | 0
ACT-00591 | 2026-03-31 | P-1010 | Labour | E-0007 |  | Timesheet | 106.7 | Yes | 10891.94 | 2026-03 | Customer Experience | 21873.5
ACT-00592 | 2026-03-31 | P-1010 | Labour | E-0018 |  | Timesheet | 108.1 | Yes | 7938.86 | 2026-03 | Customer Experience | 16215
ACT-00593 | 2026-03-31 | P-1010 | Labour | E-0022 |  | Timesheet | 104.5 | Yes | 6573.05 | 2026-03 | Customer Experience | 13585
ACT-00594 | 2026-03-31 | P-1010 | Labour | E-0030 |  | Timesheet | 212.3 | Yes | 18164.39 | 2026-03 | Customer Experience | 36091
ACT-00595 | 2026-03-31 | P-1010 | Labour | E-0038 |  | Timesheet | 116.2 | Yes | 8626.69 | 2026-03 | Customer Experience | 17430
ACT-00596 | 2026-03-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3305.66 | 2026-03 | Customer Experience | 0
ACT-00597 | 2026-03-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4002.36 | 2026-03 | Customer Experience | 0
ACT-00598 | 2026-03-31 | P-1010 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 784.58 | 2026-03 | Customer Experience | 0
ACT-00599 | 2026-03-31 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2819.35 | 2026-03 | Data & AI | 0
ACT-00600 | 2026-03-31 | P-1011 | Labour | E-0006 |  | Timesheet | 43.4 | No | 3819.2 | 2026-03 | Data & AI | 0
ACT-00601 | 2026-03-31 | P-1011 | Labour | E-0013 |  | Timesheet | 42.6 | Yes | 5152.9 | 2026-03 | Data & AI | 10437
ACT-00602 | 2026-03-31 | P-1011 | Labour | E-0039 |  | Timesheet | 83.9 | Yes | 4564.16 | 2026-03 | Data & AI | 9229
ACT-00603 | 2026-03-31 | P-1011 | Labour | E-0050 |  | Timesheet | 96.3 | Yes | 10053.72 | 2026-03 | Data & AI | 20223
ACT-00604 | 2026-03-31 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2467.4 | 2026-03 | Data & AI | 0
ACT-00605 | 2026-03-31 | P-1011 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 513.5 | 2026-03 | Data & AI | 0
ACT-00606 | 2026-03-31 | P-1013 | Labour | E-0004 |  | Timesheet | 112.6 | Yes | 11494.21 | 2026-03 | Digital Transformation | 23083
ACT-00607 | 2026-03-31 | P-1013 | Labour | E-0014 |  | Timesheet | 105.2 | Yes | 10957.63 | 2026-03 | Digital Transformation | 22092
ACT-00608 | 2026-03-31 | P-1013 | Labour | E-0019 |  | Timesheet | 166.8 | Yes | 12051.3 | 2026-03 | Digital Transformation | 20016
ACT-00609 | 2026-03-31 | P-1013 | Labour | E-0028 |  | Timesheet | 181.8 | Yes | 15554.81 | 2026-03 | Digital Transformation | 30906
ACT-00610 | 2026-03-31 | P-1013 | Labour | E-0041 |  | Timesheet | 102.5 | Yes | 6560 | 2026-03 | Digital Transformation | 13325
ACT-00611 | 2026-03-31 | P-1013 | Labour | E-0047 |  | Timesheet | 119.6 | Yes | 7769.22 | 2026-03 | Digital Transformation | 16146
ACT-00612 | 2026-03-31 | P-1013 | Labour | E-0063 |  | Timesheet | 48 | Yes | 3732.48 | 2026-03 | Digital Transformation | 7680
ACT-00613 | 2026-03-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 4501.83 | 2026-03 | Digital Transformation | 0
ACT-00614 | 2026-03-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5896.36 | 2026-03 | Digital Transformation | 0
ACT-00615 | 2026-03-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1348.47 | 2026-03 | Digital Transformation | 0
ACT-00616 | 2026-03-31 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 961.62 | 2026-03 | Digital Transformation | 0
ACT-00617 | 2026-03-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4391.12 | 2026-03 | Cloud & Infrastructure | 0
ACT-00618 | 2026-03-31 | P-1014 | Labour | E-0008 |  | Timesheet | 42.8 | Yes | 4067.71 | 2026-03 | Cloud & Infrastructure | 8132
ACT-00619 | 2026-03-31 | P-1014 | Labour | E-0011 |  | Timesheet | 43 | Yes | 5586.56 | 2026-03 | Cloud & Infrastructure | 11180
ACT-00620 | 2026-03-31 | P-1014 | Labour | E-0029 |  | Timesheet | 89.5 | Yes | 8892.72 | 2026-03 | Cloud & Infrastructure | 17900
ACT-00621 | 2026-03-31 | P-1014 | Labour | E-0057 |  | Timesheet | 129 | Yes | 14066.16 | 2026-03 | Cloud & Infrastructure | 28380
ACT-00622 | 2026-03-31 | P-1014 | Labour | E-0061 |  | Timesheet | 87.6 | Yes | 7533.6 | 2026-03 | Cloud & Infrastructure | 15330
ACT-00623 | 2026-03-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1893.39 | 2026-03 | Cloud & Infrastructure | 0
ACT-00624 | 2026-03-31 | P-1014 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 791.42 | 2026-03 | Cloud & Infrastructure | 0
ACT-00625 | 2026-03-31 | P-1015 | Labour | E-0009 |  | Timesheet | 55 | Yes | 4114 | 2026-03 | Digital Transformation | 8250
ACT-00626 | 2026-03-31 | P-1015 | Labour | E-0013 |  | Timesheet | 28.1 | Yes | 3398.98 | 2026-03 | Digital Transformation | 6884.5
ACT-00627 | 2026-03-31 | P-1015 | Labour | E-0015 |  | Timesheet | 62.6 | Yes | 4937.89 | 2026-03 | Digital Transformation | 10016
ACT-00628 | 2026-03-31 | P-1015 | Labour | E-0024 |  | Timesheet | 85.2 | Yes | 8465.47 | 2026-03 | Digital Transformation | 17040
ACT-00629 | 2026-03-31 | P-1015 | Labour | E-0040 |  | Timesheet | 88 | Yes | 5632 | 2026-03 | Digital Transformation | 11440
ACT-00630 | 2026-03-31 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3932.39 | 2026-03 | Digital Transformation | 0
ACT-00631 | 2026-03-31 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5041.17 | 2026-03 | Digital Transformation | 0
ACT-00632 | 2026-03-31 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1348.85 | 2026-03 | Digital Transformation | 0
ACT-00633 | 2026-03-31 | P-1015 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 964 | 2026-03 | Digital Transformation | 0
ACT-00634 | 2026-03-31 | P-1017 | Labour | E-0005 |  | Timesheet | 120.6 | Yes | 9020.88 | 2026-03 | Customer Experience | 18090
ACT-00635 | 2026-03-31 | P-1017 | Labour | E-0017 |  | Timesheet | 133.7 | Yes | 8455.19 | 2026-03 | Customer Experience | 17381
ACT-00636 | 2026-03-31 | P-1017 | Labour | E-0022 |  | Timesheet | 127.3 | Yes | 8007.17 | 2026-03 | Customer Experience | 16549
ACT-00637 | 2026-03-31 | P-1017 | Labour | E-0027 |  | Timesheet | 137 | Yes | 13612.32 | 2026-03 | Customer Experience | 27400
ACT-00638 | 2026-03-31 | P-1017 | Labour | E-0036 |  | Timesheet | 127.5 | Yes | 7588.8 | 2026-03 | Customer Experience | 15300
ACT-00639 | 2026-03-31 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2222.97 | 2026-03 | Customer Experience | 0
ACT-00640 | 2026-03-31 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 2926.97 | 2026-03 | Customer Experience | 0
ACT-00641 | 2026-03-31 | P-1017 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 647.25 | 2026-03 | Customer Experience | 0
ACT-00642 | 2026-03-31 | P-1019 | Labour | E-0010 |  | Timesheet | 104.8 | Yes | 9222.4 | 2026-03 | Digital Transformation | 18340
ACT-00643 | 2026-03-31 | P-1019 | Labour | E-0017 |  | Timesheet | 136.6 | Yes | 8638.58 | 2026-03 | Digital Transformation | 17758
ACT-00644 | 2026-03-31 | P-1019 | Labour | E-0025 |  | Timesheet | 151.2 | Yes | 16170.84 | 2026-03 | Digital Transformation | 25704
ACT-00645 | 2026-03-31 | P-1019 | Labour | E-0034 |  | Timesheet | 167.6 | Yes | 9117.44 | 2026-03 | Digital Transformation | 18436
ACT-00646 | 2026-03-31 | P-1019 | Labour | E-0042 |  | Timesheet | 102.3 | Yes | 6645.41 | 2026-03 | Digital Transformation | 13810.5
ACT-00647 | 2026-03-31 | P-1019 | Labour | E-0062 |  | Timesheet | 43 | Yes | 3591.36 | 2026-03 | Digital Transformation | 7525
ACT-00648 | 2026-03-31 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3292.58 | 2026-03 | Digital Transformation | 0
ACT-00649 | 2026-03-31 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5965.98 | 2026-03 | Digital Transformation | 0
ACT-00650 | 2026-03-31 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1629.34 | 2026-03 | Digital Transformation | 0
ACT-00651 | 2026-03-31 | P-1019 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 904.57 | 2026-03 | Digital Transformation | 0
ACT-00652 | 2026-03-31 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3562.26 | 2026-03 | Data & AI | 0
ACT-00653 | 2026-03-31 | P-1020 | Labour | E-0006 |  | Timesheet | 79.3 | No | 6978.4 | 2026-03 | Data & AI | 0
ACT-00654 | 2026-03-31 | P-1020 | Labour | E-0037 |  | Timesheet | 93.7 | Yes | 6371.6 | 2026-03 | Data & AI | 10307
ACT-00655 | 2026-03-31 | P-1020 | Labour | E-0043 |  | Timesheet | 45.5 | Yes | 3694.6 | 2026-03 | Data & AI | 6142.5
ACT-00656 | 2026-03-31 | P-1020 | Labour | E-0051 |  | Timesheet | 184.5 | Yes | 17933.4 | 2026-03 | Data & AI | 35977.5
ACT-00657 | 2026-03-31 | P-1020 | Labour | E-0053 |  | Timesheet | 131.2 | Yes | 12857.6 | 2026-03 | Data & AI | 26240
ACT-00658 | 2026-03-31 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2381.49 | 2026-03 | Data & AI | 0
ACT-00659 | 2026-03-31 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 639.97 | 2026-03 | Data & AI | 0
ACT-00660 | 2026-03-31 | P-1021 | Labour | E-0010 |  | Timesheet | 47 | Yes | 4136 | 2026-03 | Operational Excellence | 8225
ACT-00661 | 2026-03-31 | P-1021 | Labour | E-0016 |  | Timesheet | 92.5 | Yes | 6793.2 | 2026-03 | Operational Excellence | 13875
ACT-00662 | 2026-03-31 | P-1021 | Labour | E-0026 |  | Timesheet | 142.7 | Yes | 12209.41 | 2026-03 | Operational Excellence | 24259
ACT-00663 | 2026-03-31 | P-1021 | Labour | E-0033 |  | Timesheet | 89.3 | Yes | 5315.14 | 2026-03 | Operational Excellence | 10716
ACT-00664 | 2026-03-31 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1390.9 | 2026-03 | Operational Excellence | 0
ACT-00665 | 2026-03-31 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 869.78 | 2026-03 | Operational Excellence | 0
ACT-00666 | 2026-03-31 | P-1021 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 555.8 | 2026-03 | Operational Excellence | 0
ACT-00667 | 2026-04-30 | P-1001 | Labour | E-0003 |  | Timesheet | 88.6 | Yes | 9044.29 | 2026-04 | Customer Experience | 18163
ACT-00668 | 2026-04-30 | P-1001 | Labour | E-0015 |  | Timesheet | 92.2 | Yes | 7272.74 | 2026-04 | Customer Experience | 14752
ACT-00669 | 2026-04-30 | P-1001 | Labour | E-0020 |  | Timesheet | 143 | Yes | 12275.12 | 2026-04 | Customer Experience | 25025
ACT-00670 | 2026-04-30 | P-1001 | Labour | E-0023 |  | Timesheet | 118.8 | Yes | 12678.34 | 2026-04 | Customer Experience | 25542
ACT-00671 | 2026-04-30 | P-1001 | Labour | E-0031 |  | Timesheet | 170.2 | Yes | 12635.65 | 2026-04 | Customer Experience | 25530
ACT-00672 | 2026-04-30 | P-1001 | Labour | E-0042 |  | Timesheet | 56.6 | Yes | 3676.74 | 2026-04 | Customer Experience | 7641
ACT-00673 | 2026-04-30 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2871.47 | 2026-04 | Customer Experience | 0
ACT-00674 | 2026-04-30 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3902.65 | 2026-04 | Customer Experience | 0
ACT-00675 | 2026-04-30 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 968.21 | 2026-04 | Customer Experience | 0
ACT-00676 | 2026-04-30 | P-1002 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 21485.99 | 2026-04 | Operational Excellence | 0
ACT-00677 | 2026-04-30 | P-1002 | Labour | E-0004 |  | Timesheet | 56.7 | Yes | 5787.94 | 2026-04 | Operational Excellence | 11623.5
ACT-00678 | 2026-04-30 | P-1002 | Labour | E-0016 |  | Timesheet | 132.7 | Yes | 9745.49 | 2026-04 | Operational Excellence | 19905
ACT-00679 | 2026-04-30 | P-1002 | Labour | E-0024 |  | Timesheet | 120.6 | Yes | 11982.82 | 2026-04 | Operational Excellence | 24120
ACT-00680 | 2026-04-30 | P-1002 | Labour | E-0032 |  | Timesheet | 191.5 | Yes | 11398.08 | 2026-04 | Operational Excellence | 22980
ACT-00681 | 2026-04-30 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1601.39 | 2026-04 | Operational Excellence | 0
ACT-00682 | 2026-04-30 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 930.77 | 2026-04 | Operational Excellence | 0
ACT-00683 | 2026-04-30 | P-1002 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 608.74 | 2026-04 | Operational Excellence | 0
ACT-00684 | 2026-04-30 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3755.12 | 2026-04 | Data & AI | 0
ACT-00685 | 2026-04-30 | P-1003 | Labour | E-0005 |  | Timesheet | 47.8 | No | 3575.44 | 2026-04 | Data & AI | 0
ACT-00686 | 2026-04-30 | P-1003 | Labour | E-0013 |  | Timesheet | 47.4 | Yes | 5733.5 | 2026-04 | Data & AI | 11613
ACT-00687 | 2026-04-30 | P-1003 | Labour | E-0033 |  | Timesheet | 102.8 | Yes | 6118.66 | 2026-04 | Data & AI | 12336
ACT-00688 | 2026-04-30 | P-1003 | Labour | E-0044 |  | Timesheet | 100.7 | Yes | 7049 | 2026-04 | Data & AI | 11580.5
ACT-00689 | 2026-04-30 | P-1003 | Labour | E-0048 |  | Timesheet | 204.8 | Yes | 21381.12 | 2026-04 | Data & AI | 43008
ACT-00690 | 2026-04-30 | P-1003 | Labour | E-0052 |  | Timesheet | 91.5 | Yes | 10401.72 | 2026-04 | Data & AI | 21045
ACT-00691 | 2026-04-30 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3031.6 | 2026-04 | Data & AI | 0
ACT-00692 | 2026-04-30 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 488.08 | 2026-04 | Data & AI | 0
ACT-00693 | 2026-04-30 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6192.63 | 2026-04 | Cloud & Infrastructure | 0
ACT-00694 | 2026-04-30 | P-1004 | Labour | E-0006 |  | Timesheet | 45 | Yes | 3960 | 2026-04 | Cloud & Infrastructure | 7875
ACT-00695 | 2026-04-30 | P-1004 | Labour | E-0011 |  | Timesheet | 41 | Yes | 5326.72 | 2026-04 | Cloud & Infrastructure | 10660
ACT-00696 | 2026-04-30 | P-1004 | Labour | E-0025 |  | Timesheet | 93.8 | Yes | 10031.91 | 2026-04 | Cloud & Infrastructure | 15946
ACT-00697 | 2026-04-30 | P-1004 | Labour | E-0055 |  | Timesheet | 167.9 | Yes | 18307.82 | 2026-04 | Cloud & Infrastructure | 36938
ACT-00698 | 2026-04-30 | P-1004 | Labour | E-0059 |  | Timesheet | 91 | Yes | 9078.16 | 2026-04 | Cloud & Infrastructure | 18655
ACT-00699 | 2026-04-30 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2304.58 | 2026-04 | Cloud & Infrastructure | 0
ACT-00700 | 2026-04-30 | P-1004 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 994.95 | 2026-04 | Cloud & Infrastructure | 0
ACT-00701 | 2026-04-30 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 2790.71 | 2026-04 | Data & AI | 0
ACT-00702 | 2026-04-30 | P-1005 | Labour | E-0007 |  | Timesheet | 61.4 | Yes | 6267.71 | 2026-04 | Data & AI | 12587
ACT-00703 | 2026-04-30 | P-1005 | Labour | E-0012 |  | Timesheet | 59.4 | Yes | 7717.25 | 2026-04 | Data & AI | 15444
ACT-00704 | 2026-04-30 | P-1005 | Labour | E-0034 |  | Timesheet | 105 | Yes | 5712 | 2026-04 | Data & AI | 11550
ACT-00705 | 2026-04-30 | P-1005 | Labour | E-0049 |  | Timesheet | 168 | Yes | 12852 | 2026-04 | Data & AI | 26040
ACT-00706 | 2026-04-30 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2040.48 | 2026-04 | Data & AI | 0
ACT-00707 | 2026-04-30 | P-1005 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 513.82 | 2026-04 | Data & AI | 0
ACT-00708 | 2026-04-30 | P-1006 | Labour | E-0009 |  | Timesheet | 111.6 | Yes | 8347.68 | 2026-04 | Customer Experience | 16740
ACT-00709 | 2026-04-30 | P-1006 | Labour | E-0019 |  | Timesheet | 67.6 | Yes | 4884.1 | 2026-04 | Customer Experience | 8112
ACT-00710 | 2026-04-30 | P-1006 | Labour | E-0021 |  | Timesheet | 98.7 | Yes | 6792.53 | 2026-04 | Customer Experience | 13818
ACT-00711 | 2026-04-30 | P-1006 | Labour | E-0026 |  | Timesheet | 160.1 | Yes | 13698.16 | 2026-04 | Customer Experience | 27217
ACT-00712 | 2026-04-30 | P-1006 | Labour | E-0035 |  | Timesheet | 209.1 | Yes | 12445.63 | 2026-04 | Customer Experience | 25092
ACT-00713 | 2026-04-30 | P-1006 | Labour | E-0045 |  | Timesheet | 115.4 | Yes | 6010.03 | 2026-04 | Customer Experience | 12117
ACT-00714 | 2026-04-30 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2816.83 | 2026-04 | Customer Experience | 0
ACT-00715 | 2026-04-30 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4709.2 | 2026-04 | Customer Experience | 0
ACT-00716 | 2026-04-30 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 792.31 | 2026-04 | Customer Experience | 0
ACT-00717 | 2026-04-30 | P-1007 | Labour | E-0008 |  | Timesheet | 70.7 | Yes | 6719.33 | 2026-04 | Digital Transformation | 13433
ACT-00718 | 2026-04-30 | P-1007 | Labour | E-0014 |  | Timesheet | 77.7 | Yes | 8093.23 | 2026-04 | Digital Transformation | 16317
ACT-00719 | 2026-04-30 | P-1007 | Labour | E-0017 |  | Timesheet | 76.8 | Yes | 4856.83 | 2026-04 | Digital Transformation | 9984
ACT-00720 | 2026-04-30 | P-1007 | Labour | E-0027 |  | Timesheet | 118.1 | Yes | 11734.42 | 2026-04 | Digital Transformation | 23620
ACT-00721 | 2026-04-30 | P-1007 | Labour | E-0036 |  | Timesheet | 68.7 | Yes | 4089.02 | 2026-04 | Digital Transformation | 8244
ACT-00722 | 2026-04-30 | P-1007 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3764.62 | 2026-04 | Digital Transformation | 0
ACT-00723 | 2026-04-30 | P-1007 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4240.71 | 2026-04 | Digital Transformation | 0
ACT-00724 | 2026-04-30 | P-1007 | Training |  | Internal L&D | AP Invoice | 0 | No | 1386.44 | 2026-04 | Digital Transformation | 0
ACT-00725 | 2026-04-30 | P-1007 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 702.82 | 2026-04 | Digital Transformation | 0
ACT-00726 | 2026-04-30 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 4543.79 | 2026-04 | Cloud & Infrastructure | 0
ACT-00727 | 2026-04-30 | P-1008 | Labour | E-0010 |  | Timesheet | 48.9 | No | 4303.2 | 2026-04 | Cloud & Infrastructure | 0
ACT-00728 | 2026-04-30 | P-1008 | Labour | E-0012 |  | Timesheet | 53.9 | Yes | 7002.69 | 2026-04 | Cloud & Infrastructure | 14014
ACT-00729 | 2026-04-30 | P-1008 | Labour | E-0029 |  | Timesheet | 100 | Yes | 9936 | 2026-04 | Cloud & Infrastructure | 20000
ACT-00730 | 2026-04-30 | P-1008 | Labour | E-0056 |  | Timesheet | 155.5 | Yes | 18271.25 | 2026-04 | Cloud & Infrastructure | 29545
ACT-00731 | 2026-04-30 | P-1008 | Labour | E-0060 |  | Timesheet | 99.2 | Yes | 7934.02 | 2026-04 | Cloud & Infrastructure | 16368
ACT-00732 | 2026-04-30 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 1901.6 | 2026-04 | Cloud & Infrastructure | 0
ACT-00733 | 2026-04-30 | P-1008 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 897.38 | 2026-04 | Cloud & Infrastructure | 0
ACT-00734 | 2026-04-30 | P-1010 | Labour | E-0007 |  | Timesheet | 103.3 | Yes | 10544.86 | 2026-04 | Customer Experience | 21176.5
ACT-00735 | 2026-04-30 | P-1010 | Labour | E-0018 |  | Timesheet | 98.5 | Yes | 7233.84 | 2026-04 | Customer Experience | 14775
ACT-00736 | 2026-04-30 | P-1010 | Labour | E-0022 |  | Timesheet | 104.2 | Yes | 6554.18 | 2026-04 | Customer Experience | 13546
ACT-00737 | 2026-04-30 | P-1010 | Labour | E-0030 |  | Timesheet | 212.3 | Yes | 18164.39 | 2026-04 | Customer Experience | 36091
ACT-00738 | 2026-04-30 | P-1010 | Labour | E-0038 |  | Timesheet | 120.5 | Yes | 8945.92 | 2026-04 | Customer Experience | 18075
ACT-00739 | 2026-04-30 | P-1010 | Labour | E-0046 |  | Timesheet | 114.1 | Yes | 6389.6 | 2026-04 | Customer Experience | 13121.5
ACT-00740 | 2026-04-30 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3112.23 | 2026-04 | Customer Experience | 0
ACT-00741 | 2026-04-30 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4437.75 | 2026-04 | Customer Experience | 0
ACT-00742 | 2026-04-30 | P-1010 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 843.56 | 2026-04 | Customer Experience | 0
ACT-00743 | 2026-04-30 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 3167.39 | 2026-04 | Data & AI | 0
ACT-00744 | 2026-04-30 | P-1011 | Labour | E-0006 |  | Timesheet | 48 | No | 4224 | 2026-04 | Data & AI | 0
ACT-00745 | 2026-04-30 | P-1011 | Labour | E-0013 |  | Timesheet | 45.1 | Yes | 5455.3 | 2026-04 | Data & AI | 11049.5
ACT-00746 | 2026-04-30 | P-1011 | Labour | E-0039 |  | Timesheet | 83.4 | Yes | 4536.96 | 2026-04 | Data & AI | 9174
ACT-00747 | 2026-04-30 | P-1011 | Labour | E-0050 |  | Timesheet | 108.7 | Yes | 11348.28 | 2026-04 | Data & AI | 22827
ACT-00748 | 2026-04-30 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2210.17 | 2026-04 | Data & AI | 0
ACT-00749 | 2026-04-30 | P-1011 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 465.66 | 2026-04 | Data & AI | 0
ACT-00750 | 2026-04-30 | P-1013 | Labour | E-0004 |  | Timesheet | 116 | Yes | 11841.28 | 2026-04 | Digital Transformation | 23780
ACT-00751 | 2026-04-30 | P-1013 | Labour | E-0014 |  | Timesheet | 37.6 | Yes | 3916.42 | 2026-04 | Digital Transformation | 7896
ACT-00752 | 2026-04-30 | P-1013 | Labour | E-0019 |  | Timesheet | 165.3 | Yes | 11942.93 | 2026-04 | Digital Transformation | 19836
ACT-00753 | 2026-04-30 | P-1013 | Labour | E-0028 |  | Timesheet | 179.8 | Yes | 15383.69 | 2026-04 | Digital Transformation | 30566
ACT-00754 | 2026-04-30 | P-1013 | Labour | E-0041 |  | Timesheet | 120.6 | Yes | 7718.4 | 2026-04 | Digital Transformation | 15678
ACT-00755 | 2026-04-30 | P-1013 | Labour | E-0047 |  | Timesheet | 116.7 | Yes | 7580.83 | 2026-04 | Digital Transformation | 15754.5
ACT-00756 | 2026-04-30 | P-1013 | Labour | E-0063 |  | Timesheet | 45.5 | Yes | 3538.08 | 2026-04 | Digital Transformation | 7280
ACT-00757 | 2026-04-30 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 4528.33 | 2026-04 | Digital Transformation | 0
ACT-00758 | 2026-04-30 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5669.33 | 2026-04 | Digital Transformation | 0
ACT-00759 | 2026-04-30 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1602.03 | 2026-04 | Digital Transformation | 0
ACT-00760 | 2026-04-30 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1090.7 | 2026-04 | Digital Transformation | 0
ACT-00761 | 2026-04-30 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5053.37 | 2026-04 | Cloud & Infrastructure | 0
ACT-00762 | 2026-04-30 | P-1014 | Hardware |  | Dell Technologies | AP Invoice | 0 | No | 30317.4 | 2026-04 | Cloud & Infrastructure | 0
ACT-00763 | 2026-04-30 | P-1014 | Labour | E-0008 |  | Timesheet | 43.9 | Yes | 4172.26 | 2026-04 | Cloud & Infrastructure | 8341
ACT-00764 | 2026-04-30 | P-1014 | Labour | E-0011 |  | Timesheet | 39 | Yes | 5066.88 | 2026-04 | Cloud & Infrastructure | 10140
ACT-00765 | 2026-04-30 | P-1014 | Labour | E-0029 |  | Timesheet | 93.8 | Yes | 9319.97 | 2026-04 | Cloud & Infrastructure | 18760
ACT-00766 | 2026-04-30 | P-1014 | Labour | E-0057 |  | Timesheet | 141.6 | Yes | 15440.06 | 2026-04 | Cloud & Infrastructure | 31152
ACT-00767 | 2026-04-30 | P-1014 | Labour | E-0061 |  | Timesheet | 91.5 | Yes | 7869 | 2026-04 | Cloud & Infrastructure | 16012.5
ACT-00768 | 2026-04-30 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1850.85 | 2026-04 | Cloud & Infrastructure | 0
ACT-00769 | 2026-04-30 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 778.82 | 2026-04 | Cloud & Infrastructure | 0
ACT-00770 | 2026-04-30 | P-1015 | Labour | E-0009 |  | Timesheet | 100.8 | Yes | 7539.84 | 2026-04 | Digital Transformation | 15120
ACT-00771 | 2026-04-30 | P-1015 | Labour | E-0013 |  | Timesheet | 53.1 | Yes | 6422.98 | 2026-04 | Digital Transformation | 13009.5
ACT-00772 | 2026-04-30 | P-1015 | Labour | E-0015 |  | Timesheet | 101.9 | Yes | 8037.87 | 2026-04 | Digital Transformation | 16304
ACT-00773 | 2026-04-30 | P-1015 | Labour | E-0024 |  | Timesheet | 169.6 | Yes | 16851.46 | 2026-04 | Digital Transformation | 33920
ACT-00774 | 2026-04-30 | P-1015 | Labour | E-0040 |  | Timesheet | 155 | Yes | 9920 | 2026-04 | Digital Transformation | 20150
ACT-00775 | 2026-04-30 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 4421.12 | 2026-04 | Digital Transformation | 0
ACT-00776 | 2026-04-30 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4837.91 | 2026-04 | Digital Transformation | 0
ACT-00777 | 2026-04-30 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1444.81 | 2026-04 | Digital Transformation | 0
ACT-00778 | 2026-04-30 | P-1015 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 979.22 | 2026-04 | Digital Transformation | 0
ACT-00779 | 2026-04-30 | P-1016 | Labour | E-0003 |  | Timesheet | 30.6 | No | 3123.65 | 2026-04 | Operational Excellence | 0
ACT-00780 | 2026-04-30 | P-1016 | Labour | E-0018 |  | Timesheet | 56.4 | Yes | 4142.02 | 2026-04 | Operational Excellence | 8460
ACT-00781 | 2026-04-30 | P-1016 | Labour | E-0025 |  | Timesheet | 57.8 | Yes | 6181.71 | 2026-04 | Operational Excellence | 9826
ACT-00782 | 2026-04-30 | P-1016 | Labour | E-0038 |  | Timesheet | 51.2 | Yes | 3801.09 | 2026-04 | Operational Excellence | 7680
ACT-00783 | 2026-04-30 | P-1016 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1339.66 | 2026-04 | Operational Excellence | 0
ACT-00784 | 2026-04-30 | P-1016 | Training |  | Learning Tree | AP Invoice | 0 | No | 668.07 | 2026-04 | Operational Excellence | 0
ACT-00785 | 2026-04-30 | P-1016 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 595.4 | 2026-04 | Operational Excellence | 0
ACT-00786 | 2026-04-30 | P-1017 | Labour | E-0005 |  | Timesheet | 120.8 | Yes | 9035.84 | 2026-04 | Customer Experience | 18120
ACT-00787 | 2026-04-30 | P-1017 | Labour | E-0017 |  | Timesheet | 114.8 | Yes | 7259.95 | 2026-04 | Customer Experience | 14924
ACT-00788 | 2026-04-30 | P-1017 | Labour | E-0022 |  | Timesheet | 137.6 | Yes | 8655.04 | 2026-04 | Customer Experience | 17888
ACT-00789 | 2026-04-30 | P-1017 | Labour | E-0027 |  | Timesheet | 137.3 | Yes | 13642.13 | 2026-04 | Customer Experience | 27460
ACT-00790 | 2026-04-30 | P-1017 | Labour | E-0036 |  | Timesheet | 136.4 | Yes | 8118.53 | 2026-04 | Customer Experience | 16368
ACT-00791 | 2026-04-30 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2174.73 | 2026-04 | Customer Experience | 0
ACT-00792 | 2026-04-30 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 2947.12 | 2026-04 | Customer Experience | 0
ACT-00793 | 2026-04-30 | P-1017 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 551.25 | 2026-04 | Customer Experience | 0
ACT-00794 | 2026-04-30 | P-1019 | Labour | E-0010 |  | Timesheet | 36.8 | Yes | 3238.4 | 2026-04 | Digital Transformation | 6440
ACT-00795 | 2026-04-30 | P-1019 | Labour | E-0017 |  | Timesheet | 54 | Yes | 3414.96 | 2026-04 | Digital Transformation | 7020
ACT-00796 | 2026-04-30 | P-1019 | Labour | E-0025 |  | Timesheet | 47.8 | Yes | 5112.21 | 2026-04 | Digital Transformation | 8126
ACT-00797 | 2026-04-30 | P-1019 | Labour | E-0034 |  | Timesheet | 55.1 | Yes | 2997.44 | 2026-04 | Digital Transformation | 6061
ACT-00798 | 2026-04-30 | P-1019 | Labour | E-0042 |  | Timesheet | 32.2 | Yes | 2091.71 | 2026-04 | Digital Transformation | 4347
ACT-00799 | 2026-04-30 | P-1019 | Labour | E-0062 |  | Timesheet | 17 | Yes | 1419.84 | 2026-04 | Digital Transformation | 2975
ACT-00800 | 2026-04-30 | P-1019 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3243.73 | 2026-04 | Digital Transformation | 0
ACT-00801 | 2026-04-30 | P-1019 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 6551.51 | 2026-04 | Digital Transformation | 0
ACT-00802 | 2026-04-30 | P-1019 | Training |  | Learning Tree | AP Invoice | 0 | No | 1529.96 | 2026-04 | Digital Transformation | 0
ACT-00803 | 2026-04-30 | P-1019 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 966.37 | 2026-04 | Digital Transformation | 0
ACT-00804 | 2026-04-30 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 3450.86 | 2026-04 | Data & AI | 0
ACT-00805 | 2026-04-30 | P-1020 | Labour | E-0006 |  | Timesheet | 86.9 | No | 7647.2 | 2026-04 | Data & AI | 0
ACT-00806 | 2026-04-30 | P-1020 | Labour | E-0037 |  | Timesheet | 86.5 | Yes | 5882 | 2026-04 | Data & AI | 9515
ACT-00807 | 2026-04-30 | P-1020 | Labour | E-0043 |  | Timesheet | 43.7 | Yes | 3548.44 | 2026-04 | Data & AI | 5899.5
ACT-00808 | 2026-04-30 | P-1020 | Labour | E-0051 |  | Timesheet | 155.8 | Yes | 15143.76 | 2026-04 | Data & AI | 30381
ACT-00809 | 2026-04-30 | P-1020 | Labour | E-0053 |  | Timesheet | 107.7 | Yes | 10554.6 | 2026-04 | Data & AI | 21540
ACT-00810 | 2026-04-30 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2695.5 | 2026-04 | Data & AI | 0
ACT-00811 | 2026-04-30 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 579.72 | 2026-04 | Data & AI | 0
ACT-00812 | 2026-04-30 | P-1021 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 18097.28 | 2026-04 | Operational Excellence | 0
ACT-00813 | 2026-04-30 | P-1021 | Labour | E-0010 |  | Timesheet | 48.7 | Yes | 4285.6 | 2026-04 | Operational Excellence | 8522.5
ACT-00814 | 2026-04-30 | P-1021 | Labour | E-0016 |  | Timesheet | 86.4 | Yes | 6345.22 | 2026-04 | Operational Excellence | 12960
ACT-00815 | 2026-04-30 | P-1021 | Labour | E-0026 |  | Timesheet | 150.5 | Yes | 12876.78 | 2026-04 | Operational Excellence | 25585
ACT-00816 | 2026-04-30 | P-1021 | Labour | E-0033 |  | Timesheet | 94 | Yes | 5594.88 | 2026-04 | Operational Excellence | 11280
ACT-00817 | 2026-04-30 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1320.69 | 2026-04 | Operational Excellence | 0
ACT-00818 | 2026-04-30 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 738.27 | 2026-04 | Operational Excellence | 0
ACT-00819 | 2026-04-30 | P-1021 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 688.27 | 2026-04 | Operational Excellence | 0
ACT-00820 | 2026-05-31 | P-1001 | Labour | E-0003 |  | Timesheet | 78 | Yes | 7962.24 | 2026-05 | Customer Experience | 15990
ACT-00821 | 2026-05-31 | P-1001 | Labour | E-0015 |  | Timesheet | 52.7 | Yes | 4156.98 | 2026-05 | Customer Experience | 8432
ACT-00822 | 2026-05-31 | P-1001 | Labour | E-0020 |  | Timesheet | 80.2 | Yes | 6884.37 | 2026-05 | Customer Experience | 14035
ACT-00823 | 2026-05-31 | P-1001 | Labour | E-0023 |  | Timesheet | 121.5 | Yes | 12966.48 | 2026-05 | Customer Experience | 26122.5
ACT-00824 | 2026-05-31 | P-1001 | Labour | E-0031 |  | Timesheet | 174.6 | Yes | 12962.3 | 2026-05 | Customer Experience | 26190
ACT-00825 | 2026-05-31 | P-1001 | Labour | E-0042 |  | Timesheet | 90.9 | Yes | 5904.86 | 2026-05 | Customer Experience | 12271.5
ACT-00826 | 2026-05-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3012.36 | 2026-05 | Customer Experience | 0
ACT-00827 | 2026-05-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4070.36 | 2026-05 | Customer Experience | 0
ACT-00828 | 2026-05-31 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1083.87 | 2026-05 | Customer Experience | 0
ACT-00829 | 2026-05-31 | P-1002 | Labour | E-0004 |  | Timesheet | 57.4 | Yes | 5859.39 | 2026-05 | Operational Excellence | 11767
ACT-00830 | 2026-05-31 | P-1002 | Labour | E-0016 |  | Timesheet | 117.5 | Yes | 8629.2 | 2026-05 | Operational Excellence | 17625
ACT-00831 | 2026-05-31 | P-1002 | Labour | E-0024 |  | Timesheet | 119 | Yes | 11823.84 | 2026-05 | Operational Excellence | 23800
ACT-00832 | 2026-05-31 | P-1002 | Labour | E-0032 |  | Timesheet | 165.3 | Yes | 9838.66 | 2026-05 | Operational Excellence | 19836
ACT-00833 | 2026-05-31 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1721.8 | 2026-05 | Operational Excellence | 0
ACT-00834 | 2026-05-31 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 981.29 | 2026-05 | Operational Excellence | 0
ACT-00835 | 2026-05-31 | P-1002 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 669.35 | 2026-05 | Operational Excellence | 0
ACT-00836 | 2026-05-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4292.58 | 2026-05 | Data & AI | 0
ACT-00837 | 2026-05-31 | P-1003 | Labour | E-0005 |  | Timesheet | 42.1 | No | 3149.08 | 2026-05 | Data & AI | 0
ACT-00838 | 2026-05-31 | P-1003 | Labour | E-0013 |  | Timesheet | 12.2 | Yes | 1475.71 | 2026-05 | Data & AI | 2989
ACT-00839 | 2026-05-31 | P-1003 | Labour | E-0033 |  | Timesheet | 90.7 | Yes | 5398.46 | 2026-05 | Data & AI | 10884
ACT-00840 | 2026-05-31 | P-1003 | Labour | E-0044 |  | Timesheet | 95.9 | Yes | 6713 | 2026-05 | Data & AI | 11028.5
ACT-00841 | 2026-05-31 | P-1003 | Labour | E-0048 |  | Timesheet | 195.7 | Yes | 20431.08 | 2026-05 | Data & AI | 41097
ACT-00842 | 2026-05-31 | P-1003 | Labour | E-0052 |  | Timesheet | 95.3 | Yes | 10833.7 | 2026-05 | Data & AI | 21919
ACT-00843 | 2026-05-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2400.03 | 2026-05 | Data & AI | 0
ACT-00844 | 2026-05-31 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 569.99 | 2026-05 | Data & AI | 0
ACT-00845 | 2026-05-31 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6512.9 | 2026-05 | Cloud & Infrastructure | 0
ACT-00846 | 2026-05-31 | P-1004 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 32528.39 | 2026-05 | Cloud & Infrastructure | 0
ACT-00847 | 2026-05-31 | P-1004 | Labour | E-0006 |  | Timesheet | 42.4 | Yes | 3731.2 | 2026-05 | Cloud & Infrastructure | 7420
ACT-00848 | 2026-05-31 | P-1004 | Labour | E-0011 |  | Timesheet | 40.1 | Yes | 5209.79 | 2026-05 | Cloud & Infrastructure | 10426
ACT-00849 | 2026-05-31 | P-1004 | Labour | E-0025 |  | Timesheet | 79.8 | Yes | 8534.61 | 2026-05 | Cloud & Infrastructure | 13566
ACT-00850 | 2026-05-31 | P-1004 | Labour | E-0055 |  | Timesheet | 179.4 | Yes | 19561.78 | 2026-05 | Cloud & Infrastructure | 39468
ACT-00851 | 2026-05-31 | P-1004 | Labour | E-0059 |  | Timesheet | 89.4 | Yes | 8918.54 | 2026-05 | Cloud & Infrastructure | 18327
ACT-00852 | 2026-05-31 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2547.56 | 2026-05 | Cloud & Infrastructure | 0
ACT-00853 | 2026-05-31 | P-1004 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 804.24 | 2026-05 | Cloud & Infrastructure | 0
ACT-00854 | 2026-05-31 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 2812.33 | 2026-05 | Data & AI | 0
ACT-00855 | 2026-05-31 | P-1005 | Labour | E-0007 |  | Timesheet | 54.8 | Yes | 5593.98 | 2026-05 | Data & AI | 11234
ACT-00856 | 2026-05-31 | P-1005 | Labour | E-0012 |  | Timesheet | 60.9 | Yes | 7912.13 | 2026-05 | Data & AI | 15834
ACT-00857 | 2026-05-31 | P-1005 | Labour | E-0034 |  | Timesheet | 102.3 | Yes | 5565.12 | 2026-05 | Data & AI | 11253
ACT-00858 | 2026-05-31 | P-1005 | Labour | E-0049 |  | Timesheet | 194.8 | Yes | 14902.2 | 2026-05 | Data & AI | 30194
ACT-00859 | 2026-05-31 | P-1005 | Labour | E-0052 |  | Timesheet | 67.3 | Yes | 7650.66 | 2026-05 | Data & AI | 15479
ACT-00860 | 2026-05-31 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1912.15 | 2026-05 | Data & AI | 0
ACT-00861 | 2026-05-31 | P-1005 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 509.26 | 2026-05 | Data & AI | 0
ACT-00862 | 2026-05-31 | P-1006 | Labour | E-0009 |  | Timesheet | 107.6 | Yes | 8048.48 | 2026-05 | Customer Experience | 16140
ACT-00863 | 2026-05-31 | P-1006 | Labour | E-0026 |  | Timesheet | 161 | Yes | 13775.16 | 2026-05 | Customer Experience | 27370
ACT-00864 | 2026-05-31 | P-1006 | Labour | E-0035 |  | Timesheet | 220.4 | Yes | 13118.21 | 2026-05 | Customer Experience | 26448
ACT-00865 | 2026-05-31 | P-1006 | Labour | E-0045 |  | Timesheet | 110.6 | Yes | 5760.05 | 2026-05 | Customer Experience | 11613
ACT-00866 | 2026-05-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2309.86 | 2026-05 | Customer Experience | 0
ACT-00867 | 2026-05-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3935.2 | 2026-05 | Customer Experience | 0
ACT-00868 | 2026-05-31 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 722.09 | 2026-05 | Customer Experience | 0
ACT-00869 | 2026-05-31 | P-1007 | Labour | E-0008 |  | Timesheet | 81.1 | Yes | 7707.74 | 2026-05 | Digital Transformation | 15409
ACT-00870 | 2026-05-31 | P-1007 | Labour | E-0014 |  | Timesheet | 88.4 | Yes | 9207.74 | 2026-05 | Digital Transformation | 18564
ACT-00871 | 2026-05-31 | P-1007 | Labour | E-0017 |  | Timesheet | 87.5 | Yes | 5533.5 | 2026-05 | Digital Transformation | 11375
ACT-00872 | 2026-05-31 | P-1007 | Labour | E-0027 |  | Timesheet | 130.1 | Yes | 12926.74 | 2026-05 | Digital Transformation | 26020
ACT-00873 | 2026-05-31 | P-1007 | Labour | E-0036 |  | Timesheet | 76.3 | Yes | 4541.38 | 2026-05 | Digital Transformation | 9156
ACT-00874 | 2026-05-31 | P-1007 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3499.65 | 2026-05 | Digital Transformation | 0
ACT-00875 | 2026-05-31 | P-1007 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4659.88 | 2026-05 | Digital Transformation | 0
ACT-00876 | 2026-05-31 | P-1007 | Training |  | Internal L&D | AP Invoice | 0 | No | 1321.27 | 2026-05 | Digital Transformation | 0
ACT-00877 | 2026-05-31 | P-1007 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 853.98 | 2026-05 | Digital Transformation | 0
ACT-00878 | 2026-05-31 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 4892.07 | 2026-05 | Cloud & Infrastructure | 0
ACT-00879 | 2026-05-31 | P-1008 | Labour | E-0010 |  | Timesheet | 51.4 | No | 4523.2 | 2026-05 | Cloud & Infrastructure | 0
ACT-00880 | 2026-05-31 | P-1008 | Labour | E-0012 |  | Timesheet | 53 | Yes | 6885.76 | 2026-05 | Cloud & Infrastructure | 13780
ACT-00881 | 2026-05-31 | P-1008 | Labour | E-0029 |  | Timesheet | 92.7 | Yes | 9210.67 | 2026-05 | Cloud & Infrastructure | 18540
ACT-00882 | 2026-05-31 | P-1008 | Labour | E-0056 |  | Timesheet | 155.5 | Yes | 18271.25 | 2026-05 | Cloud & Infrastructure | 29545
ACT-00883 | 2026-05-31 | P-1008 | Labour | E-0060 |  | Timesheet | 97.1 | Yes | 7766.06 | 2026-05 | Cloud & Infrastructure | 16021.5
ACT-00884 | 2026-05-31 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2223.17 | 2026-05 | Cloud & Infrastructure | 0
ACT-00885 | 2026-05-31 | P-1008 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 912.66 | 2026-05 | Cloud & Infrastructure | 0
ACT-00886 | 2026-05-31 | P-1009 | Labour | E-0005 |  | Timesheet | 75.2 | Yes | 5624.96 | 2026-05 | Operational Excellence | 11280
ACT-00887 | 2026-05-31 | P-1009 | Labour | E-0018 |  | Timesheet | 82.6 | Yes | 6066.14 | 2026-05 | Operational Excellence | 12390
ACT-00888 | 2026-05-31 | P-1009 | Labour | E-0028 |  | Timesheet | 127.4 | Yes | 10900.34 | 2026-05 | Operational Excellence | 21658
ACT-00889 | 2026-05-31 | P-1009 | Labour | E-0037 |  | Timesheet | 119.3 | Yes | 8112.4 | 2026-05 | Operational Excellence | 13123
ACT-00890 | 2026-05-31 | P-1009 | Software & Licences |  | Atlassian Cloud | AP Invoice | 0 | No | 1334.56 | 2026-05 | Operational Excellence | 0
ACT-00891 | 2026-05-31 | P-1009 | Training |  | Internal L&D | AP Invoice | 0 | No | 931.6 | 2026-05 | Operational Excellence | 0
ACT-00892 | 2026-05-31 | P-1009 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 653.79 | 2026-05 | Operational Excellence | 0
ACT-00893 | 2026-05-31 | P-1010 | Labour | E-0007 |  | Timesheet | 113.9 | Yes | 11626.91 | 2026-05 | Customer Experience | 23349.5
ACT-00894 | 2026-05-31 | P-1010 | Labour | E-0030 |  | Timesheet | 190.9 | Yes | 16333.4 | 2026-05 | Customer Experience | 32453
ACT-00895 | 2026-05-31 | P-1010 | Labour | E-0038 |  | Timesheet | 111.4 | Yes | 8270.34 | 2026-05 | Customer Experience | 16710
ACT-00896 | 2026-05-31 | P-1010 | Labour | E-0046 |  | Timesheet | 99.2 | Yes | 5555.2 | 2026-05 | Customer Experience | 11408
ACT-00897 | 2026-05-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3050.81 | 2026-05 | Customer Experience | 0
ACT-00898 | 2026-05-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3686.91 | 2026-05 | Customer Experience | 0
ACT-00899 | 2026-05-31 | P-1010 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 947.92 | 2026-05 | Customer Experience | 0
ACT-00900 | 2026-05-31 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2999.18 | 2026-05 | Data & AI | 0
ACT-00901 | 2026-05-31 | P-1011 | Labour | E-0006 |  | Timesheet | 41.2 | No | 3625.6 | 2026-05 | Data & AI | 0
ACT-00902 | 2026-05-31 | P-1011 | Labour | E-0013 |  | Timesheet | 45.6 | Yes | 5515.78 | 2026-05 | Data & AI | 11172
ACT-00903 | 2026-05-31 | P-1011 | Labour | E-0039 |  | Timesheet | 80 | Yes | 4352 | 2026-05 | Data & AI | 8800
ACT-00904 | 2026-05-31 | P-1011 | Labour | E-0050 |  | Timesheet | 108.5 | Yes | 11327.4 | 2026-05 | Data & AI | 22785
ACT-00905 | 2026-05-31 | P-1011 | Labour | E-0053 |  | Timesheet | 77.8 | Yes | 7624.4 | 2026-05 | Data & AI | 15560
ACT-00906 | 2026-05-31 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1933.27 | 2026-05 | Data & AI | 0
ACT-00907 | 2026-05-31 | P-1011 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 451.66 | 2026-05 | Data & AI | 0
ACT-00908 | 2026-05-31 | P-1013 | Labour | E-0004 |  | Timesheet | 114.4 | Yes | 11677.95 | 2026-05 | Digital Transformation | 23452
ACT-00909 | 2026-05-31 | P-1013 | Labour | E-0019 |  | Timesheet | 163.6 | Yes | 11820.1 | 2026-05 | Digital Transformation | 19632
ACT-00910 | 2026-05-31 | P-1013 | Labour | E-0028 |  | Timesheet | 166.8 | Yes | 14271.41 | 2026-05 | Digital Transformation | 28356
ACT-00911 | 2026-05-31 | P-1013 | Labour | E-0041 |  | Timesheet | 105.6 | Yes | 6758.4 | 2026-05 | Digital Transformation | 13728
ACT-00912 | 2026-05-31 | P-1013 | Labour | E-0047 |  | Timesheet | 106.7 | Yes | 6931.23 | 2026-05 | Digital Transformation | 14404.5
ACT-00913 | 2026-05-31 | P-1013 | Labour | E-0063 |  | Timesheet | 43.3 | Yes | 3367.01 | 2026-05 | Digital Transformation | 6928
ACT-00914 | 2026-05-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3902.31 | 2026-05 | Digital Transformation | 0
ACT-00915 | 2026-05-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5731.45 | 2026-05 | Digital Transformation | 0
ACT-00916 | 2026-05-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1388.4 | 2026-05 | Digital Transformation | 0
ACT-00917 | 2026-05-31 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 980.98 | 2026-05 | Digital Transformation | 0
ACT-00918 | 2026-05-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4946.91 | 2026-05 | Cloud & Infrastructure | 0
ACT-00919 | 2026-05-31 | P-1014 | Labour | E-0008 |  | Timesheet | 43.7 | Yes | 4153.25 | 2026-05 | Cloud & Infrastructure | 8303
ACT-00920 | 2026-05-31 | P-1014 | Labour | E-0029 |  | Timesheet | 76.9 | Yes | 7640.78 | 2026-05 | Cloud & Infrastructure | 15380
ACT-00921 | 2026-05-31 | P-1014 | Labour | E-0057 |  | Timesheet | 112.9 | Yes | 12310.62 | 2026-05 | Cloud & Infrastructure | 24838
ACT-00922 | 2026-05-31 | P-1014 | Labour | E-0061 |  | Timesheet | 79.3 | Yes | 6819.8 | 2026-05 | Cloud & Infrastructure | 13877.5
ACT-00923 | 2026-05-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1609.79 | 2026-05 | Cloud & Infrastructure | 0
ACT-00924 | 2026-05-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 687.93 | 2026-05 | Cloud & Infrastructure | 0
ACT-00925 | 2026-05-31 | P-1015 | Labour | E-0009 |  | Timesheet | 99.4 | Yes | 7435.12 | 2026-05 | Digital Transformation | 14910
ACT-00926 | 2026-05-31 | P-1015 | Labour | E-0013 |  | Timesheet | 53.4 | Yes | 6459.26 | 2026-05 | Digital Transformation | 13083
ACT-00927 | 2026-05-31 | P-1015 | Labour | E-0015 |  | Timesheet | 95.3 | Yes | 7517.26 | 2026-05 | Digital Transformation | 15248
ACT-00928 | 2026-05-31 | P-1015 | Labour | E-0024 |  | Timesheet | 153.2 | Yes | 15221.95 | 2026-05 | Digital Transformation | 30640
ACT-00929 | 2026-05-31 | P-1015 | Labour | E-0040 |  | Timesheet | 152 | Yes | 9728 | 2026-05 | Digital Transformation | 19760
ACT-00930 | 2026-05-31 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3806.29 | 2026-05 | Digital Transformation | 0
ACT-00931 | 2026-05-31 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5208.52 | 2026-05 | Digital Transformation | 0
ACT-00932 | 2026-05-31 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1337.06 | 2026-05 | Digital Transformation | 0
ACT-00933 | 2026-05-31 | P-1015 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1110.05 | 2026-05 | Digital Transformation | 0
ACT-00934 | 2026-05-31 | P-1016 | Labour | E-0003 |  | Timesheet | 39.9 | No | 4072.99 | 2026-05 | Operational Excellence | 0
ACT-00935 | 2026-05-31 | P-1016 | Labour | E-0018 |  | Timesheet | 88.1 | Yes | 6470.06 | 2026-05 | Operational Excellence | 13215
ACT-00936 | 2026-05-31 | P-1016 | Labour | E-0025 |  | Timesheet | 81 | Yes | 8662.95 | 2026-05 | Operational Excellence | 13770
ACT-00937 | 2026-05-31 | P-1016 | Labour | E-0038 |  | Timesheet | 89.9 | Yes | 6674.18 | 2026-05 | Operational Excellence | 13485
ACT-00938 | 2026-05-31 | P-1016 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1455.94 | 2026-05 | Operational Excellence | 0
ACT-00939 | 2026-05-31 | P-1016 | Training |  | Learning Tree | AP Invoice | 0 | No | 720.11 | 2026-05 | Operational Excellence | 0
ACT-00940 | 2026-05-31 | P-1016 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 614.26 | 2026-05 | Operational Excellence | 0
ACT-00941 | 2026-05-31 | P-1017 | Labour | E-0005 |  | Timesheet | 118.3 | Yes | 8848.84 | 2026-05 | Customer Experience | 17745
ACT-00942 | 2026-05-31 | P-1017 | Labour | E-0017 |  | Timesheet | 127.7 | Yes | 8075.75 | 2026-05 | Customer Experience | 16601
ACT-00943 | 2026-05-31 | P-1017 | Labour | E-0022 |  | Timesheet | 114.5 | Yes | 7202.05 | 2026-05 | Customer Experience | 14885
ACT-00944 | 2026-05-31 | P-1017 | Labour | E-0027 |  | Timesheet | 119.5 | Yes | 11873.52 | 2026-05 | Customer Experience | 23900
ACT-00945 | 2026-05-31 | P-1017 | Labour | E-0036 |  | Timesheet | 109.3 | Yes | 6505.54 | 2026-05 | Customer Experience | 13116
ACT-00946 | 2026-05-31 | P-1017 | Labour | E-0043 |  | Timesheet | 81.2 | Yes | 6593.44 | 2026-05 | Customer Experience | 10962
ACT-00947 | 2026-05-31 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2009.48 | 2026-05 | Customer Experience | 0
ACT-00948 | 2026-05-31 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3073.78 | 2026-05 | Customer Experience | 0
ACT-00949 | 2026-05-31 | P-1017 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 682.29 | 2026-05 | Customer Experience | 0
ACT-00950 | 2026-05-31 | P-1020 | Cloud Hosting |  | Google Cloud | AP Invoice | 0 | No | 4113.28 | 2026-05 | Data & AI | 0
ACT-00951 | 2026-05-31 | P-1020 | Labour | E-0006 |  | Timesheet | 84.4 | No | 7427.2 | 2026-05 | Data & AI | 0
ACT-00952 | 2026-05-31 | P-1020 | Labour | E-0037 |  | Timesheet | 78.6 | Yes | 5344.8 | 2026-05 | Data & AI | 8646
ACT-00953 | 2026-05-31 | P-1020 | Labour | E-0043 |  | Timesheet | 40.6 | Yes | 3296.72 | 2026-05 | Data & AI | 5481
ACT-00954 | 2026-05-31 | P-1020 | Labour | E-0051 |  | Timesheet | 171.6 | Yes | 16679.52 | 2026-05 | Data & AI | 33462
ACT-00955 | 2026-05-31 | P-1020 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2169.53 | 2026-05 | Data & AI | 0
ACT-00956 | 2026-05-31 | P-1020 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 572.21 | 2026-05 | Data & AI | 0
ACT-00957 | 2026-05-31 | P-1021 | Labour | E-0010 |  | Timesheet | 43.6 | Yes | 3836.8 | 2026-05 | Operational Excellence | 7630
ACT-00958 | 2026-05-31 | P-1021 | Labour | E-0016 |  | Timesheet | 83.9 | Yes | 6161.62 | 2026-05 | Operational Excellence | 12585
ACT-00959 | 2026-05-31 | P-1021 | Labour | E-0026 |  | Timesheet | 139.5 | Yes | 11935.62 | 2026-05 | Operational Excellence | 23715
ACT-00960 | 2026-05-31 | P-1021 | Labour | E-0033 |  | Timesheet | 82.1 | Yes | 4886.59 | 2026-05 | Operational Excellence | 9852
ACT-00961 | 2026-05-31 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1474.24 | 2026-05 | Operational Excellence | 0
ACT-00962 | 2026-05-31 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 804.1 | 2026-05 | Operational Excellence | 0
ACT-00963 | 2026-05-31 | P-1021 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 543.44 | 2026-05 | Operational Excellence | 0
ACT-00964 | 2026-06-30 | P-1001 | Labour | E-0003 |  | Timesheet | 92.5 | Yes | 9442.4 | 2026-06 | Customer Experience | 18962.5
ACT-00965 | 2026-06-30 | P-1001 | Labour | E-0023 |  | Timesheet | 118.4 | Yes | 12635.65 | 2026-06 | Customer Experience | 25456
ACT-00966 | 2026-06-30 | P-1001 | Labour | E-0031 |  | Timesheet | 184.1 | Yes | 13667.58 | 2026-06 | Customer Experience | 27615
ACT-00967 | 2026-06-30 | P-1001 | Labour | E-0042 |  | Timesheet | 87.9 | Yes | 5709.98 | 2026-06 | Customer Experience | 11866.5
ACT-00968 | 2026-06-30 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2743.46 | 2026-06 | Customer Experience | 0
ACT-00969 | 2026-06-30 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4728.26 | 2026-06 | Customer Experience | 0
ACT-00970 | 2026-06-30 | P-1001 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1013.79 | 2026-06 | Customer Experience | 0
ACT-00971 | 2026-06-30 | P-1002 | Labour | E-0004 |  | Timesheet | 68.3 | Yes | 6972.06 | 2026-06 | Operational Excellence | 14001.5
ACT-00972 | 2026-06-30 | P-1002 | Labour | E-0016 |  | Timesheet | 132.7 | Yes | 9745.49 | 2026-06 | Operational Excellence | 19905
ACT-00973 | 2026-06-30 | P-1002 | Labour | E-0024 |  | Timesheet | 132.3 | Yes | 13145.33 | 2026-06 | Operational Excellence | 26460
ACT-00974 | 2026-06-30 | P-1002 | Labour | E-0032 |  | Timesheet | 206.4 | Yes | 12284.93 | 2026-06 | Operational Excellence | 24768
ACT-00975 | 2026-06-30 | P-1002 | Labour | E-0043 |  | Timesheet | 31.1 | Yes | 2525.32 | 2026-06 | Operational Excellence | 4198.5
ACT-00976 | 2026-06-30 | P-1002 | Labour | E-0062 |  | Timesheet | 30.9 | Yes | 2580.77 | 2026-06 | Operational Excellence | 5407.5
ACT-00977 | 2026-06-30 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1975.18 | 2026-06 | Operational Excellence | 0
ACT-00978 | 2026-06-30 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 812.2 | 2026-06 | Operational Excellence | 0
ACT-00979 | 2026-06-30 | P-1002 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 701.64 | 2026-06 | Operational Excellence | 0
ACT-00980 | 2026-06-30 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4164.25 | 2026-06 | Data & AI | 0
ACT-00981 | 2026-06-30 | P-1003 | Labour | E-0005 |  | Timesheet | 45.4 | No | 3395.92 | 2026-06 | Data & AI | 0
ACT-00982 | 2026-06-30 | P-1003 | Labour | E-0033 |  | Timesheet | 94.7 | Yes | 5636.54 | 2026-06 | Data & AI | 11364
ACT-00983 | 2026-06-30 | P-1003 | Labour | E-0044 |  | Timesheet | 93.9 | Yes | 6573 | 2026-06 | Data & AI | 10798.5
ACT-00984 | 2026-06-30 | P-1003 | Labour | E-0048 |  | Timesheet | 199.8 | Yes | 20859.12 | 2026-06 | Data & AI | 41958
ACT-00985 | 2026-06-30 | P-1003 | Labour | E-0052 |  | Timesheet | 104.8 | Yes | 11913.66 | 2026-06 | Data & AI | 24104
ACT-00986 | 2026-06-30 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2456.61 | 2026-06 | Data & AI | 0
ACT-00987 | 2026-06-30 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 562.5 | 2026-06 | Data & AI | 0
ACT-00988 | 2026-06-30 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6184.9 | 2026-06 | Cloud & Infrastructure | 0
ACT-00989 | 2026-06-30 | P-1004 | Labour | E-0006 |  | Timesheet | 42.3 | Yes | 3722.4 | 2026-06 | Cloud & Infrastructure | 7402.5
ACT-00990 | 2026-06-30 | P-1004 | Labour | E-0011 |  | Timesheet | 47.5 | Yes | 6171.2 | 2026-06 | Cloud & Infrastructure | 12350
ACT-00991 | 2026-06-30 | P-1004 | Labour | E-0025 |  | Timesheet | 78.9 | Yes | 8438.36 | 2026-06 | Cloud & Infrastructure | 13413
ACT-00992 | 2026-06-30 | P-1004 | Labour | E-0055 |  | Timesheet | 157.8 | Yes | 17206.51 | 2026-06 | Cloud & Infrastructure | 34716
ACT-00993 | 2026-06-30 | P-1004 | Labour | E-0059 |  | Timesheet | 83.1 | Yes | 8290.06 | 2026-06 | Cloud & Infrastructure | 17035.5
ACT-00994 | 2026-06-30 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2582.63 | 2026-06 | Cloud & Infrastructure | 0
ACT-00995 | 2026-06-30 | P-1004 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 988.87 | 2026-06 | Cloud & Infrastructure | 0
ACT-00996 | 2026-06-30 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3232.18 | 2026-06 | Data & AI | 0
ACT-00997 | 2026-06-30 | P-1005 | Labour | E-0007 |  | Timesheet | 66.7 | Yes | 6808.74 | 2026-06 | Data & AI | 13673.5
ACT-00998 | 2026-06-30 | P-1005 | Labour | E-0012 |  | Timesheet | 64.9 | Yes | 8431.81 | 2026-06 | Data & AI | 16874
ACT-00999 | 2026-06-30 | P-1005 | Labour | E-0034 |  | Timesheet | 96.2 | Yes | 5233.28 | 2026-06 | Data & AI | 10582
ACT-01000 | 2026-06-30 | P-1005 | Labour | E-0049 |  | Timesheet | 194.5 | Yes | 14879.25 | 2026-06 | Data & AI | 30147.5
ACT-01001 | 2026-06-30 | P-1005 | Labour | E-0052 |  | Timesheet | 118.4 | Yes | 13459.71 | 2026-06 | Data & AI | 27232
ACT-01002 | 2026-06-30 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2421.11 | 2026-06 | Data & AI | 0
ACT-01003 | 2026-06-30 | P-1005 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 558.65 | 2026-06 | Data & AI | 0
ACT-01004 | 2026-06-30 | P-1006 | Labour | E-0009 |  | Timesheet | 104.4 | Yes | 7809.12 | 2026-06 | Customer Experience | 15660
ACT-01005 | 2026-06-30 | P-1006 | Labour | E-0026 |  | Timesheet | 168.2 | Yes | 14391.19 | 2026-06 | Customer Experience | 28594
ACT-01006 | 2026-06-30 | P-1006 | Labour | E-0035 |  | Timesheet | 232.3 | Yes | 13826.5 | 2026-06 | Customer Experience | 27876
ACT-01007 | 2026-06-30 | P-1006 | Labour | E-0045 |  | Timesheet | 112.7 | Yes | 5869.42 | 2026-06 | Customer Experience | 11833.5
ACT-01008 | 2026-06-30 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2231.79 | 2026-06 | Customer Experience | 0
ACT-01009 | 2026-06-30 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4204.48 | 2026-06 | Customer Experience | 0
ACT-01010 | 2026-06-30 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 842.89 | 2026-06 | Customer Experience | 0
ACT-01011 | 2026-06-30 | P-1007 | Labour | E-0008 |  | Timesheet | 79.4 | Yes | 7546.18 | 2026-06 | Digital Transformation | 15086
ACT-01012 | 2026-06-30 | P-1007 | Labour | E-0014 |  | Timesheet | 89.2 | Yes | 9291.07 | 2026-06 | Digital Transformation | 18732
ACT-01013 | 2026-06-30 | P-1007 | Labour | E-0017 |  | Timesheet | 95.6 | Yes | 6045.74 | 2026-06 | Digital Transformation | 12428
ACT-01014 | 2026-06-30 | P-1007 | Labour | E-0027 |  | Timesheet | 125.6 | Yes | 12479.62 | 2026-06 | Digital Transformation | 25120
ACT-01015 | 2026-06-30 | P-1007 | Labour | E-0036 |  | Timesheet | 83.1 | Yes | 4946.11 | 2026-06 | Digital Transformation | 9972
ACT-01016 | 2026-06-30 | P-1007 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3674.87 | 2026-06 | Digital Transformation | 0
ACT-01017 | 2026-06-30 | P-1007 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4385.64 | 2026-06 | Digital Transformation | 0
ACT-01018 | 2026-06-30 | P-1007 | Training |  | Internal L&D | AP Invoice | 0 | No | 1388.97 | 2026-06 | Digital Transformation | 0
ACT-01019 | 2026-06-30 | P-1007 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 768.41 | 2026-06 | Digital Transformation | 0
ACT-01020 | 2026-06-30 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 4997.18 | 2026-06 | Cloud & Infrastructure | 0
ACT-01021 | 2026-06-30 | P-1008 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 13278.63 | 2026-06 | Cloud & Infrastructure | 0
ACT-01022 | 2026-06-30 | P-1008 | Labour | E-0010 |  | Timesheet | 51.4 | No | 4523.2 | 2026-06 | Cloud & Infrastructure | 0
ACT-01023 | 2026-06-30 | P-1008 | Labour | E-0012 |  | Timesheet | 20.1 | Yes | 2611.39 | 2026-06 | Cloud & Infrastructure | 5226
ACT-01024 | 2026-06-30 | P-1008 | Labour | E-0029 |  | Timesheet | 105.6 | Yes | 10492.42 | 2026-06 | Cloud & Infrastructure | 21120
ACT-01025 | 2026-06-30 | P-1008 | Labour | E-0056 |  | Timesheet | 155.1 | Yes | 18224.25 | 2026-06 | Cloud & Infrastructure | 29469
ACT-01026 | 2026-06-30 | P-1008 | Labour | E-0060 |  | Timesheet | 113.9 | Yes | 9109.72 | 2026-06 | Cloud & Infrastructure | 18793.5
ACT-01027 | 2026-06-30 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2193.66 | 2026-06 | Cloud & Infrastructure | 0
ACT-01028 | 2026-06-30 | P-1008 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 861.45 | 2026-06 | Cloud & Infrastructure | 0
ACT-01029 | 2026-06-30 | P-1009 | Labour | E-0005 |  | Timesheet | 95.8 | Yes | 7165.84 | 2026-06 | Operational Excellence | 14370
ACT-01030 | 2026-06-30 | P-1009 | Labour | E-0018 |  | Timesheet | 79.7 | Yes | 5853.17 | 2026-06 | Operational Excellence | 11955
ACT-01031 | 2026-06-30 | P-1009 | Labour | E-0028 |  | Timesheet | 120.2 | Yes | 10284.31 | 2026-06 | Operational Excellence | 20434
ACT-01032 | 2026-06-30 | P-1009 | Labour | E-0037 |  | Timesheet | 130.2 | Yes | 8853.6 | 2026-06 | Operational Excellence | 14322
ACT-01033 | 2026-06-30 | P-1009 | Software & Licences |  | Atlassian Cloud | AP Invoice | 0 | No | 1451.31 | 2026-06 | Operational Excellence | 0
ACT-01034 | 2026-06-30 | P-1009 | Training |  | Internal L&D | AP Invoice | 0 | No | 857.8 | 2026-06 | Operational Excellence | 0
ACT-01035 | 2026-06-30 | P-1009 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 687.36 | 2026-06 | Operational Excellence | 0
ACT-01036 | 2026-06-30 | P-1010 | Labour | E-0007 |  | Timesheet | 110.7 | Yes | 11300.26 | 2026-06 | Customer Experience | 22693.5
ACT-01037 | 2026-06-30 | P-1010 | Labour | E-0030 |  | Timesheet | 203.4 | Yes | 17402.9 | 2026-06 | Customer Experience | 34578
ACT-01038 | 2026-06-30 | P-1010 | Labour | E-0038 |  | Timesheet | 115 | Yes | 8537.6 | 2026-06 | Customer Experience | 17250
ACT-01039 | 2026-06-30 | P-1010 | Labour | E-0046 |  | Timesheet | 106.3 | Yes | 5952.8 | 2026-06 | Customer Experience | 12224.5
ACT-01040 | 2026-06-30 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2994.29 | 2026-06 | Customer Experience | 0
ACT-01041 | 2026-06-30 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3901 | 2026-06 | Customer Experience | 0
ACT-01042 | 2026-06-30 | P-1010 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 814.6 | 2026-06 | Customer Experience | 0
ACT-01043 | 2026-06-30 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2964.76 | 2026-06 | Data & AI | 0
ACT-01044 | 2026-06-30 | P-1011 | Labour | E-0006 |  | Timesheet | 44 | No | 3872 | 2026-06 | Data & AI | 0
ACT-01045 | 2026-06-30 | P-1011 | Labour | E-0013 |  | Timesheet | 47.6 | Yes | 5757.7 | 2026-06 | Data & AI | 11662
ACT-01046 | 2026-06-30 | P-1011 | Labour | E-0039 |  | Timesheet | 95.1 | Yes | 5173.44 | 2026-06 | Data & AI | 10461
ACT-01047 | 2026-06-30 | P-1011 | Labour | E-0050 |  | Timesheet | 112.9 | Yes | 11786.76 | 2026-06 | Data & AI | 23709
ACT-01048 | 2026-06-30 | P-1011 | Labour | E-0053 |  | Timesheet | 131.1 | Yes | 12847.8 | 2026-06 | Data & AI | 26220
ACT-01049 | 2026-06-30 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1975.8 | 2026-06 | Data & AI | 0
ACT-01050 | 2026-06-30 | P-1011 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 515.92 | 2026-06 | Data & AI | 0
ACT-01051 | 2026-06-30 | P-1012 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4238.98 | 2026-06 | Data & AI | 0
ACT-01052 | 2026-06-30 | P-1012 | Labour | E-0010 |  | Timesheet | 88.1 | Yes | 7752.8 | 2026-06 | Data & AI | 15417.5
ACT-01053 | 2026-06-30 | P-1012 | Labour | E-0011 |  | Timesheet | 44.6 | Yes | 5794.43 | 2026-06 | Data & AI | 11596
ACT-01054 | 2026-06-30 | P-1012 | Labour | E-0040 |  | Timesheet | 95 | Yes | 6080 | 2026-06 | Data & AI | 12350
ACT-01055 | 2026-06-30 | P-1012 | Labour | E-0051 |  | Timesheet | 128.8 | Yes | 12519.36 | 2026-06 | Data & AI | 25116
ACT-01056 | 2026-06-30 | P-1012 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2511.44 | 2026-06 | Data & AI | 0
ACT-01057 | 2026-06-30 | P-1012 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 539.19 | 2026-06 | Data & AI | 0
ACT-01058 | 2026-06-30 | P-1013 | Labour | E-0004 |  | Timesheet | 119.1 | Yes | 12157.73 | 2026-06 | Digital Transformation | 24415.5
ACT-01059 | 2026-06-30 | P-1013 | Labour | E-0019 |  | Timesheet | 154.2 | Yes | 11140.95 | 2026-06 | Digital Transformation | 18504
ACT-01060 | 2026-06-30 | P-1013 | Labour | E-0028 |  | Timesheet | 177.9 | Yes | 15221.12 | 2026-06 | Digital Transformation | 30243
ACT-01061 | 2026-06-30 | P-1013 | Labour | E-0041 |  | Timesheet | 102.9 | Yes | 6585.6 | 2026-06 | Digital Transformation | 13377
ACT-01062 | 2026-06-30 | P-1013 | Labour | E-0047 |  | Timesheet | 102 | Yes | 6625.92 | 2026-06 | Digital Transformation | 13770
ACT-01063 | 2026-06-30 | P-1013 | Labour | E-0063 |  | Timesheet | 47.7 | Yes | 3709.15 | 2026-06 | Digital Transformation | 7632
ACT-01064 | 2026-06-30 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 4031.09 | 2026-06 | Digital Transformation | 0
ACT-01065 | 2026-06-30 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 6047.11 | 2026-06 | Digital Transformation | 0
ACT-01066 | 2026-06-30 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1260.31 | 2026-06 | Digital Transformation | 0
ACT-01067 | 2026-06-30 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1106.58 | 2026-06 | Digital Transformation | 0
ACT-01068 | 2026-06-30 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5513.19 | 2026-06 | Cloud & Infrastructure | 0
ACT-01069 | 2026-06-30 | P-1014 | Labour | E-0008 |  | Timesheet | 40.9 | Yes | 3887.14 | 2026-06 | Cloud & Infrastructure | 7771
ACT-01070 | 2026-06-30 | P-1014 | Labour | E-0029 |  | Timesheet | 91.3 | Yes | 9071.57 | 2026-06 | Cloud & Infrastructure | 18260
ACT-01071 | 2026-06-30 | P-1014 | Labour | E-0057 |  | Timesheet | 131.8 | Yes | 14371.47 | 2026-06 | Cloud & Infrastructure | 28996
ACT-01072 | 2026-06-30 | P-1014 | Labour | E-0061 |  | Timesheet | 94.3 | Yes | 8109.8 | 2026-06 | Cloud & Infrastructure | 16502.5
ACT-01073 | 2026-06-30 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1678.02 | 2026-06 | Cloud & Infrastructure | 0
ACT-01074 | 2026-06-30 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 777.33 | 2026-06 | Cloud & Infrastructure | 0
ACT-01075 | 2026-06-30 | P-1015 | Labour | E-0009 |  | Timesheet | 115.2 | Yes | 8616.96 | 2026-06 | Digital Transformation | 17280
ACT-01076 | 2026-06-30 | P-1015 | Labour | E-0013 |  | Timesheet | 59.4 | Yes | 7185.02 | 2026-06 | Digital Transformation | 14553
ACT-01077 | 2026-06-30 | P-1015 | Labour | E-0015 |  | Timesheet | 105 | Yes | 8282.4 | 2026-06 | Digital Transformation | 16800
ACT-01078 | 2026-06-30 | P-1015 | Labour | E-0024 |  | Timesheet | 179.5 | Yes | 17835.12 | 2026-06 | Digital Transformation | 35900
ACT-01079 | 2026-06-30 | P-1015 | Labour | E-0040 |  | Timesheet | 150.4 | Yes | 9625.6 | 2026-06 | Digital Transformation | 19552
ACT-01080 | 2026-06-30 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3625.31 | 2026-06 | Digital Transformation | 0
ACT-01081 | 2026-06-30 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4312.32 | 2026-06 | Digital Transformation | 0
ACT-01082 | 2026-06-30 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1336.95 | 2026-06 | Digital Transformation | 0
ACT-01083 | 2026-06-30 | P-1015 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1073.85 | 2026-06 | Digital Transformation | 0
ACT-01084 | 2026-06-30 | P-1016 | Hardware |  | Rockwell Automation | AP Invoice | 0 | No | 12005.88 | 2026-06 | Operational Excellence | 0
ACT-01085 | 2026-06-30 | P-1016 | Labour | E-0003 |  | Timesheet | 40.4 | No | 4124.03 | 2026-06 | Operational Excellence | 0
ACT-01086 | 2026-06-30 | P-1016 | Labour | E-0018 |  | Timesheet | 89.3 | Yes | 6558.19 | 2026-06 | Operational Excellence | 13395
ACT-01087 | 2026-06-30 | P-1016 | Labour | E-0025 |  | Timesheet | 80.7 | Yes | 8630.86 | 2026-06 | Operational Excellence | 13719
ACT-01088 | 2026-06-30 | P-1016 | Labour | E-0038 |  | Timesheet | 85.4 | Yes | 6340.1 | 2026-06 | Operational Excellence | 12810
ACT-01089 | 2026-06-30 | P-1016 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1555.89 | 2026-06 | Operational Excellence | 0
ACT-01090 | 2026-06-30 | P-1016 | Training |  | Learning Tree | AP Invoice | 0 | No | 697.51 | 2026-06 | Operational Excellence | 0
ACT-01091 | 2026-06-30 | P-1016 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 542.89 | 2026-06 | Operational Excellence | 0
ACT-01092 | 2026-06-30 | P-1017 | Labour | E-0005 |  | Timesheet | 125.4 | Yes | 9379.92 | 2026-06 | Customer Experience | 18810
ACT-01093 | 2026-06-30 | P-1017 | Labour | E-0017 |  | Timesheet | 29 | Yes | 1833.96 | 2026-06 | Customer Experience | 3770
ACT-01094 | 2026-06-30 | P-1017 | Labour | E-0022 |  | Timesheet | 30.6 | Yes | 1924.74 | 2026-06 | Customer Experience | 3978
ACT-01095 | 2026-06-30 | P-1017 | Labour | E-0027 |  | Timesheet | 127 | Yes | 12618.72 | 2026-06 | Customer Experience | 25400
ACT-01096 | 2026-06-30 | P-1017 | Labour | E-0036 |  | Timesheet | 113.6 | Yes | 6761.47 | 2026-06 | Customer Experience | 13632
ACT-01097 | 2026-06-30 | P-1017 | Labour | E-0043 |  | Timesheet | 126.9 | Yes | 10304.28 | 2026-06 | Customer Experience | 17131.5
ACT-01098 | 2026-06-30 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2095.66 | 2026-06 | Customer Experience | 0
ACT-01099 | 2026-06-30 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3292.79 | 2026-06 | Customer Experience | 0
ACT-01100 | 2026-06-30 | P-1017 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 628.58 | 2026-06 | Customer Experience | 0
ACT-01101 | 2026-06-30 | P-1020 | Labour | E-0006 |  | Timesheet | 4.3 | No | 378.4 | 2026-06 | Data & AI | 0
ACT-01102 | 2026-06-30 | P-1020 | Labour | E-0037 |  | Timesheet | 4.1 | Yes | 278.8 | 2026-06 | Data & AI | 451
ACT-01103 | 2026-06-30 | P-1020 | Labour | E-0043 |  | Timesheet | 1.9 | Yes | 154.28 | 2026-06 | Data & AI | 256.5
ACT-01104 | 2026-06-30 | P-1020 | Labour | E-0051 |  | Timesheet | 7.9 | Yes | 767.88 | 2026-06 | Data & AI | 1540.5
ACT-01105 | 2026-06-30 | P-1021 | Labour | E-0010 |  | Timesheet | 49.4 | Yes | 4347.2 | 2026-06 | Operational Excellence | 8645
ACT-01106 | 2026-06-30 | P-1021 | Labour | E-0016 |  | Timesheet | 87.1 | Yes | 6396.62 | 2026-06 | Operational Excellence | 13065
ACT-01107 | 2026-06-30 | P-1021 | Labour | E-0026 |  | Timesheet | 133.7 | Yes | 11439.37 | 2026-06 | Operational Excellence | 22729
ACT-01108 | 2026-06-30 | P-1021 | Labour | E-0033 |  | Timesheet | 97.9 | Yes | 5827.01 | 2026-06 | Operational Excellence | 11748
ACT-01109 | 2026-06-30 | P-1021 | Labour | E-0045 |  | Timesheet | 25.3 | Yes | 1317.62 | 2026-06 | Operational Excellence | 2656.5
ACT-01110 | 2026-06-30 | P-1021 | Labour | E-0062 |  | Timesheet | 11.8 | Yes | 985.54 | 2026-06 | Operational Excellence | 2065
ACT-01111 | 2026-06-30 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1370.33 | 2026-06 | Operational Excellence | 0
ACT-01112 | 2026-06-30 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 795.01 | 2026-06 | Operational Excellence | 0
ACT-01113 | 2026-06-30 | P-1021 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 561.54 | 2026-06 | Operational Excellence | 0
ACT-01114 | 2026-07-31 | P-1001 | Labour | E-0003 |  | Timesheet | 90.6 | Yes | 9248.45 | 2026-07 | Customer Experience | 18573
ACT-01115 | 2026-07-31 | P-1001 | Labour | E-0023 |  | Timesheet | 133.5 | Yes | 14247.12 | 2026-07 | Customer Experience | 28702.5
ACT-01116 | 2026-07-31 | P-1001 | Labour | E-0031 |  | Timesheet | 188 | Yes | 13957.12 | 2026-07 | Customer Experience | 28200
ACT-01117 | 2026-07-31 | P-1001 | Labour | E-0042 |  | Timesheet | 99 | Yes | 6431.04 | 2026-07 | Customer Experience | 13365
ACT-01118 | 2026-07-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2992.38 | 2026-07 | Customer Experience | 0
ACT-01119 | 2026-07-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 4286.44 | 2026-07 | Customer Experience | 0
ACT-01120 | 2026-07-31 | P-1001 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1083.65 | 2026-07 | Customer Experience | 0
ACT-01121 | 2026-07-31 | P-1002 | Hardware |  | Rockwell Automation | AP Invoice | 0 | No | 14044.15 | 2026-07 | Operational Excellence | 0
ACT-01122 | 2026-07-31 | P-1002 | Labour | E-0004 |  | Timesheet | 60.8 | Yes | 6206.46 | 2026-07 | Operational Excellence | 12464
ACT-01123 | 2026-07-31 | P-1002 | Labour | E-0016 |  | Timesheet | 127.9 | Yes | 9392.98 | 2026-07 | Operational Excellence | 19185
ACT-01124 | 2026-07-31 | P-1002 | Labour | E-0024 |  | Timesheet | 125.2 | Yes | 12439.87 | 2026-07 | Operational Excellence | 25040
ACT-01125 | 2026-07-31 | P-1002 | Labour | E-0032 |  | Timesheet | 179.3 | Yes | 10671.94 | 2026-07 | Operational Excellence | 21516
ACT-01126 | 2026-07-31 | P-1002 | Labour | E-0043 |  | Timesheet | 65.4 | Yes | 5310.48 | 2026-07 | Operational Excellence | 8829
ACT-01127 | 2026-07-31 | P-1002 | Labour | E-0062 |  | Timesheet | 64.6 | Yes | 5395.39 | 2026-07 | Operational Excellence | 11305
ACT-01128 | 2026-07-31 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1667.19 | 2026-07 | Operational Excellence | 0
ACT-01129 | 2026-07-31 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 847.26 | 2026-07 | Operational Excellence | 0
ACT-01130 | 2026-07-31 | P-1002 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 587.21 | 2026-07 | Operational Excellence | 0
ACT-01131 | 2026-07-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3983.63 | 2026-07 | Data & AI | 0
ACT-01132 | 2026-07-31 | P-1003 | Labour | E-0005 |  | Timesheet | 49.6 | No | 3710.08 | 2026-07 | Data & AI | 0
ACT-01133 | 2026-07-31 | P-1003 | Labour | E-0033 |  | Timesheet | 110.9 | Yes | 6600.77 | 2026-07 | Data & AI | 13308
ACT-01134 | 2026-07-31 | P-1003 | Labour | E-0044 |  | Timesheet | 99 | Yes | 6930 | 2026-07 | Data & AI | 11385
ACT-01135 | 2026-07-31 | P-1003 | Labour | E-0048 |  | Timesheet | 197.3 | Yes | 20598.12 | 2026-07 | Data & AI | 41433
ACT-01136 | 2026-07-31 | P-1003 | Labour | E-0052 |  | Timesheet | 96 | Yes | 10913.28 | 2026-07 | Data & AI | 22080
ACT-01137 | 2026-07-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2982.72 | 2026-07 | Data & AI | 0
ACT-01138 | 2026-07-31 | P-1003 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 491 | 2026-07 | Data & AI | 0
ACT-01139 | 2026-07-31 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 6917.73 | 2026-07 | Cloud & Infrastructure | 0
ACT-01140 | 2026-07-31 | P-1004 | Labour | E-0006 |  | Timesheet | 49.2 | Yes | 4329.6 | 2026-07 | Cloud & Infrastructure | 8610
ACT-01141 | 2026-07-31 | P-1004 | Labour | E-0011 |  | Timesheet | 42.5 | Yes | 5521.6 | 2026-07 | Cloud & Infrastructure | 11050
ACT-01142 | 2026-07-31 | P-1004 | Labour | E-0025 |  | Timesheet | 98.6 | Yes | 10545.27 | 2026-07 | Cloud & Infrastructure | 16762
ACT-01143 | 2026-07-31 | P-1004 | Labour | E-0055 |  | Timesheet | 170.7 | Yes | 18613.13 | 2026-07 | Cloud & Infrastructure | 37554
ACT-01144 | 2026-07-31 | P-1004 | Labour | E-0059 |  | Timesheet | 82.8 | Yes | 8260.13 | 2026-07 | Cloud & Infrastructure | 16974
ACT-01145 | 2026-07-31 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2199.21 | 2026-07 | Cloud & Infrastructure | 0
ACT-01146 | 2026-07-31 | P-1004 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 833.39 | 2026-07 | Cloud & Infrastructure | 0
ACT-01147 | 2026-07-31 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3171.66 | 2026-07 | Data & AI | 0
ACT-01148 | 2026-07-31 | P-1005 | Labour | E-0007 |  | Timesheet | 65.2 | Yes | 6655.62 | 2026-07 | Data & AI | 13366
ACT-01149 | 2026-07-31 | P-1005 | Labour | E-0012 |  | Timesheet | 68 | Yes | 8834.56 | 2026-07 | Data & AI | 17680
ACT-01150 | 2026-07-31 | P-1005 | Labour | E-0034 |  | Timesheet | 93.9 | Yes | 5108.16 | 2026-07 | Data & AI | 10329
ACT-01151 | 2026-07-31 | P-1005 | Labour | E-0049 |  | Timesheet | 203.4 | Yes | 15560.1 | 2026-07 | Data & AI | 31527
ACT-01152 | 2026-07-31 | P-1005 | Labour | E-0052 |  | Timesheet | 124.5 | Yes | 14153.16 | 2026-07 | Data & AI | 28635
ACT-01153 | 2026-07-31 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2137.32 | 2026-07 | Data & AI | 0
ACT-01154 | 2026-07-31 | P-1005 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 480.22 | 2026-07 | Data & AI | 0
ACT-01155 | 2026-07-31 | P-1006 | Labour | E-0009 |  | Timesheet | 107.2 | Yes | 8018.56 | 2026-07 | Customer Experience | 16080
ACT-01156 | 2026-07-31 | P-1006 | Labour | E-0026 |  | Timesheet | 179.6 | Yes | 15366.58 | 2026-07 | Customer Experience | 30532
ACT-01157 | 2026-07-31 | P-1006 | Labour | E-0035 |  | Timesheet | 239.5 | Yes | 14255.04 | 2026-07 | Customer Experience | 28740
ACT-01158 | 2026-07-31 | P-1006 | Labour | E-0045 |  | Timesheet | 115.2 | Yes | 5999.62 | 2026-07 | Customer Experience | 12096
ACT-01159 | 2026-07-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2395.47 | 2026-07 | Customer Experience | 0
ACT-01160 | 2026-07-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 3955.12 | 2026-07 | Customer Experience | 0
ACT-01161 | 2026-07-31 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 742.97 | 2026-07 | Customer Experience | 0
ACT-01162 | 2026-07-31 | P-1007 | Labour | E-0008 |  | Timesheet | 98.4 | Yes | 9351.94 | 2026-07 | Digital Transformation | 18696
ACT-01163 | 2026-07-31 | P-1007 | Labour | E-0014 |  | Timesheet | 84.8 | Yes | 8832.77 | 2026-07 | Digital Transformation | 17808
ACT-01164 | 2026-07-31 | P-1007 | Labour | E-0017 |  | Timesheet | 98.3 | Yes | 6216.49 | 2026-07 | Digital Transformation | 12779
ACT-01165 | 2026-07-31 | P-1007 | Labour | E-0027 |  | Timesheet | 132.1 | Yes | 13125.46 | 2026-07 | Digital Transformation | 26420
ACT-01166 | 2026-07-31 | P-1007 | Labour | E-0036 |  | Timesheet | 82.7 | Yes | 4922.3 | 2026-07 | Digital Transformation | 9924
ACT-01167 | 2026-07-31 | P-1007 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3886.13 | 2026-07 | Digital Transformation | 0
ACT-01168 | 2026-07-31 | P-1007 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4894.34 | 2026-07 | Digital Transformation | 0
ACT-01169 | 2026-07-31 | P-1007 | Training |  | Internal L&D | AP Invoice | 0 | No | 1202.74 | 2026-07 | Digital Transformation | 0
ACT-01170 | 2026-07-31 | P-1007 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 745.41 | 2026-07 | Digital Transformation | 0
ACT-01171 | 2026-07-31 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 5192.04 | 2026-07 | Cloud & Infrastructure | 0
ACT-01172 | 2026-07-31 | P-1008 | Labour | E-0010 |  | Timesheet | 53.9 | No | 4743.2 | 2026-07 | Cloud & Infrastructure | 0
ACT-01173 | 2026-07-31 | P-1008 | Labour | E-0029 |  | Timesheet | 112.8 | Yes | 11207.81 | 2026-07 | Cloud & Infrastructure | 22560
ACT-01174 | 2026-07-31 | P-1008 | Labour | E-0056 |  | Timesheet | 174 | Yes | 20445 | 2026-07 | Cloud & Infrastructure | 33060
ACT-01175 | 2026-07-31 | P-1008 | Labour | E-0060 |  | Timesheet | 123.4 | Yes | 9869.53 | 2026-07 | Cloud & Infrastructure | 20361
ACT-01176 | 2026-07-31 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2440.02 | 2026-07 | Cloud & Infrastructure | 0
ACT-01177 | 2026-07-31 | P-1008 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 867.33 | 2026-07 | Cloud & Infrastructure | 0
ACT-01178 | 2026-07-31 | P-1009 | Hardware |  | Rockwell Automation | AP Invoice | 0 | No | 13460.95 | 2026-07 | Operational Excellence | 0
ACT-01179 | 2026-07-31 | P-1009 | Labour | E-0005 |  | Timesheet | 89.1 | Yes | 6664.68 | 2026-07 | Operational Excellence | 13365
ACT-01180 | 2026-07-31 | P-1009 | Labour | E-0018 |  | Timesheet | 92.7 | Yes | 6807.89 | 2026-07 | Operational Excellence | 13905
ACT-01181 | 2026-07-31 | P-1009 | Labour | E-0028 |  | Timesheet | 137.2 | Yes | 11738.83 | 2026-07 | Operational Excellence | 23324
ACT-01182 | 2026-07-31 | P-1009 | Labour | E-0037 |  | Timesheet | 131.6 | Yes | 8948.8 | 2026-07 | Operational Excellence | 14476
ACT-01183 | 2026-07-31 | P-1009 | Software & Licences |  | Atlassian Cloud | AP Invoice | 0 | No | 1259.43 | 2026-07 | Operational Excellence | 0
ACT-01184 | 2026-07-31 | P-1009 | Training |  | Internal L&D | AP Invoice | 0 | No | 892.53 | 2026-07 | Operational Excellence | 0
ACT-01185 | 2026-07-31 | P-1009 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 671.65 | 2026-07 | Operational Excellence | 0
ACT-01186 | 2026-07-31 | P-1010 | Labour | E-0007 |  | Timesheet | 110.9 | Yes | 11320.67 | 2026-07 | Customer Experience | 22734.5
ACT-01187 | 2026-07-31 | P-1010 | Labour | E-0030 |  | Timesheet | 246 | Yes | 21047.76 | 2026-07 | Customer Experience | 41820
ACT-01188 | 2026-07-31 | P-1010 | Labour | E-0038 |  | Timesheet | 113 | Yes | 8389.12 | 2026-07 | Customer Experience | 16950
ACT-01189 | 2026-07-31 | P-1010 | Labour | E-0046 |  | Timesheet | 123.9 | Yes | 6938.4 | 2026-07 | Customer Experience | 14248.5
ACT-01190 | 2026-07-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3639.44 | 2026-07 | Customer Experience | 0
ACT-01191 | 2026-07-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3650.77 | 2026-07 | Customer Experience | 0
ACT-01192 | 2026-07-31 | P-1010 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 757.18 | 2026-07 | Customer Experience | 0
ACT-01193 | 2026-07-31 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2735.61 | 2026-07 | Data & AI | 0
ACT-01194 | 2026-07-31 | P-1011 | Labour | E-0006 |  | Timesheet | 49.2 | No | 4329.6 | 2026-07 | Data & AI | 0
ACT-01195 | 2026-07-31 | P-1011 | Labour | E-0013 |  | Timesheet | 44 | Yes | 5322.24 | 2026-07 | Data & AI | 10780
ACT-01196 | 2026-07-31 | P-1011 | Labour | E-0039 |  | Timesheet | 87.2 | Yes | 4743.68 | 2026-07 | Data & AI | 9592
ACT-01197 | 2026-07-31 | P-1011 | Labour | E-0050 |  | Timesheet | 111 | Yes | 11588.4 | 2026-07 | Data & AI | 23310
ACT-01198 | 2026-07-31 | P-1011 | Labour | E-0053 |  | Timesheet | 150.4 | Yes | 14739.2 | 2026-07 | Data & AI | 30080
ACT-01199 | 2026-07-31 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2381.25 | 2026-07 | Data & AI | 0
ACT-01200 | 2026-07-31 | P-1011 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 526 | 2026-07 | Data & AI | 0
ACT-01201 | 2026-07-31 | P-1012 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4265.34 | 2026-07 | Data & AI | 0
ACT-01202 | 2026-07-31 | P-1012 | Labour | E-0010 |  | Timesheet | 101 | Yes | 8888 | 2026-07 | Data & AI | 17675
ACT-01203 | 2026-07-31 | P-1012 | Labour | E-0011 |  | Timesheet | 45.1 | Yes | 5859.39 | 2026-07 | Data & AI | 11726
ACT-01204 | 2026-07-31 | P-1012 | Labour | E-0040 |  | Timesheet | 90.2 | Yes | 5772.8 | 2026-07 | Data & AI | 11726
ACT-01205 | 2026-07-31 | P-1012 | Labour | E-0051 |  | Timesheet | 134.8 | Yes | 13102.56 | 2026-07 | Data & AI | 26286
ACT-01206 | 2026-07-31 | P-1012 | Labour | E-0054 |  | Timesheet | 88.8 | Yes | 10094.78 | 2026-07 | Data & AI | 20424
ACT-01207 | 2026-07-31 | P-1012 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2232.25 | 2026-07 | Data & AI | 0
ACT-01208 | 2026-07-31 | P-1012 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 653.68 | 2026-07 | Data & AI | 0
ACT-01209 | 2026-07-31 | P-1013 | Labour | E-0004 |  | Timesheet | 109.4 | Yes | 11167.55 | 2026-07 | Digital Transformation | 22427
ACT-01210 | 2026-07-31 | P-1013 | Labour | E-0019 |  | Timesheet | 188 | Yes | 13583 | 2026-07 | Digital Transformation | 22560
ACT-01211 | 2026-07-31 | P-1013 | Labour | E-0028 |  | Timesheet | 176.6 | Yes | 15109.9 | 2026-07 | Digital Transformation | 30022
ACT-01212 | 2026-07-31 | P-1013 | Labour | E-0041 |  | Timesheet | 112 | Yes | 7168 | 2026-07 | Digital Transformation | 14560
ACT-01213 | 2026-07-31 | P-1013 | Labour | E-0047 |  | Timesheet | 128 | Yes | 8314.88 | 2026-07 | Digital Transformation | 17280
ACT-01214 | 2026-07-31 | P-1013 | Labour | E-0063 |  | Timesheet | 45.3 | Yes | 3522.53 | 2026-07 | Digital Transformation | 7248
ACT-01215 | 2026-07-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3714.47 | 2026-07 | Digital Transformation | 0
ACT-01216 | 2026-07-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5277.59 | 2026-07 | Digital Transformation | 0
ACT-01217 | 2026-07-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1507.83 | 2026-07 | Digital Transformation | 0
ACT-01218 | 2026-07-31 | P-1013 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1218.21 | 2026-07 | Digital Transformation | 0
ACT-01219 | 2026-07-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 5693.66 | 2026-07 | Cloud & Infrastructure | 0
ACT-01220 | 2026-07-31 | P-1014 | Labour | E-0008 |  | Timesheet | 47.3 | Yes | 4495.39 | 2026-07 | Cloud & Infrastructure | 8987
ACT-01221 | 2026-07-31 | P-1014 | Labour | E-0029 |  | Timesheet | 90 | Yes | 8942.4 | 2026-07 | Cloud & Infrastructure | 18000
ACT-01222 | 2026-07-31 | P-1014 | Labour | E-0057 |  | Timesheet | 125.3 | Yes | 13662.71 | 2026-07 | Cloud & Infrastructure | 27566
ACT-01223 | 2026-07-31 | P-1014 | Labour | E-0061 |  | Timesheet | 86.3 | Yes | 7421.8 | 2026-07 | Cloud & Infrastructure | 15102.5
ACT-01224 | 2026-07-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1662.3 | 2026-07 | Cloud & Infrastructure | 0
ACT-01225 | 2026-07-31 | P-1014 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 704.76 | 2026-07 | Cloud & Infrastructure | 0
ACT-01226 | 2026-07-31 | P-1015 | Labour | E-0009 |  | Timesheet | 114.9 | Yes | 8594.52 | 2026-07 | Digital Transformation | 17235
ACT-01227 | 2026-07-31 | P-1015 | Labour | E-0013 |  | Timesheet | 53.1 | Yes | 6422.98 | 2026-07 | Digital Transformation | 13009.5
ACT-01228 | 2026-07-31 | P-1015 | Labour | E-0015 |  | Timesheet | 114.9 | Yes | 9063.31 | 2026-07 | Digital Transformation | 18384
ACT-01229 | 2026-07-31 | P-1015 | Labour | E-0024 |  | Timesheet | 165.1 | Yes | 16404.34 | 2026-07 | Digital Transformation | 33020
ACT-01230 | 2026-07-31 | P-1015 | Labour | E-0040 |  | Timesheet | 154.2 | Yes | 9868.8 | 2026-07 | Digital Transformation | 20046
ACT-01231 | 2026-07-31 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 4020.75 | 2026-07 | Digital Transformation | 0
ACT-01232 | 2026-07-31 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4709.2 | 2026-07 | Digital Transformation | 0
ACT-01233 | 2026-07-31 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1267.29 | 2026-07 | Digital Transformation | 0
ACT-01234 | 2026-07-31 | P-1015 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1063.85 | 2026-07 | Digital Transformation | 0
ACT-01235 | 2026-07-31 | P-1016 | Labour | E-0003 |  | Timesheet | 47.8 | No | 4879.42 | 2026-07 | Operational Excellence | 0
ACT-01236 | 2026-07-31 | P-1016 | Labour | E-0018 |  | Timesheet | 94.4 | Yes | 6932.74 | 2026-07 | Operational Excellence | 14160
ACT-01237 | 2026-07-31 | P-1016 | Labour | E-0025 |  | Timesheet | 88.2 | Yes | 9432.99 | 2026-07 | Operational Excellence | 14994
ACT-01238 | 2026-07-31 | P-1016 | Labour | E-0038 |  | Timesheet | 93.8 | Yes | 6963.71 | 2026-07 | Operational Excellence | 14070
ACT-01239 | 2026-07-31 | P-1016 | Labour | E-0043 |  | Timesheet | 19.5 | Yes | 1583.4 | 2026-07 | Operational Excellence | 2632.5
ACT-01240 | 2026-07-31 | P-1016 | Labour | E-0062 |  | Timesheet | 18.3 | Yes | 1528.42 | 2026-07 | Operational Excellence | 3202.5
ACT-01241 | 2026-07-31 | P-1016 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1406.48 | 2026-07 | Operational Excellence | 0
ACT-01242 | 2026-07-31 | P-1016 | Training |  | Learning Tree | AP Invoice | 0 | No | 850.75 | 2026-07 | Operational Excellence | 0
ACT-01243 | 2026-07-31 | P-1016 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 508.03 | 2026-07 | Operational Excellence | 0
ACT-01244 | 2026-07-31 | P-1017 | Labour | E-0005 |  | Timesheet | 122.1 | Yes | 9133.08 | 2026-07 | Customer Experience | 18315
ACT-01245 | 2026-07-31 | P-1017 | Labour | E-0027 |  | Timesheet | 120.6 | Yes | 11982.82 | 2026-07 | Customer Experience | 24120
ACT-01246 | 2026-07-31 | P-1017 | Labour | E-0036 |  | Timesheet | 129 | Yes | 7678.08 | 2026-07 | Customer Experience | 15480
ACT-01247 | 2026-07-31 | P-1017 | Labour | E-0043 |  | Timesheet | 134.3 | Yes | 10905.16 | 2026-07 | Customer Experience | 18130.5
ACT-01248 | 2026-07-31 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2248.35 | 2026-07 | Customer Experience | 0
ACT-01249 | 2026-07-31 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 2947.05 | 2026-07 | Customer Experience | 0
ACT-01250 | 2026-07-31 | P-1017 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 696.13 | 2026-07 | Customer Experience | 0
ACT-01251 | 2026-07-31 | P-1021 | Labour | E-0010 |  | Timesheet | 18.5 | Yes | 1628 | 2026-07 | Operational Excellence | 3237.5
ACT-01252 | 2026-07-31 | P-1021 | Labour | E-0016 |  | Timesheet | 33.5 | Yes | 2460.24 | 2026-07 | Operational Excellence | 5025
ACT-01253 | 2026-07-31 | P-1021 | Labour | E-0026 |  | Timesheet | 54.9 | Yes | 4697.24 | 2026-07 | Operational Excellence | 9333
ACT-01254 | 2026-07-31 | P-1021 | Labour | E-0033 |  | Timesheet | 34.1 | Yes | 2029.63 | 2026-07 | Operational Excellence | 4092
ACT-01255 | 2026-07-31 | P-1021 | Labour | E-0045 |  | Timesheet | 35.7 | Yes | 1859.26 | 2026-07 | Operational Excellence | 3748.5
ACT-01256 | 2026-07-31 | P-1021 | Labour | E-0062 |  | Timesheet | 16.7 | Yes | 1394.78 | 2026-07 | Operational Excellence | 2922.5
ACT-01257 | 2026-07-31 | P-1021 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1276.44 | 2026-07 | Operational Excellence | 0
ACT-01258 | 2026-07-31 | P-1021 | Training |  | Learning Tree | AP Invoice | 0 | No | 691.13 | 2026-07 | Operational Excellence | 0
ACT-01259 | 2026-07-31 | P-1021 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 563.78 | 2026-07 | Operational Excellence | 0
ACT-01260 | 2026-08-31 | P-1001 | Labour | E-0003 |  | Timesheet | 77.9 | Yes | 7952.03 | 2026-08 | Customer Experience | 15969.5
ACT-01261 | 2026-08-31 | P-1001 | Labour | E-0023 |  | Timesheet | 130 | Yes | 13873.6 | 2026-08 | Customer Experience | 27950
ACT-01262 | 2026-08-31 | P-1001 | Labour | E-0031 |  | Timesheet | 154.2 | Yes | 11447.81 | 2026-08 | Customer Experience | 23130
ACT-01263 | 2026-08-31 | P-1001 | Labour | E-0042 |  | Timesheet | 78.7 | Yes | 5112.35 | 2026-08 | Customer Experience | 10624.5
ACT-01264 | 2026-08-31 | P-1001 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3127.49 | 2026-08 | Customer Experience | 0
ACT-01265 | 2026-08-31 | P-1001 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3852.34 | 2026-08 | Customer Experience | 0
ACT-01266 | 2026-08-31 | P-1001 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 1088.71 | 2026-08 | Customer Experience | 0
ACT-01267 | 2026-08-31 | P-1002 | Labour | E-0004 |  | Timesheet | 54.9 | Yes | 5604.19 | 2026-08 | Operational Excellence | 11254.5
ACT-01268 | 2026-08-31 | P-1002 | Labour | E-0016 |  | Timesheet | 123.5 | Yes | 9069.84 | 2026-08 | Operational Excellence | 18525
ACT-01269 | 2026-08-31 | P-1002 | Labour | E-0024 |  | Timesheet | 108.7 | Yes | 10800.43 | 2026-08 | Operational Excellence | 21740
ACT-01270 | 2026-08-31 | P-1002 | Labour | E-0032 |  | Timesheet | 168.1 | Yes | 10005.31 | 2026-08 | Operational Excellence | 20172
ACT-01271 | 2026-08-31 | P-1002 | Labour | E-0043 |  | Timesheet | 62.2 | Yes | 5050.64 | 2026-08 | Operational Excellence | 8397
ACT-01272 | 2026-08-31 | P-1002 | Labour | E-0062 |  | Timesheet | 58 | Yes | 4844.16 | 2026-08 | Operational Excellence | 10150
ACT-01273 | 2026-08-31 | P-1002 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1642.24 | 2026-08 | Operational Excellence | 0
ACT-01274 | 2026-08-31 | P-1002 | Training |  | Internal L&D | AP Invoice | 0 | No | 956.54 | 2026-08 | Operational Excellence | 0
ACT-01275 | 2026-08-31 | P-1002 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 651.53 | 2026-08 | Operational Excellence | 0
ACT-01276 | 2026-08-31 | P-1003 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4143.59 | 2026-08 | Data & AI | 0
ACT-01277 | 2026-08-31 | P-1003 | Labour | E-0005 |  | Timesheet | 45.8 | No | 3425.84 | 2026-08 | Data & AI | 0
ACT-01278 | 2026-08-31 | P-1003 | Labour | E-0033 |  | Timesheet | 91.6 | Yes | 5452.03 | 2026-08 | Data & AI | 10992
ACT-01279 | 2026-08-31 | P-1003 | Labour | E-0044 |  | Timesheet | 86.6 | Yes | 6062 | 2026-08 | Data & AI | 9959
ACT-01280 | 2026-08-31 | P-1003 | Labour | E-0048 |  | Timesheet | 198.2 | Yes | 20692.08 | 2026-08 | Data & AI | 41622
ACT-01281 | 2026-08-31 | P-1003 | Labour | E-0052 |  | Timesheet | 84.1 | Yes | 9560.49 | 2026-08 | Data & AI | 19343
ACT-01282 | 2026-08-31 | P-1003 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2489.36 | 2026-08 | Data & AI | 0
ACT-01283 | 2026-08-31 | P-1003 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 502.12 | 2026-08 | Data & AI | 0
ACT-01284 | 2026-08-31 | P-1004 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 7117.69 | 2026-08 | Cloud & Infrastructure | 0
ACT-01285 | 2026-08-31 | P-1004 | Hardware |  | Rockwell Automation | AP Invoice | 0 | No | 22310.72 | 2026-08 | Cloud & Infrastructure | 0
ACT-01286 | 2026-08-31 | P-1004 | Labour | E-0006 |  | Timesheet | 44.7 | Yes | 3933.6 | 2026-08 | Cloud & Infrastructure | 7822.5
ACT-01287 | 2026-08-31 | P-1004 | Labour | E-0011 |  | Timesheet | 24.7 | Yes | 3209.02 | 2026-08 | Cloud & Infrastructure | 6422
ACT-01288 | 2026-08-31 | P-1004 | Labour | E-0025 |  | Timesheet | 91.1 | Yes | 9743.15 | 2026-08 | Cloud & Infrastructure | 15487
ACT-01289 | 2026-08-31 | P-1004 | Labour | E-0055 |  | Timesheet | 157.9 | Yes | 17217.42 | 2026-08 | Cloud & Infrastructure | 34738
ACT-01290 | 2026-08-31 | P-1004 | Labour | E-0059 |  | Timesheet | 77.1 | Yes | 7691.5 | 2026-08 | Cloud & Infrastructure | 15805.5
ACT-01291 | 2026-08-31 | P-1004 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2105.26 | 2026-08 | Cloud & Infrastructure | 0
ACT-01292 | 2026-08-31 | P-1004 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 990.96 | 2026-08 | Cloud & Infrastructure | 0
ACT-01293 | 2026-08-31 | P-1005 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3385.13 | 2026-08 | Data & AI | 0
ACT-01294 | 2026-08-31 | P-1005 | Labour | E-0007 |  | Timesheet | 57.1 | Yes | 5828.77 | 2026-08 | Data & AI | 11705.5
ACT-01295 | 2026-08-31 | P-1005 | Labour | E-0012 |  | Timesheet | 58.8 | Yes | 7639.3 | 2026-08 | Data & AI | 15288
ACT-01296 | 2026-08-31 | P-1005 | Labour | E-0034 |  | Timesheet | 95.9 | Yes | 5216.96 | 2026-08 | Data & AI | 10549
ACT-01297 | 2026-08-31 | P-1005 | Labour | E-0046 |  | Timesheet | 79.4 | Yes | 4446.4 | 2026-08 | Data & AI | 9131
ACT-01298 | 2026-08-31 | P-1005 | Labour | E-0049 |  | Timesheet | 162.3 | Yes | 12415.95 | 2026-08 | Data & AI | 25156.5
ACT-01299 | 2026-08-31 | P-1005 | Labour | E-0052 |  | Timesheet | 116 | Yes | 13186.88 | 2026-08 | Data & AI | 26680
ACT-01300 | 2026-08-31 | P-1005 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2170.97 | 2026-08 | Data & AI | 0
ACT-01301 | 2026-08-31 | P-1005 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 540.7 | 2026-08 | Data & AI | 0
ACT-01302 | 2026-08-31 | P-1006 | Labour | E-0009 |  | Timesheet | 95.6 | Yes | 7150.88 | 2026-08 | Customer Experience | 14340
ACT-01303 | 2026-08-31 | P-1006 | Labour | E-0026 |  | Timesheet | 149 | Yes | 12748.44 | 2026-08 | Customer Experience | 25330
ACT-01304 | 2026-08-31 | P-1006 | Labour | E-0035 |  | Timesheet | 192.1 | Yes | 11433.79 | 2026-08 | Customer Experience | 23052
ACT-01305 | 2026-08-31 | P-1006 | Labour | E-0045 |  | Timesheet | 114.2 | Yes | 5947.54 | 2026-08 | Customer Experience | 11991
ACT-01306 | 2026-08-31 | P-1006 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2530.29 | 2026-08 | Customer Experience | 0
ACT-01307 | 2026-08-31 | P-1006 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4186.71 | 2026-08 | Customer Experience | 0
ACT-01308 | 2026-08-31 | P-1006 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 743.73 | 2026-08 | Customer Experience | 0
ACT-01309 | 2026-08-31 | P-1007 | Labour | E-0008 |  | Timesheet | 89.9 | Yes | 8544.1 | 2026-08 | Digital Transformation | 17081
ACT-01310 | 2026-08-31 | P-1007 | Labour | E-0014 |  | Timesheet | 89.6 | Yes | 9332.74 | 2026-08 | Digital Transformation | 18816
ACT-01311 | 2026-08-31 | P-1007 | Labour | E-0017 |  | Timesheet | 88.3 | Yes | 5584.09 | 2026-08 | Digital Transformation | 11479
ACT-01312 | 2026-08-31 | P-1007 | Labour | E-0027 |  | Timesheet | 116.8 | Yes | 11605.25 | 2026-08 | Digital Transformation | 23360
ACT-01313 | 2026-08-31 | P-1007 | Labour | E-0036 |  | Timesheet | 77.8 | Yes | 4630.66 | 2026-08 | Digital Transformation | 9336
ACT-01314 | 2026-08-31 | P-1007 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 3551.97 | 2026-08 | Digital Transformation | 0
ACT-01315 | 2026-08-31 | P-1007 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4875.32 | 2026-08 | Digital Transformation | 0
ACT-01316 | 2026-08-31 | P-1007 | Training |  | Internal L&D | AP Invoice | 0 | No | 1412.84 | 2026-08 | Digital Transformation | 0
ACT-01317 | 2026-08-31 | P-1007 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 873.47 | 2026-08 | Digital Transformation | 0
ACT-01318 | 2026-08-31 | P-1008 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 4768.74 | 2026-08 | Cloud & Infrastructure | 0
ACT-01319 | 2026-08-31 | P-1008 | Labour | E-0010 |  | Timesheet | 55.4 | No | 4875.2 | 2026-08 | Cloud & Infrastructure | 0
ACT-01320 | 2026-08-31 | P-1008 | Labour | E-0029 |  | Timesheet | 101.5 | Yes | 10085.04 | 2026-08 | Cloud & Infrastructure | 20300
ACT-01321 | 2026-08-31 | P-1008 | Labour | E-0056 |  | Timesheet | 163.8 | Yes | 19246.5 | 2026-08 | Cloud & Infrastructure | 31122
ACT-01322 | 2026-08-31 | P-1008 | Labour | E-0060 |  | Timesheet | 100.4 | Yes | 8029.99 | 2026-08 | Cloud & Infrastructure | 16566
ACT-01323 | 2026-08-31 | P-1008 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2372.84 | 2026-08 | Cloud & Infrastructure | 0
ACT-01324 | 2026-08-31 | P-1008 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 944.89 | 2026-08 | Cloud & Infrastructure | 0
ACT-01325 | 2026-08-31 | P-1009 | Labour | E-0005 |  | Timesheet | 83.4 | Yes | 6238.32 | 2026-08 | Operational Excellence | 12510
ACT-01326 | 2026-08-31 | P-1009 | Labour | E-0018 |  | Timesheet | 77 | Yes | 5654.88 | 2026-08 | Operational Excellence | 11550
ACT-01327 | 2026-08-31 | P-1009 | Labour | E-0028 |  | Timesheet | 138.4 | Yes | 11841.5 | 2026-08 | Operational Excellence | 23528
ACT-01328 | 2026-08-31 | P-1009 | Labour | E-0037 |  | Timesheet | 126.6 | Yes | 8608.8 | 2026-08 | Operational Excellence | 13926
ACT-01329 | 2026-08-31 | P-1009 | Labour | E-0047 |  | Timesheet | 65.6 | Yes | 4261.38 | 2026-08 | Operational Excellence | 8856
ACT-01330 | 2026-08-31 | P-1009 | Labour | E-0063 |  | Timesheet | 26 | Yes | 2021.76 | 2026-08 | Operational Excellence | 4160
ACT-01331 | 2026-08-31 | P-1009 | Software & Licences |  | Atlassian Cloud | AP Invoice | 0 | No | 1420.25 | 2026-08 | Operational Excellence | 0
ACT-01332 | 2026-08-31 | P-1009 | Training |  | Internal L&D | AP Invoice | 0 | No | 823.64 | 2026-08 | Operational Excellence | 0
ACT-01333 | 2026-08-31 | P-1009 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 663.06 | 2026-08 | Operational Excellence | 0
ACT-01334 | 2026-08-31 | P-1010 | Labour | E-0007 |  | Timesheet | 100 | Yes | 10208 | 2026-08 | Customer Experience | 20500
ACT-01335 | 2026-08-31 | P-1010 | Labour | E-0030 |  | Timesheet | 205.9 | Yes | 17616.8 | 2026-08 | Customer Experience | 35003
ACT-01336 | 2026-08-31 | P-1010 | Labour | E-0038 |  | Timesheet | 103.9 | Yes | 7713.54 | 2026-08 | Customer Experience | 15585
ACT-01337 | 2026-08-31 | P-1010 | Labour | E-0046 |  | Timesheet | 103.7 | Yes | 5807.2 | 2026-08 | Customer Experience | 11925.5
ACT-01338 | 2026-08-31 | P-1010 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 3043.61 | 2026-08 | Customer Experience | 0
ACT-01339 | 2026-08-31 | P-1010 | Subcontractors |  | Cedar Integration Partners | AP Invoice | 0 | No | 3516.39 | 2026-08 | Customer Experience | 0
ACT-01340 | 2026-08-31 | P-1010 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 804.25 | 2026-08 | Customer Experience | 0
ACT-01341 | 2026-08-31 | P-1011 | Cloud Hosting |  | AWS | AP Invoice | 0 | No | 2687.23 | 2026-08 | Data & AI | 0
ACT-01342 | 2026-08-31 | P-1011 | Labour | E-0006 |  | Timesheet | 41 | No | 3608 | 2026-08 | Data & AI | 0
ACT-01343 | 2026-08-31 | P-1011 | Labour | E-0013 |  | Timesheet | 44.1 | Yes | 5334.34 | 2026-08 | Data & AI | 10804.5
ACT-01344 | 2026-08-31 | P-1011 | Labour | E-0039 |  | Timesheet | 75.1 | Yes | 4085.44 | 2026-08 | Data & AI | 8261
ACT-01345 | 2026-08-31 | P-1011 | Labour | E-0050 |  | Timesheet | 97.5 | Yes | 10179 | 2026-08 | Data & AI | 20475
ACT-01346 | 2026-08-31 | P-1011 | Labour | E-0053 |  | Timesheet | 135.2 | Yes | 13249.6 | 2026-08 | Data & AI | 27040
ACT-01347 | 2026-08-31 | P-1011 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 2187.28 | 2026-08 | Data & AI | 0
ACT-01348 | 2026-08-31 | P-1011 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 418.84 | 2026-08 | Data & AI | 0
ACT-01349 | 2026-08-31 | P-1012 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 3840.58 | 2026-08 | Data & AI | 0
ACT-01350 | 2026-08-31 | P-1012 | Labour | E-0010 |  | Timesheet | 82 | Yes | 7216 | 2026-08 | Data & AI | 14350
ACT-01351 | 2026-08-31 | P-1012 | Labour | E-0011 |  | Timesheet | 39.4 | Yes | 5118.85 | 2026-08 | Data & AI | 10244
ACT-01352 | 2026-08-31 | P-1012 | Labour | E-0040 |  | Timesheet | 92 | Yes | 5888 | 2026-08 | Data & AI | 11960
ACT-01353 | 2026-08-31 | P-1012 | Labour | E-0042 |  | Timesheet | 3.7 | Yes | 240.35 | 2026-08 | Data & AI | 499.5
ACT-01354 | 2026-08-31 | P-1012 | Labour | E-0051 |  | Timesheet | 138.5 | Yes | 13462.2 | 2026-08 | Data & AI | 27007.5
ACT-01355 | 2026-08-31 | P-1012 | Labour | E-0054 |  | Timesheet | 117.2 | Yes | 13323.3 | 2026-08 | Data & AI | 26956
ACT-01356 | 2026-08-31 | P-1012 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 2328.88 | 2026-08 | Data & AI | 0
ACT-01357 | 2026-08-31 | P-1012 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 537.66 | 2026-08 | Data & AI | 0
ACT-01358 | 2026-08-31 | P-1013 | Labour | E-0004 |  | Timesheet | 96.7 | Yes | 9871.14 | 2026-08 | Digital Transformation | 19823.5
ACT-01359 | 2026-08-31 | P-1013 | Labour | E-0019 |  | Timesheet | 162.8 | Yes | 11762.3 | 2026-08 | Digital Transformation | 19536
ACT-01360 | 2026-08-31 | P-1013 | Labour | E-0028 |  | Timesheet | 154.9 | Yes | 13253.24 | 2026-08 | Digital Transformation | 26333
ACT-01361 | 2026-08-31 | P-1013 | Labour | E-0041 |  | Timesheet | 117.9 | Yes | 7545.6 | 2026-08 | Digital Transformation | 15327
ACT-01362 | 2026-08-31 | P-1013 | Labour | E-0047 |  | Timesheet | 111.2 | Yes | 7223.55 | 2026-08 | Digital Transformation | 15012
ACT-01363 | 2026-08-31 | P-1013 | Labour | E-0063 |  | Timesheet | 40.3 | Yes | 3133.73 | 2026-08 | Digital Transformation | 6448
ACT-01364 | 2026-08-31 | P-1013 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 3917.64 | 2026-08 | Digital Transformation | 0
ACT-01365 | 2026-08-31 | P-1013 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 5742.97 | 2026-08 | Digital Transformation | 0
ACT-01366 | 2026-08-31 | P-1013 | Training |  | Learning Tree | AP Invoice | 0 | No | 1641.89 | 2026-08 | Digital Transformation | 0
ACT-01367 | 2026-08-31 | P-1013 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 1150.19 | 2026-08 | Digital Transformation | 0
ACT-01368 | 2026-08-31 | P-1014 | Cloud Hosting |  | Microsoft Azure | AP Invoice | 0 | No | 4841.58 | 2026-08 | Cloud & Infrastructure | 0
ACT-01369 | 2026-08-31 | P-1014 | Labour | E-0008 |  | Timesheet | 45.1 | Yes | 4286.3 | 2026-08 | Cloud & Infrastructure | 8569
ACT-01370 | 2026-08-31 | P-1014 | Labour | E-0029 |  | Timesheet | 91.3 | Yes | 9071.57 | 2026-08 | Cloud & Infrastructure | 18260
ACT-01371 | 2026-08-31 | P-1014 | Labour | E-0057 |  | Timesheet | 124.3 | Yes | 13553.67 | 2026-08 | Cloud & Infrastructure | 27346
ACT-01372 | 2026-08-31 | P-1014 | Labour | E-0061 |  | Timesheet | 90.3 | Yes | 7765.8 | 2026-08 | Cloud & Infrastructure | 15802.5
ACT-01373 | 2026-08-31 | P-1014 | Software & Licences |  | Microsoft | AP Invoice | 0 | No | 1700.94 | 2026-08 | Cloud & Infrastructure | 0
ACT-01374 | 2026-08-31 | P-1014 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 755.91 | 2026-08 | Cloud & Infrastructure | 0
ACT-01375 | 2026-08-31 | P-1015 | Labour | E-0009 |  | Timesheet | 96.9 | Yes | 7248.12 | 2026-08 | Digital Transformation | 14535
ACT-01376 | 2026-08-31 | P-1015 | Labour | E-0013 |  | Timesheet | 52.5 | Yes | 6350.4 | 2026-08 | Digital Transformation | 12862.5
ACT-01377 | 2026-08-31 | P-1015 | Labour | E-0015 |  | Timesheet | 106.2 | Yes | 8377.06 | 2026-08 | Digital Transformation | 16992
ACT-01378 | 2026-08-31 | P-1015 | Labour | E-0024 |  | Timesheet | 169.4 | Yes | 16831.58 | 2026-08 | Digital Transformation | 33880
ACT-01379 | 2026-08-31 | P-1015 | Labour | E-0040 |  | Timesheet | 164.4 | Yes | 10521.6 | 2026-08 | Digital Transformation | 21372
ACT-01380 | 2026-08-31 | P-1015 | Software & Licences |  | Figma Inc. | AP Invoice | 0 | No | 4485.94 | 2026-08 | Digital Transformation | 0
ACT-01381 | 2026-08-31 | P-1015 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 4352.14 | 2026-08 | Digital Transformation | 0
ACT-01382 | 2026-08-31 | P-1015 | Training |  | Internal L&D | AP Invoice | 0 | No | 1266.74 | 2026-08 | Digital Transformation | 0
ACT-01383 | 2026-08-31 | P-1015 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 895.21 | 2026-08 | Digital Transformation | 0
ACT-01384 | 2026-08-31 | P-1016 | Hardware |  | Cisco Systems | AP Invoice | 0 | No | 8216.52 | 2026-08 | Operational Excellence | 0
ACT-01385 | 2026-08-31 | P-1016 | Labour | E-0003 |  | Timesheet | 44.9 | No | 4583.39 | 2026-08 | Operational Excellence | 0
ACT-01386 | 2026-08-31 | P-1016 | Labour | E-0018 |  | Timesheet | 87.7 | Yes | 6440.69 | 2026-08 | Operational Excellence | 13155
ACT-01387 | 2026-08-31 | P-1016 | Labour | E-0025 |  | Timesheet | 92.6 | Yes | 9903.57 | 2026-08 | Operational Excellence | 15742
ACT-01388 | 2026-08-31 | P-1016 | Labour | E-0038 |  | Timesheet | 88.4 | Yes | 6562.82 | 2026-08 | Operational Excellence | 13260
ACT-01389 | 2026-08-31 | P-1016 | Labour | E-0043 |  | Timesheet | 44.2 | Yes | 3589.04 | 2026-08 | Operational Excellence | 5967
ACT-01390 | 2026-08-31 | P-1016 | Labour | E-0062 |  | Timesheet | 42.5 | Yes | 3549.6 | 2026-08 | Operational Excellence | 7437.5
ACT-01391 | 2026-08-31 | P-1016 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 1259.08 | 2026-08 | Operational Excellence | 0
ACT-01392 | 2026-08-31 | P-1016 | Training |  | Learning Tree | AP Invoice | 0 | No | 835.08 | 2026-08 | Operational Excellence | 0
ACT-01393 | 2026-08-31 | P-1016 | Travel & Expenses |  | Corporate Travel (Navan) | Expense Claim | 0 | No | 608.86 | 2026-08 | Operational Excellence | 0
ACT-01394 | 2026-08-31 | P-1017 | Labour | E-0005 |  | Timesheet | 120.2 | Yes | 8990.96 | 2026-08 | Customer Experience | 18030
ACT-01395 | 2026-08-31 | P-1017 | Labour | E-0027 |  | Timesheet | 108.9 | Yes | 10820.3 | 2026-08 | Customer Experience | 21780
ACT-01396 | 2026-08-31 | P-1017 | Labour | E-0036 |  | Timesheet | 124.8 | Yes | 7428.1 | 2026-08 | Customer Experience | 14976
ACT-01397 | 2026-08-31 | P-1017 | Labour | E-0043 |  | Timesheet | 125 | Yes | 10150 | 2026-08 | Customer Experience | 16875
ACT-01398 | 2026-08-31 | P-1017 | Software & Licences |  | Salesforce | AP Invoice | 0 | No | 2526.53 | 2026-08 | Customer Experience | 0
ACT-01399 | 2026-08-31 | P-1017 | Subcontractors |  | NorthByte Testing | AP Invoice | 0 | No | 2978.68 | 2026-08 | Customer Experience | 0
ACT-01400 | 2026-08-31 | P-1017 | Travel & Expenses |  | Expense claims | Expense Claim | 0 | No | 586.4 | 2026-08 | Customer Experience | 0

## Milestones
MilestoneID | ProjectID | MilestoneName | Phase | BaselineDate | ForecastDate | ActualDate | IsBillingMilestone | BillingPct | BillingAmount | VarianceDays | Status | Invoiced
M-0001 | P-1001 | Discovery sign-off | Discovery | 2025-12-09 | 2025-12-09 | 2025-12-09 | Yes | 10% | 110000 | 0 | Completed | Yes
M-0002 | P-1001 | Design approval | Design | 2026-02-04 | 2026-02-04 | 2026-02-04 | Yes | 20% | 220000 | 0 | Completed | Yes
M-0003 | P-1001 | Build complete | Build | 2026-07-13 | 2026-07-15 | 2026-07-15 | Yes | 30% | 330000 | 2 | Completed | Yes
M-0004 | P-1001 | UAT sign-off | Test | 2026-09-23 | 2026-09-28 |  | Yes | 20% | 220000 | 5 | On Track | No
M-0005 | P-1001 | Go-live | Deploy | 2026-10-30 | 2026-11-03 |  | Yes | 20% | 220000 | 4 | On Track | No
M-0006 | P-1002 | Discovery sign-off | Discovery | 2026-02-13 | 2026-02-13 | 2026-02-13 | Yes | 10% | 68500 | 0 | Completed | Yes
M-0007 | P-1002 | Design approval | Design | 2026-04-10 | 2026-04-13 | 2026-04-13 | Yes | 20% | 137000 | 3 | Completed | Yes
M-0008 | P-1002 | Build complete | Build | 2026-09-04 | 2026-09-04 |  | Yes | 30% | 205500 | 0 | Overdue | No
M-0009 | P-1002 | UAT sign-off | Test | 2026-11-13 | 2026-11-27 |  | Yes | 20% | 137000 | 14 | On Track | No
M-0010 | P-1002 | Go-live | Deploy | 2026-12-18 | 2027-01-04 |  | Yes | 20% | 137000 | 17 | At Risk | No
M-0011 | P-1003 | Discovery sign-off | Discovery | 2025-10-22 | 2025-10-24 | 2025-10-24 | No | 0% | 0 | 2 | Completed | No
M-0012 | P-1003 | Design approval | Design | 2026-01-01 | 2026-01-08 | 2026-01-08 | No | 0% | 0 | 7 | Completed | No
M-0013 | P-1003 | Build complete | Build | 2026-07-16 | 2026-08-29 |  | No | 0% | 0 | 44 | Overdue | No
M-0014 | P-1003 | UAT sign-off | Test | 2026-10-13 | 2026-11-17 |  | No | 0% | 0 | 35 | At Risk | No
M-0015 | P-1003 | Go-live | Deploy | 2026-11-27 | 2027-01-07 |  | No | 0% | 0 | 41 | At Risk | No
M-0016 | P-1004 | Discovery sign-off | Discovery | 2026-03-10 | 2026-03-10 | 2026-03-10 | Yes | 10% | 115500 | 0 | Completed | Yes
M-0017 | P-1004 | Design approval | Design | 2026-05-06 | 2026-05-07 | 2026-05-07 | Yes | 20% | 231000 | 1 | Completed | Yes
M-0018 | P-1004 | Build complete | Build | 2026-10-12 | 2026-10-15 |  | Yes | 30% | 346500 | 3 | On Track | No
M-0019 | P-1004 | UAT sign-off | Test | 2026-12-23 | 2026-12-28 |  | Yes | 20% | 231000 | 5 | On Track | No
M-0020 | P-1004 | Go-live | Deploy | 2027-01-29 | 2027-02-04 |  | Yes | 20% | 231000 | 6 | On Track | No
M-0021 | P-1005 | Discovery sign-off | Discovery | 2026-04-07 | 2026-04-10 | 2026-04-10 | Yes | 10% | 74000 | 3 | Completed | Yes
M-0022 | P-1005 | Design approval | Design | 2026-06-03 | 2026-06-15 | 2026-06-15 | Yes | 20% | 148000 | 12 | Completed | Yes
M-0023 | P-1005 | Build complete | Build | 2026-11-09 | 2026-12-21 |  | Yes | 30% | 222000 | 42 | At Risk | No
M-0024 | P-1005 | UAT sign-off | Test | 2027-01-20 | 2027-03-18 |  | Yes | 20% | 148000 | 57 | At Risk | No
M-0025 | P-1005 | Go-live | Deploy | 2027-02-26 | 2027-05-03 |  | Yes | 20% | 148000 | 66 | At Risk | No
M-0026 | P-1006 | Discovery sign-off | Discovery | 2025-11-10 | 2025-11-10 | 2025-11-10 | Yes | 10% | 94000 | 0 | Completed | Yes
M-0027 | P-1006 | Design approval | Design | 2026-01-06 | 2026-01-07 | 2026-01-07 | Yes | 20% | 188000 | 1 | Completed | Yes
M-0028 | P-1006 | Build complete | Build | 2026-06-10 | 2026-06-16 | 2026-06-16 | Yes | 30% | 282000 | 6 | Completed | Yes
M-0029 | P-1006 | UAT sign-off | Test | 2026-08-20 | 2026-08-28 | 2026-08-28 | Yes | 20% | 188000 | 8 | Completed | Yes
M-0030 | P-1006 | Go-live | Deploy | 2026-09-25 | 2026-10-05 |  | Yes | 20% | 188000 | 10 | On Track | No
M-0031 | P-1007 | Discovery sign-off | Discovery | 2026-05-11 | 2026-05-11 | 2026-05-11 | Yes | 10% | 97000 | 0 | Completed | Yes
M-0032 | P-1007 | Design approval | Design | 2026-07-07 | 2026-07-07 | 2026-07-07 | Yes | 20% | 194000 | 0 | Completed | Yes
M-0033 | P-1007 | Build complete | Build | 2026-12-09 | 2026-12-10 |  | Yes | 30% | 291000 | 1 | On Track | No
M-0034 | P-1007 | UAT sign-off | Test | 2027-02-18 | 2027-02-22 |  | Yes | 20% | 194000 | 4 | On Track | No
M-0035 | P-1007 | Go-live | Deploy | 2027-03-26 | 2027-03-29 |  | Yes | 20% | 194000 | 3 | On Track | No
M-0036 | P-1008 | Discovery sign-off | Discovery | 2026-02-02 | 2026-02-02 | 2026-02-02 | No | 0% | 0 | 0 | Completed | No
M-0037 | P-1008 | Design approval | Design | 2026-03-19 | 2026-03-23 | 2026-03-23 | No | 0% | 0 | 4 | Completed | No
M-0038 | P-1008 | Build complete | Build | 2026-07-22 | 2026-08-03 | 2026-08-03 | No | 0% | 0 | 12 | Completed | No
M-0039 | P-1008 | UAT sign-off | Test | 2026-09-17 | 2026-10-01 |  | No | 0% | 0 | 14 | On Track | No
M-0040 | P-1008 | Go-live | Deploy | 2026-10-16 | 2026-11-02 |  | No | 0% | 0 | 17 | At Risk | No
M-0041 | P-1009 | Discovery sign-off | Discovery | 2026-05-26 | 2026-05-26 | 2026-05-26 | Yes | 10% | 53500 | 0 | Completed | Yes
M-0042 | P-1009 | Design approval | Design | 2026-06-30 | 2026-06-30 | 2026-06-30 | Yes | 20% | 107000 | 0 | Completed | Yes
M-0043 | P-1009 | Build complete | Build | 2026-10-05 | 2026-10-06 |  | Yes | 30% | 160500 | 1 | On Track | No
M-0044 | P-1009 | UAT sign-off | Test | 2026-11-18 | 2026-11-20 |  | Yes | 20% | 107000 | 2 | On Track | No
M-0045 | P-1009 | Go-live | Deploy | 2026-12-11 | 2026-12-14 |  | Yes | 20% | 107000 | 3 | On Track | No
M-0046 | P-1010 | Discovery sign-off | Discovery | 2025-12-26 | 2025-12-29 | 2025-12-29 | Yes | 10% | 73500 | 3 | Completed | Yes
M-0047 | P-1010 | Design approval | Design | 2026-02-09 | 2026-02-17 | 2026-02-17 | Yes | 20% | 147000 | 8 | Completed | Yes
M-0048 | P-1010 | Build complete | Build | 2026-06-08 | 2026-07-08 | 2026-07-08 | Yes | 30% | 220500 | 30 | Completed | Yes
M-0049 | P-1010 | UAT sign-off | Test | 2026-07-31 | 2026-09-02 |  | Yes | 20% | 147000 | 33 | Overdue | No
M-0050 | P-1010 | Go-live | Deploy | 2026-08-28 | 2026-10-16 |  | Yes | 20% | 147000 | 49 | At Risk | No
M-0051 | P-1011 | Discovery sign-off | Discovery | 2026-03-31 | 2026-03-31 | 2026-03-31 | No | 0% | 0 | 0 | Completed | No
M-0052 | P-1011 | Design approval | Design | 2026-06-09 | 2026-06-09 | 2026-06-09 | No | 0% | 0 | 0 | Completed | No
M-0053 | P-1011 | Build complete | Build | 2026-12-18 | 2026-12-18 |  | No | 0% | 0 | 0 | On Track | No
M-0054 | P-1011 | UAT sign-off | Test | 2027-03-17 | 2027-03-17 |  | No | 0% | 0 | 0 | On Track | No
M-0055 | P-1011 | Go-live | Deploy | 2027-04-30 | 2027-04-30 |  | No | 0% | 0 | 0 | On Track | No
M-0056 | P-1012 | Discovery sign-off | Discovery | 2026-06-19 | 2026-06-19 | 2026-06-19 | Yes | 10% | 51000 | 0 | Completed | Yes
M-0057 | P-1012 | Design approval | Design | 2026-07-23 | 2026-07-23 | 2026-07-23 | Yes | 20% | 102000 | 0 | Completed | Yes
M-0058 | P-1012 | Build complete | Build | 2026-10-19 | 2026-10-19 |  | Yes | 30% | 153000 | 0 | On Track | No
M-0059 | P-1012 | UAT sign-off | Test | 2026-11-27 | 2026-11-27 |  | Yes | 20% | 102000 | 0 | On Track | No
M-0060 | P-1012 | Go-live | Deploy | 2026-12-18 | 2026-12-18 |  | Yes | 20% | 102000 | 0 | On Track | No
M-0061 | P-1013 | Discovery sign-off | Discovery | 2025-09-18 | 2025-09-18 | 2025-09-18 | Yes | 10% | 141500 | 0 | Completed | Yes
M-0062 | P-1013 | Design approval | Design | 2025-11-28 | 2025-12-01 | 2025-12-01 | Yes | 20% | 283000 | 3 | Completed | Yes
M-0063 | P-1013 | Build complete | Build | 2026-06-16 | 2026-06-26 | 2026-06-26 | Yes | 30% | 424500 | 10 | Completed | Yes
M-0064 | P-1013 | UAT sign-off | Test | 2026-09-14 | 2026-09-28 |  | Yes | 20% | 283000 | 14 | On Track | No
M-0065 | P-1013 | Go-live | Deploy | 2026-10-30 | 2026-11-16 |  | Yes | 20% | 283000 | 17 | At Risk | No
M-0066 | P-1014 | Discovery sign-off | Discovery | 2025-08-22 | 2025-08-22 | 2025-08-22 | No | 0% | 0 | 0 | Completed | No
M-0067 | P-1014 | Design approval | Design | 2025-11-20 | 2025-11-20 | 2025-11-20 | No | 0% | 0 | 0 | Completed | No
M-0068 | P-1014 | Build complete | Build | 2026-07-17 | 2026-07-20 | 2026-07-20 | No | 0% | 0 | 3 | Completed | No
M-0069 | P-1014 | UAT sign-off | Test | 2026-11-06 | 2026-11-09 |  | No | 0% | 0 | 3 | On Track | No
M-0070 | P-1014 | Go-live | Deploy | 2026-12-31 | 2027-01-04 |  | No | 0% | 0 | 4 | On Track | No
M-0071 | P-1015 | Discovery sign-off | Discovery | 2026-05-01 | 2026-05-01 | 2026-05-01 | Yes | 10% | 131500 | 0 | Completed | Yes
M-0072 | P-1015 | Design approval | Design | 2026-07-15 | 2026-07-16 | 2026-07-16 | Yes | 20% | 263000 | 1 | Completed | Yes
M-0073 | P-1015 | Build complete | Build | 2027-02-05 | 2027-02-11 |  | Yes | 30% | 394500 | 6 | On Track | No
M-0074 | P-1015 | UAT sign-off | Test | 2027-05-07 | 2027-05-17 |  | Yes | 20% | 263000 | 10 | On Track | No
M-0075 | P-1015 | Go-live | Deploy | 2027-06-25 | 2027-07-05 |  | Yes | 20% | 263000 | 10 | On Track | No
M-0076 | P-1016 | Discovery sign-off | Discovery | 2026-05-05 | 2026-05-05 | 2026-05-05 | No | 0% | 0 | 0 | Completed | No
M-0077 | P-1016 | Design approval | Design | 2026-06-09 | 2026-06-09 | 2026-06-09 | No | 0% | 0 | 0 | Completed | No
M-0078 | P-1016 | Build complete | Build | 2026-09-14 | 2026-09-15 |  | No | 0% | 0 | 1 | On Track | No
M-0079 | P-1016 | UAT sign-off | Test | 2026-10-28 | 2026-10-30 |  | No | 0% | 0 | 2 | On Track | No
M-0080 | P-1016 | Go-live | Deploy | 2026-11-20 | 2026-11-23 |  | No | 0% | 0 | 3 | On Track | No
M-0081 | P-1017 | Discovery sign-off | Discovery | 2026-02-13 | 2026-02-16 | 2026-02-16 | Yes | 10% | 46500 | 3 | Completed | Yes
M-0082 | P-1017 | Design approval | Design | 2026-03-26 | 2026-04-06 | 2026-04-06 | Yes | 20% | 93000 | 11 | Completed | Yes
M-0083 | P-1017 | Build complete | Build | 2026-07-15 | 2026-08-18 | 2026-08-18 | Yes | 30% | 139500 | 34 | Completed | Yes
M-0084 | P-1017 | UAT sign-off | Test | 2026-09-04 | 2026-09-05 |  | Yes | 20% | 93000 | 1 | Overdue | No
M-0085 | P-1017 | Go-live | Deploy | 2026-09-30 | 2026-11-24 |  | Yes | 20% | 93000 | 55 | At Risk | No
M-0086 | P-1018 | Discovery sign-off | Discovery | 2025-06-20 | 2025-06-20 | 2025-06-20 | Yes | 10% | 62000 | 0 | Completed | Yes
M-0087 | P-1018 | Design approval | Design | 2025-07-24 | 2025-07-24 | 2025-07-24 | Yes | 20% | 124000 | 0 | Completed | Yes
M-0088 | P-1018 | Build complete | Build | 2025-10-20 | 2025-10-20 | 2025-10-20 | Yes | 30% | 186000 | 0 | Completed | Yes
M-0089 | P-1018 | UAT sign-off | Test | 2025-11-28 | 2025-11-28 | 2025-11-28 | Yes | 20% | 124000 | 0 | Completed | Yes
M-0090 | P-1018 | Go-live | Deploy | 2025-12-19 | 2025-12-19 | 2025-12-19 | Yes | 20% | 124000 | 0 | Completed | Yes
M-0091 | P-1019 | Discovery sign-off | Discovery | 2025-06-03 | 2025-06-05 | 2025-06-05 | Yes | 10% | 98500 | 2 | Completed | Yes
M-0092 | P-1019 | Design approval | Design | 2025-07-21 | 2025-07-28 | 2025-07-28 | Yes | 20% | 197000 | 7 | Completed | Yes
M-0093 | P-1019 | Build complete | Build | 2025-11-28 | 2025-12-24 | 2025-12-24 | Yes | 30% | 295500 | 26 | Completed | Yes
M-0094 | P-1019 | UAT sign-off | Test | 2026-01-28 | 2026-03-05 | 2026-03-05 | Yes | 20% | 197000 | 36 | Completed | Yes
M-0095 | P-1019 | Go-live | Deploy | 2026-02-27 | 2026-04-10 | 2026-04-10 | Yes | 20% | 197000 | 42 | Completed | Yes
M-0096 | P-1020 | Discovery sign-off | Discovery | 2025-11-04 | 2025-11-04 | 2025-11-04 | No | 0% | 0 | 0 | Completed | No
M-0097 | P-1020 | Design approval | Design | 2025-12-11 | 2025-12-11 | 2025-12-11 | No | 0% | 0 | 0 | Completed | No
M-0098 | P-1020 | Build complete | Build | 2026-03-20 | 2026-03-23 | 2026-03-23 | No | 0% | 0 | 3 | Completed | No
M-0099 | P-1020 | UAT sign-off | Test | 2026-05-06 | 2026-05-08 | 2026-05-08 | No | 0% | 0 | 2 | Completed | No
M-0100 | P-1020 | Go-live | Deploy | 2026-05-29 | 2026-06-01 | 2026-06-01 | No | 0% | 0 | 3 | Completed | No
M-0101 | P-1021 | Discovery sign-off | Discovery | 2026-03-10 | 2026-03-16 | 2026-03-16 | Yes | 10% | 62500 | 6 | Completed | Yes
M-0102 | P-1021 | Design approval | Design | 2026-04-27 | 2026-05-12 | 2026-05-12 | Yes | 20% | 125000 | 15 | Completed | Yes
M-0103 | P-1021 | Build complete | Build | 2026-09-04 | 2026-10-30 |  | Yes | 30% | 187500 | 56 | At Risk | No
M-0104 | P-1021 | UAT sign-off | Test | 2026-11-04 | 2027-01-21 |  | Yes | 20% | 125000 | 78 | At Risk | No
M-0105 | P-1021 | Go-live | Deploy | 2026-12-04 | 2027-03-04 |  | Yes | 20% | 125000 | 90 | At Risk | No
M-0106 | P-1022 | Discovery sign-off | Discovery | 2026-10-28 | 2026-10-28 |  | Yes | 10% | 51500 | 0 | On Track | No
M-0107 | P-1022 | Design approval | Design | 2026-12-04 | 2026-12-04 |  | Yes | 20% | 103000 | 0 | On Track | No
M-0108 | P-1022 | Build complete | Build | 2027-03-18 | 2027-03-18 |  | Yes | 30% | 154500 | 0 | On Track | No
M-0109 | P-1022 | UAT sign-off | Test | 2027-05-04 | 2027-05-04 |  | Yes | 20% | 103000 | 0 | On Track | No
M-0110 | P-1022 | Go-live | Deploy | 2027-05-28 | 2027-05-28 |  | Yes | 20% | 103000 | 0 | On Track | No
M-0111 | P-1023 | Discovery sign-off | Discovery | 2026-11-25 | 2026-11-25 |  | No | 0% | 0 | 0 | On Track | No
M-0112 | P-1023 | Design approval | Design | 2027-01-01 | 2027-01-01 |  | No | 0% | 0 | 0 | On Track | No
M-0113 | P-1023 | Build complete | Build | 2027-04-15 | 2027-04-15 |  | No | 0% | 0 | 0 | On Track | No
M-0114 | P-1023 | UAT sign-off | Test | 2027-06-01 | 2027-06-01 |  | No | 0% | 0 | 0 | On Track | No
M-0115 | P-1023 | Go-live | Deploy | 2027-06-25 | 2027-06-25 |  | No | 0% | 0 | 0 | On Track | No
M-0116 | P-1024 | Discovery sign-off | Discovery | 2027-02-09 | 2027-02-09 |  | Yes | 10% | 109000 | 0 | On Track | No
M-0117 | P-1024 | Design approval | Design | 2027-03-26 | 2027-03-26 |  | Yes | 20% | 218000 | 0 | On Track | No
M-0118 | P-1024 | Build complete | Build | 2027-08-02 | 2027-08-02 |  | Yes | 30% | 327000 | 0 | On Track | No
M-0119 | P-1024 | UAT sign-off | Test | 2027-09-29 | 2027-09-29 |  | Yes | 20% | 218000 | 0 | On Track | No
M-0120 | P-1024 | Go-live | Deploy | 2027-10-29 | 2027-10-29 |  | Yes | 20% | 218000 | 0 | On Track | No

## Invoices
InvoiceID | ProjectID | MilestoneID | InvoiceDate | Description | Amount | PaidDate | ClientName | PaymentTermsDays | DueDate | Status | DaysOutstanding | DaysOverdue | AgingBucket
INV-00001 | P-1019 | M-0091 | 2025-06-09 | Milestone: Discovery sign-off | 98500 | 2025-08-15 | Pinecrest University | 60 | 2025-08-08 | Paid | 67 | 0 | Paid
INV-00002 | P-1018 | M-0086 | 2025-06-23 | Milestone: Discovery sign-off | 62000 | 2025-07-30 | Summit Telecom | 45 | 2025-08-07 | Paid | 37 | 0 | Paid
INV-00003 | P-1018 | M-0087 | 2025-07-28 | Milestone: Design approval | 124000 | 2025-09-07 | Summit Telecom | 45 | 2025-09-11 | Paid | 41 | 0 | Paid
INV-00004 | P-1019 | M-0092 | 2025-07-31 | Milestone: Design approval | 197000 | 2025-10-04 | Pinecrest University | 60 | 2025-09-29 | Paid | 65 | 0 | Paid
INV-00005 | P-1014 |  | 2025-08-05 | Monthly retainer Jul 2025 | 80555.56 | 2025-11-01 | Harbourview Logistics | 45 | 2025-09-19 | Paid | 88 | 0 | Paid
INV-00006 | P-1014 |  | 2025-09-05 | Monthly retainer Aug 2025 | 80555.56 | 2025-12-08 | Harbourview Logistics | 45 | 2025-10-20 | Paid | 94 | 0 | Paid
INV-00007 | P-1013 | M-0061 | 2025-09-22 | Milestone: Discovery sign-off | 141500 | 2025-10-16 | Maple Ridge Financial | 30 | 2025-10-22 | Paid | 24 | 0 | Paid
INV-00008 | P-1003 |  | 2025-10-06 | T&M services Sep 2025 | 61135.69 | 2025-10-28 | Maple Ridge Financial | 30 | 2025-11-05 | Paid | 22 | 0 | Paid
INV-00009 | P-1014 |  | 2025-10-06 | Monthly retainer Sep 2025 | 80555.56 | 2025-11-13 | Harbourview Logistics | 45 | 2025-11-20 | Paid | 38 | 0 | Paid
INV-00010 | P-1018 | M-0088 | 2025-10-23 | Milestone: Build complete | 186000 | 2025-12-15 | Summit Telecom | 45 | 2025-12-07 | Paid | 53 | 0 | Paid
INV-00011 | P-1003 |  | 2025-11-05 | T&M services Oct 2025 | 70760.07 | 2025-12-15 | Maple Ridge Financial | 30 | 2025-12-05 | Paid | 40 | 0 | Paid
INV-00012 | P-1014 |  | 2025-11-05 | Monthly retainer Oct 2025 | 80555.56 | 2025-12-15 | Harbourview Logistics | 45 | 2025-12-20 | Paid | 40 | 0 | Paid
INV-00013 | P-1020 |  | 2025-11-05 | T&M services Oct 2025 | 42424.04 | 2025-12-16 | Granite Manufacturing | 45 | 2025-12-20 | Paid | 41 | 0 | Paid
INV-00014 | P-1006 | M-0026 | 2025-11-13 | Milestone: Discovery sign-off | 94000 | 2026-01-22 | Aurora Retail Group | 60 | 2026-01-12 | Paid | 70 | 0 | Paid
INV-00015 | P-1018 | M-0089 | 2025-12-01 | Milestone: UAT sign-off | 124000 | 2026-01-14 | Summit Telecom | 45 | 2026-01-15 | Paid | 44 | 0 | Paid
INV-00016 | P-1013 | M-0062 | 2025-12-04 | Milestone: Design approval | 283000 | 2026-01-14 | Maple Ridge Financial | 30 | 2026-01-03 | Paid | 41 | 0 | Paid
INV-00017 | P-1003 |  | 2025-12-05 | T&M services Nov 2025 | 68573.23 | 2025-12-28 | Maple Ridge Financial | 30 | 2026-01-04 | Paid | 23 | 0 | Paid
INV-00018 | P-1014 |  | 2025-12-05 | Monthly retainer Nov 2025 | 80555.56 | 2026-01-19 | Harbourview Logistics | 45 | 2026-01-19 | Paid | 45 | 0 | Paid
INV-00019 | P-1020 |  | 2025-12-05 | T&M services Nov 2025 | 57923.36 | 2026-01-15 | Granite Manufacturing | 45 | 2026-01-19 | Paid | 41 | 0 | Paid
INV-00020 | P-1001 | M-0001 | 2025-12-12 | Milestone: Discovery sign-off | 110000 | 2026-01-22 | Northgate Health Network | 45 | 2026-01-26 | Paid | 41 | 0 | Paid
INV-00021 | P-1018 | M-0090 | 2025-12-22 | Milestone: Go-live | 124000 | 2026-02-13 | Summit Telecom | 45 | 2026-02-05 | Paid | 53 | 0 | Paid
INV-00022 | P-1019 | M-0093 | 2025-12-29 | Milestone: Build complete | 295500 | 2026-02-20 | Pinecrest University | 60 | 2026-02-27 | Paid | 53 | 0 | Paid
INV-00023 | P-1010 | M-0046 | 2026-01-01 | Milestone: Discovery sign-off | 73500 | 2026-03-04 | Bluewater Municipal Services | 60 | 2026-03-02 | Paid | 62 | 0 | Paid
INV-00024 | P-1003 |  | 2026-01-05 | T&M services Dec 2025 | 99312.28 | 2026-01-26 | Maple Ridge Financial | 30 | 2026-02-04 | Paid | 21 | 0 | Paid
INV-00025 | P-1014 |  | 2026-01-05 | Monthly retainer Dec 2025 | 80555.56 | 2026-03-01 | Harbourview Logistics | 45 | 2026-02-19 | Paid | 55 | 0 | Paid
INV-00026 | P-1020 |  | 2026-01-05 | T&M services Dec 2025 | 89213.9 | 2026-02-24 | Granite Manufacturing | 45 | 2026-02-19 | Paid | 50 | 0 | Paid
INV-00027 | P-1006 | M-0027 | 2026-01-12 | Milestone: Design approval | 188000 | 2026-03-11 | Aurora Retail Group | 60 | 2026-03-13 | Paid | 58 | 0 | Paid
INV-00028 | P-1003 |  | 2026-02-05 | T&M services Jan 2026 | 92039.18 | 2026-02-28 | Maple Ridge Financial | 30 | 2026-03-07 | Paid | 23 | 0 | Paid
INV-00029 | P-1008 |  | 2026-02-05 | T&M services Jan 2026 | 82799.25 | 2026-03-28 | Summit Telecom | 45 | 2026-03-22 | Paid | 51 | 0 | Paid
INV-00030 | P-1014 |  | 2026-02-05 | Monthly retainer Jan 2026 | 80555.56 | 2026-04-01 | Harbourview Logistics | 45 | 2026-03-22 | Paid | 55 | 0 | Paid
INV-00031 | P-1020 |  | 2026-02-05 | T&M services Jan 2026 | 86768.78 | 2026-03-13 | Granite Manufacturing | 45 | 2026-03-22 | Paid | 36 | 0 | Paid
INV-00032 | P-1001 | M-0002 | 2026-02-09 | Milestone: Design approval | 220000 | 2026-03-27 | Northgate Health Network | 45 | 2026-03-26 | Paid | 46 | 0 | Paid
INV-00033 | P-1002 | M-0006 | 2026-02-16 | Milestone: Discovery sign-off | 68500 | 2026-03-21 | Crestline Insurance | 30 | 2026-03-18 | Paid | 33 | 0 | Paid
INV-00034 | P-1017 | M-0081 | 2026-02-19 | Milestone: Discovery sign-off | 46500 | 2026-05-15 | Aurora Retail Group | 60 | 2026-04-20 | Paid | 85 | 0 | Paid
INV-00035 | P-1010 | M-0047 | 2026-02-20 | Milestone: Design approval | 147000 | 2026-05-16 | Bluewater Municipal Services | 60 | 2026-04-21 | Paid | 85 | 0 | Paid
INV-00036 | P-1003 |  | 2026-03-05 | T&M services Feb 2026 | 90055.45 | 2026-03-29 | Maple Ridge Financial | 30 | 2026-04-04 | Paid | 24 | 0 | Paid
INV-00037 | P-1008 |  | 2026-03-05 | T&M services Feb 2026 | 83036.53 | 2026-04-17 | Summit Telecom | 45 | 2026-04-19 | Paid | 43 | 0 | Paid
INV-00038 | P-1011 |  | 2026-03-05 | T&M services Feb 2026 | 25018.08 | 2026-04-13 | Evergreen Pharma | 45 | 2026-04-19 | Paid | 39 | 0 | Paid
INV-00039 | P-1014 |  | 2026-03-05 | Monthly retainer Feb 2026 | 80555.56 | 2026-04-11 | Harbourview Logistics | 45 | 2026-04-19 | Paid | 37 | 0 | Paid
INV-00040 | P-1020 |  | 2026-03-05 | T&M services Feb 2026 | 81169.46 | 2026-04-13 | Granite Manufacturing | 45 | 2026-04-19 | Paid | 39 | 0 | Paid
INV-00041 | P-1019 | M-0094 | 2026-03-09 | Milestone: UAT sign-off | 197000 | 2026-05-03 | Pinecrest University | 60 | 2026-05-08 | Paid | 55 | 0 | Paid
INV-00042 | P-1004 | M-0016 | 2026-03-13 | Milestone: Discovery sign-off | 115500 | 2026-05-01 | Harbourview Logistics | 45 | 2026-04-27 | Paid | 49 | 0 | Paid
INV-00043 | P-1021 | M-0101 | 2026-03-19 | Milestone: Discovery sign-off | 62500 | 2026-04-16 | Lakeshore Energy | 30 | 2026-04-18 | Paid | 28 | 0 | Paid
INV-00044 | P-1003 |  | 2026-04-06 | T&M services Mar 2026 | 93591.54 | 2026-05-06 | Maple Ridge Financial | 30 | 2026-05-06 | Paid | 30 | 0 | Paid
INV-00045 | P-1008 |  | 2026-04-06 | T&M services Mar 2026 | 115575.99 | 2026-05-31 | Summit Telecom | 45 | 2026-05-21 | Paid | 55 | 0 | Paid
INV-00046 | P-1011 |  | 2026-04-06 | T&M services Mar 2026 | 46269.28 | 2026-05-25 | Evergreen Pharma | 45 | 2026-05-21 | Paid | 49 | 0 | Paid
INV-00047 | P-1014 |  | 2026-04-06 | Monthly retainer Mar 2026 | 80555.56 | 2026-05-26 | Harbourview Logistics | 45 | 2026-05-21 | Paid | 50 | 0 | Paid
INV-00048 | P-1020 |  | 2026-04-06 | T&M services Mar 2026 | 85909.09 | 2026-05-23 | Granite Manufacturing | 45 | 2026-05-21 | Paid | 47 | 0 | Paid
INV-00049 | P-1017 | M-0082 | 2026-04-09 | Milestone: Design approval (disputed) | 93000 |  | Aurora Retail Group | 60 | 2026-06-08 | Overdue | 155 | 95 | 60+
INV-00050 | P-1005 | M-0021 | 2026-04-13 | Milestone: Discovery sign-off | 74000 | 2026-05-22 | Ironbridge Capital | 30 | 2026-05-13 | Paid | 39 | 0 | Paid
INV-00051 | P-1019 | M-0095 | 2026-04-13 | Milestone: Go-live | 197000 | 2026-06-05 | Pinecrest University | 60 | 2026-06-12 | Paid | 53 | 0 | Paid
INV-00052 | P-1002 | M-0007 | 2026-04-16 | Milestone: Design approval | 137000 | 2026-05-14 | Crestline Insurance | 30 | 2026-05-16 | Paid | 28 | 0 | Paid
INV-00053 | P-1015 | M-0071 | 2026-05-04 | Milestone: Discovery sign-off | 131500 | 2026-05-29 | Crestline Insurance | 30 | 2026-06-03 | Paid | 25 | 0 | Paid
INV-00054 | P-1003 |  | 2026-05-05 | T&M services Apr 2026 | 107584.78 | 2026-06-10 | Maple Ridge Financial | 30 | 2026-06-04 | Paid | 36 | 0 | Paid
INV-00055 | P-1008 |  | 2026-05-05 | T&M services Apr 2026 | 88004.05 | 2026-06-14 | Summit Telecom | 45 | 2026-06-19 | Paid | 40 | 0 | Paid
INV-00056 | P-1011 |  | 2026-05-05 | T&M services Apr 2026 | 49478.04 | 2026-06-28 | Evergreen Pharma | 45 | 2026-06-19 | Paid | 54 | 0 | Paid
INV-00057 | P-1014 |  | 2026-05-05 | Monthly retainer Apr 2026 | 80555.56 | 2026-08-06 | Harbourview Logistics | 45 | 2026-06-19 | Paid | 93 | 0 | Paid
INV-00058 | P-1016 |  | 2026-05-05 | T&M services Apr 2026 | 28829.44 | 2026-06-18 | Harbourview Logistics | 45 | 2026-06-19 | Paid | 44 | 0 | Paid
INV-00059 | P-1020 |  | 2026-05-05 | T&M services Apr 2026 | 74734.19 | 2026-06-26 | Granite Manufacturing | 45 | 2026-06-19 | Paid | 52 | 0 | Paid
INV-00060 | P-1004 | M-0017 | 2026-05-11 | Milestone: Design approval | 231000 | 2026-07-02 | Harbourview Logistics | 45 | 2026-06-25 | Paid | 52 | 0 | Paid
INV-00061 | P-1007 | M-0031 | 2026-05-14 | Milestone: Discovery sign-off | 97000 | 2026-07-17 | Pinecrest University | 60 | 2026-07-13 | Paid | 64 | 0 | Paid
INV-00062 | P-1021 | M-0102 | 2026-05-15 | Milestone: Design approval | 125000 | 2026-06-22 | Lakeshore Energy | 30 | 2026-06-14 | Paid | 38 | 0 | Paid
INV-00063 | P-1009 | M-0041 | 2026-05-29 | Milestone: Discovery sign-off | 53500 | 2026-07-21 | Granite Manufacturing | 45 | 2026-07-13 | Paid | 53 | 0 | Paid
INV-00064 | P-1003 |  | 2026-06-05 | T&M services May 2026 | 95906.36 | 2026-07-11 | Maple Ridge Financial | 30 | 2026-07-05 | Paid | 36 | 0 | Paid
INV-00065 | P-1008 |  | 2026-06-05 | T&M services May 2026 | 86717.19 | 2026-07-28 | Summit Telecom | 45 | 2026-07-20 | Paid | 53 | 0 | Paid
INV-00066 | P-1011 |  | 2026-06-05 | T&M services May 2026 | 64239.52 | 2026-07-27 | Evergreen Pharma | 45 | 2026-07-20 | Paid | 52 | 0 | Paid
INV-00067 | P-1014 |  | 2026-06-05 | Monthly retainer May 2026 | 80555.56 |  | Harbourview Logistics | 45 | 2026-07-20 | Overdue | 98 | 53 | 31-60
INV-00068 | P-1016 |  | 2026-06-05 | T&M services May 2026 | 43539.34 |  | Harbourview Logistics | 45 | 2026-07-20 | Overdue | 98 | 53 | 31-60
INV-00069 | P-1020 |  | 2026-06-05 | T&M services May 2026 | 55129.52 | 2026-07-27 | Granite Manufacturing | 45 | 2026-07-20 | Paid | 52 | 0 | Paid
INV-00070 | P-1005 | M-0022 | 2026-06-18 | Milestone: Design approval | 148000 | 2026-07-23 | Ironbridge Capital | 30 | 2026-07-18 | Paid | 35 | 0 | Paid
INV-00071 | P-1006 | M-0028 | 2026-06-19 | Milestone: Build complete (disputed) | 282000 |  | Aurora Retail Group | 60 | 2026-08-18 | Overdue | 84 | 24 | 1-30
INV-00072 | P-1012 | M-0056 | 2026-06-22 | Milestone: Discovery sign-off | 51000 | 2026-07-25 | Lakeshore Energy | 30 | 2026-07-22 | Paid | 33 | 0 | Paid
INV-00073 | P-1013 | M-0063 | 2026-06-29 | Milestone: Build complete | 424500 | 2026-07-26 | Maple Ridge Financial | 30 | 2026-07-29 | Paid | 27 | 0 | Paid
INV-00074 | P-1009 | M-0042 | 2026-07-03 | Milestone: Design approval | 107000 | 2026-08-12 | Granite Manufacturing | 45 | 2026-08-17 | Paid | 40 | 0 | Paid
INV-00075 | P-1003 |  | 2026-07-06 | T&M services Jun 2026 | 96126.2 | 2026-07-31 | Maple Ridge Financial | 30 | 2026-08-05 | Paid | 25 | 0 | Paid
INV-00076 | P-1008 |  | 2026-07-06 | T&M services Jun 2026 | 98072.51 | 2026-08-30 | Summit Telecom | 45 | 2026-08-20 | Paid | 55 | 0 | Paid
INV-00077 | P-1011 |  | 2026-07-06 | T&M services Jun 2026 | 78054.13 | 2026-08-11 | Evergreen Pharma | 45 | 2026-08-20 | Paid | 36 | 0 | Paid
INV-00078 | P-1014 |  | 2026-07-06 | Monthly retainer Jun 2026 | 80555.56 | 2026-08-15 | Harbourview Logistics | 45 | 2026-08-20 | Paid | 40 | 0 | Paid
INV-00079 | P-1016 |  | 2026-07-06 | T&M services Jun 2026 | 56206.39 | 2026-08-22 | Harbourview Logistics | 45 | 2026-08-20 | Paid | 47 | 0 | Paid
INV-00080 | P-1020 |  | 2026-07-06 | T&M services Jun 2026 | 2248 | 2026-08-11 | Granite Manufacturing | 45 | 2026-08-20 | Paid | 36 | 0 | Paid
INV-00081 | P-1007 | M-0032 | 2026-07-10 | Milestone: Design approval | 194000 |  | Pinecrest University | 60 | 2026-09-08 | Overdue | 63 | 3 | 1-30
INV-00082 | P-1010 | M-0048 | 2026-07-13 | Milestone: Build complete (disputed) | 220500 |  | Bluewater Municipal Services | 60 | 2026-09-11 | Outstanding | 60 | 0 | Current
INV-00083 | P-1001 | M-0003 | 2026-07-20 | Milestone: Build complete | 330000 | 2026-09-10 | Northgate Health Network | 45 | 2026-09-03 | Paid | 52 | 0 | Paid
INV-00084 | P-1015 | M-0072 | 2026-07-20 | Milestone: Design approval | 263000 | 2026-08-14 | Crestline Insurance | 30 | 2026-08-19 | Paid | 25 | 0 | Paid
INV-00085 | P-1012 | M-0057 | 2026-07-27 | Milestone: Design approval | 102000 | 2026-09-03 | Lakeshore Energy | 30 | 2026-08-26 | Paid | 38 | 0 | Paid
INV-00086 | P-1003 |  | 2026-08-05 | T&M services Jul 2026 | 96409.09 |  | Maple Ridge Financial | 30 | 2026-09-04 | Overdue | 37 | 7 | 1-30
INV-00087 | P-1008 |  | 2026-08-05 | T&M services Jul 2026 | 85330.33 | 2026-09-10 | Summit Telecom | 45 | 2026-09-19 | Paid | 36 | 0 | Paid
INV-00088 | P-1011 |  | 2026-08-05 | T&M services Jul 2026 | 79969.15 |  | Evergreen Pharma | 45 | 2026-09-19 | Outstanding | 37 | 0 | Current
INV-00089 | P-1014 |  | 2026-08-05 | Monthly retainer Jul 2026 | 80555.56 |  | Harbourview Logistics | 45 | 2026-09-19 | Outstanding | 37 | 0 | Current
INV-00090 | P-1016 |  | 2026-08-05 | T&M services Jul 2026 | 52100.79 |  | Harbourview Logistics | 45 | 2026-09-19 | Outstanding | 37 | 0 | Current
INV-00091 | P-1017 | M-0083 | 2026-08-21 | Milestone: Build complete | 139500 |  | Aurora Retail Group | 60 | 2026-10-20 | Outstanding | 21 | 0 | Current
INV-00092 | P-1006 | M-0029 | 2026-08-31 | Milestone: UAT sign-off | 188000 |  | Aurora Retail Group | 60 | 2026-10-30 | Outstanding | 11 | 0 | Current
INV-00093 | P-1003 |  | 2026-09-07 | T&M services Aug 2026 | 89764.58 |  | Maple Ridge Financial | 30 | 2026-10-07 | Outstanding | 4 | 0 | Current
INV-00094 | P-1008 |  | 2026-09-07 | T&M services Aug 2026 | 76883.12 |  | Summit Telecom | 45 | 2026-10-22 | Outstanding | 4 | 0 | Current
INV-00095 | P-1011 |  | 2026-09-07 | T&M services Aug 2026 | 72403.18 |  | Evergreen Pharma | 45 | 2026-10-22 | Outstanding | 4 | 0 | Current
INV-00096 | P-1014 |  | 2026-09-07 | Monthly retainer Aug 2026 | 80555.56 |  | Harbourview Logistics | 45 | 2026-10-22 | Outstanding | 4 | 0 | Current
INV-00097 | P-1016 |  | 2026-09-07 | T&M services Aug 2026 | 67572.99 |  | Harbourview Logistics | 45 | 2026-10-22 | Outstanding | 4 | 0 | Current
Formulas:
DueDate = [InvoiceDate]+[PaymentTermsDays]

## RAID
RAIDID | ProjectID | Type | Category | Title | Probability | Impact | CostExposure | OwnerID | Status | RaisedDate | TargetDate | Mitigation | OwnerName | RiskScore | Severity | ExpectedExposure | DaysOpen | PastTarget
R-0001 | P-1014 | Issue | Technical | Performance below NFR in load test | 5 | 2 | 15000 | E-0011 | Mitigating | 2025-08-29 | 2025-11-07 | Tuning sprint; caching layer | Chloe Reyes | 10 | High | 15000 | 378 | Yes
R-0002 | P-1003 | Risk | Vendor | Third-party API delivery delay | 2 | 4 | 32000 | E-0033 | Open | 2025-09-23 | 2025-11-25 | Mock services; contractual SLA escalation | Elijah Adeyemi | 8 | Medium | 12800 | 353 | Yes
R-0003 | P-1018 | Risk | Technical | Data quality in source systems | 1 | 2 | 53000 | E-0012 | Closed | 2025-10-19 | 2025-12-18 | Profiling + cleansing rules upfront | Mateo Bianchi | 2 | Low | 10600 | 0 | No
R-0004 | P-1020 | Risk | Technical | Data quality in source systems | 1 | 1 | 38000 | E-0006 | Closed | 2025-11-05 | 2026-01-03 | Profiling + cleansing rules upfront | Noah Rahimi | 1 | Low | 7600 | 0 | No
R-0005 | P-1013 | Risk | Security | Pen-test findings delay go-live | 3 | 1 | 15000 | E-0014 | Open | 2025-11-07 | 2026-01-08 | Early threat modelling; shift-left scans | Lucas Okoro | 3 | Low | 9000 | 308 | Yes
R-0006 | P-1010 | Risk | Vendor | Third-party API delivery delay | 2 | 5 | 89000 | E-0018 | Closed | 2025-11-11 | 2026-01-13 | Mock services; contractual SLA escalation | Ravi Gagnon | 10 | High | 35600 | 0 | No
R-0007 | P-1001 | Risk | Scope | Scope creep from stakeholder requests | 3 | 1 | 57000 | E-0023 | Closed | 2025-11-14 | 2025-12-31 | Enforce CR process; weekly scope review | Yuki Wright | 3 | Low | 34200 | 0 | No
R-0008 | P-1019 | Risk | Scope | Scope creep from stakeholder requests | 3 | 2 | 36000 | E-0017 | Closed | 2025-11-28 | 2026-01-14 | Enforce CR process; weekly scope review | Amara Martin | 6 | Medium | 21600 | 0 | No
R-0009 | P-1018 | Risk | Technical | Legacy integration undocumented | 2 | 2 | 15000 | E-0012 | Closed | 2025-12-16 | 2026-02-28 | Spike to reverse-engineer; vendor SME | Mateo Bianchi | 4 | Low | 6000 | 0 | No
R-0010 | P-1019 | Risk | Technical | Legacy integration undocumented | 3 | 1 | 40000 | E-0025 | Closed | 2025-12-20 | 2026-02-12 | Spike to reverse-engineer; vendor SME | Kwame Malik | 3 | Low | 24000 | 0 | No
R-0011 | P-1010 | Risk | Schedule | UAT window conflicts with client freeze | 3 | 4 | 107000 | E-0046 | Open | 2025-12-31 | 2026-02-26 | Negotiate early UAT slot | Ines Morales | 12 | High | 64200 | 254 | Yes
R-0012 | P-1013 | Risk | Schedule | UAT window conflicts with client freeze | 3 | 2 | 31000 | E-0063 | Closed | 2026-01-10 | 2026-02-12 | Negotiate early UAT slot | Callum Dubois | 6 | Medium | 18600 | 0 | No
R-0013 | P-1006 | Issue | Technical | Performance below NFR in load test | 5 | 3 | 56000 | E-0026 | Closed | 2026-01-12 | 2026-03-10 | Tuning sprint; caching layer | Leah Haddad | 15 | Critical | 56000 | 0 | No
R-0014 | P-1002 | Risk | Financial | FX exposure on USD licences | 3 | 4 | 44000 | E-0004 | Open | 2026-01-13 | 2026-02-15 | Lock pricing; hedge with finance | Liam Roy | 12 | High | 26400 | 241 | Yes
R-0015 | P-1010 | Risk | Technical | Data quality in source systems | 2 | 4 | 123000 | E-0030 | Mitigating | 2026-01-15 | 2026-03-14 | Profiling + cleansing rules upfront | Sofia Hassan | 8 | Medium | 49200 | 239 | Yes
R-0016 | P-1021 | Assumption | Scope | Client provides test data by Build | 2 | 2 | 28000 | E-0062 | Mitigating | 2026-01-20 | 2026-03-10 | Confirm in steering minutes | Mariam Brooks | 4 | Low | 11200 | 234 | Yes
R-0017 | P-1021 | Risk | Financial | FX exposure on USD licences | 3 | 1 | 56000 | E-0045 | Mitigating | 2026-01-25 | 2026-04-03 | Lock pricing; hedge with finance | Hugo Ahmed | 3 | Low | 33600 | 229 | Yes
R-0018 | P-1017 | Risk | Technical | Data quality in source systems | 3 | 3 | 36000 | E-0017 | Mitigating | 2026-01-28 | 2026-02-16 | Profiling + cleansing rules upfront | Amara Martin | 9 | Medium | 21600 | 226 | Yes
R-0019 | P-1021 | Dependency | Vendor | Client identity platform upgrade | 1 | 2 | 31000 | E-0026 | Open | 2026-01-28 | 2026-02-21 | Track in joint RAID; weekly sync | Leah Haddad | 2 | Low | 6200 | 226 | Yes
R-0020 | P-1002 | Issue | Technical | Performance below NFR in load test | 5 | 4 | 35000 | E-0032 | Closed | 2026-02-02 | 2026-02-20 | Tuning sprint; caching layer | Maya Osei | 20 | Critical | 35000 | 0 | No
R-0021 | P-1003 | Issue | Technical | Performance below NFR in load test | 5 | 3 | 51000 | E-0033 | Closed | 2026-02-02 | 2026-03-22 | Tuning sprint; caching layer | Elijah Adeyemi | 15 | Critical | 51000 | 0 | No
R-0022 | P-1011 | Risk | Technical | Data quality in source systems | 1 | 2 | 46000 | E-0006 | Closed | 2026-02-06 | 2026-03-07 | Profiling + cleansing rules upfront | Noah Rahimi | 2 | Low | 9200 | 0 | No
R-0023 | P-1017 | Risk | Financial | FX exposure on USD licences | 3 | 2 | 127000 | E-0027 | Closed | 2026-02-06 | 2026-04-07 | Lock pricing; hedge with finance | Omar Bose | 6 | Medium | 76200 | 0 | No
R-0024 | P-1005 | Risk | Financial | FX exposure on USD licences | 2 | 5 | 99000 | E-0046 | Open | 2026-02-10 | 2026-04-17 | Lock pricing; hedge with finance | Ines Morales | 10 | High | 39600 | 213 | Yes
R-0025 | P-1001 | Issue | Resource | Client SME availability limited | 5 | 3 | 35000 | E-0003 | Closed | 2026-02-18 | 2026-04-22 | Escalated to sponsor; fixed office hours | Aisha Tremblay | 15 | Critical | 35000 | 0 | No
R-0026 | P-1013 | Issue | Schedule | Environment provisioning delayed | 5 | 3 | 41000 | E-0019 | Closed | 2026-02-25 | 2026-05-02 | Escalated with client IT | Emma Leblanc | 15 | Critical | 41000 | 0 | No
R-0027 | P-1008 | Risk | Technical | Legacy integration undocumented | 3 | 1 | 46000 | E-0060 | Closed | 2026-02-27 | 2026-03-16 | Spike to reverse-engineer; vendor SME | Priyanka Tanaka | 3 | Low | 27600 | 0 | No
R-0028 | P-1003 | Dependency | Vendor | Client identity platform upgrade | 2 | 5 | 64000 | E-0033 | Open | 2026-03-17 | 2026-04-27 | Track in joint RAID; weekly sync | Elijah Adeyemi | 10 | High | 25600 | 178 | Yes
R-0029 | P-1005 | Risk | Scope | Scope creep from stakeholder requests | 2 | 3 | 11000 | E-0046 | Closed | 2026-03-20 | 2026-04-25 | Enforce CR process; weekly scope review | Ines Morales | 6 | Medium | 4400 | 0 | No
R-0030 | P-1010 | Issue | Schedule | Environment provisioning delayed | 5 | 2 | 173000 | E-0030 | Mitigating | 2026-03-23 | 2026-05-02 | Escalated with client IT | Sofia Hassan | 10 | High | 173000 | 172 | Yes
R-0031 | P-1015 | Risk | Security | Pen-test findings delay go-live | 3 | 3 | 10000 | E-0013 | Open | 2026-04-11 | 2026-05-04 | Early threat modelling; shift-left scans | Hana Clarke | 9 | Medium | 6000 | 153 | Yes
R-0032 | P-1004 | Dependency | Vendor | Client identity platform upgrade | 3 | 2 | 54000 | E-0006 | Mitigating | 2026-04-15 | 2026-05-29 | Track in joint RAID; weekly sync | Noah Rahimi | 6 | Medium | 32400 | 149 | Yes
R-0033 | P-1015 | Risk | Financial | FX exposure on USD licences | 3 | 3 | 12000 | E-0024 | Closed | 2026-04-20 | 2026-06-19 | Lock pricing; hedge with finance | Isabel Gill | 9 | Medium | 7200 | 0 | No
R-0034 | P-1008 | Risk | Vendor | Third-party API delivery delay | 3 | 3 | 10000 | E-0029 | Mitigating | 2026-04-21 | 2026-05-24 | Mock services; contractual SLA escalation | Tariq Obi | 9 | Medium | 6000 | 143 | Yes
R-0035 | P-1016 | Assumption | Scope | Client provides test data by Build | 2 | 1 | 48000 | E-0043 | Closed | 2026-04-30 | 2026-06-02 | Confirm in steering minutes | Victor Chen | 2 | Low | 19200 | 0 | No
R-0036 | P-1020 | Risk | Vendor | Third-party API delivery delay | 1 | 1 | 16000 | E-0037 | Closed | 2026-05-01 | 2026-06-03 | Mock services; contractual SLA escalation | Imran Ivanova | 1 | Low | 3200 | 0 | No
R-0037 | P-1015 | Risk | Resource | Key developer attrition risk | 2 | 1 | 56000 | E-0040 | Closed | 2026-05-08 | 2026-05-27 | Cross-train backup; retention conversation | Leila Nguyen | 2 | Low | 22400 | 0 | No
R-0038 | P-1017 | Risk | Schedule | UAT window conflicts with client freeze | 4 | 4 | 74000 | E-0005 | Open | 2026-05-09 | 2026-07-14 | Negotiate early UAT slot | Mei Fraser | 16 | Critical | 59200 | 125 | Yes
R-0039 | P-1007 | Risk | Resource | Key developer attrition risk | 3 | 1 | 13000 | E-0008 | Mitigating | 2026-05-14 | 2026-07-20 | Cross-train backup; retention conversation | Ethan Park | 3 | Low | 7800 | 120 | Yes
R-0040 | P-1009 | Risk | Financial | FX exposure on USD licences | 3 | 3 | 51000 | E-0005 | Open | 2026-05-14 | 2026-06-28 | Lock pricing; hedge with finance | Mei Fraser | 9 | Medium | 30600 | 120 | Yes
R-0041 | P-1010 | Assumption | Scope | Client provides test data by Build | 4 | 4 | 135000 | E-0007 | Closed | 2026-05-23 | 2026-06-28 | Confirm in steering minutes | Fatima Cohen | 16 | Critical | 108000 | 0 | No
R-0042 | P-1006 | Issue | Resource | Client SME availability limited | 5 | 2 | 21000 | E-0035 | Open | 2026-05-28 | 2026-07-02 | Escalated to sponsor; fixed office hours | Felix Singh | 10 | High | 21000 | 106 | Yes
R-0043 | P-1009 | Issue | Technical | Performance below NFR in load test | 5 | 3 | 40000 | E-0028 | Open | 2026-06-01 | 2026-07-15 | Tuning sprint; caching layer | Grace Chowdhury | 15 | Critical | 40000 | 102 | Yes
R-0044 | P-1006 | Risk | Security | Pen-test findings delay go-live | 2 | 3 | 12000 | E-0035 | Closed | 2026-06-04 | 2026-08-04 | Early threat modelling; shift-left scans | Felix Singh | 6 | Medium | 4800 | 0 | No
R-0045 | P-1012 | Risk | Schedule | UAT window conflicts with client freeze | 1 | 3 | 12000 | E-0040 | Closed | 2026-06-08 | 2026-07-24 | Negotiate early UAT slot | Leila Nguyen | 3 | Low | 2400 | 0 | No
R-0046 | P-1005 | Dependency | Vendor | Client identity platform upgrade | 4 | 3 | 143000 | E-0007 | Mitigating | 2026-06-13 | 2026-08-05 | Track in joint RAID; weekly sync | Fatima Cohen | 12 | High | 114400 | 90 | Yes
R-0047 | P-1014 | Issue | Schedule | Environment provisioning delayed | 5 | 3 | 40000 | E-0061 | Open | 2026-06-15 | 2026-08-21 | Escalated with client IT | Jonah Lee | 15 | Critical | 40000 | 88 | Yes
R-0048 | P-1002 | Risk | Vendor | Third-party API delivery delay | 3 | 4 | 31000 | E-0024 | Mitigating | 2026-06-16 | 2026-07-03 | Mock services; contractual SLA escalation | Isabel Gill | 12 | High | 18600 | 87 | Yes
R-0049 | P-1006 | Risk | Technical | Data quality in source systems | 1 | 3 | 23000 | E-0035 | Closed | 2026-06-16 | 2026-07-11 | Profiling + cleansing rules upfront | Felix Singh | 3 | Low | 4600 | 0 | No
R-0050 | P-1007 | Risk | Technical | Legacy integration undocumented | 3 | 3 | 25000 | E-0063 | Mitigating | 2026-06-19 | 2026-07-31 | Spike to reverse-engineer; vendor SME | Callum Dubois | 9 | Medium | 15000 | 84 | Yes
R-0051 | P-1005 | Risk | Resource | Key developer attrition risk | 4 | 3 | 31000 | E-0012 | Closed | 2026-06-28 | 2026-09-09 | Cross-train backup; retention conversation | Mateo Bianchi | 12 | High | 24800 | 0 | No
R-0052 | P-1017 | Risk | Security | Pen-test findings delay go-live | 3 | 2 | 85000 | E-0017 | Open | 2026-06-29 | 2026-08-20 | Early threat modelling; shift-left scans | Amara Martin | 6 | Medium | 51000 | 74 | Yes
R-0053 | P-1015 | Risk | Schedule | UAT window conflicts with client freeze | 3 | 1 | 39000 | E-0015 | Mitigating | 2026-07-03 | 2026-08-29 | Negotiate early UAT slot | Zara Vasquez | 3 | Low | 23400 | 70 | Yes
R-0054 | P-1005 | Risk | Schedule | UAT window conflicts with client freeze | 4 | 2 | 51000 | E-0052 | Open | 2026-07-05 | 2026-09-11 | Negotiate early UAT slot | Ayesha Schmidt | 8 | Medium | 40800 | 68 | No
R-0055 | P-1002 | Dependency | Vendor | Client identity platform upgrade | 4 | 5 | 59000 | E-0024 | Mitigating | 2026-07-14 | 2026-09-20 | Track in joint RAID; weekly sync | Isabel Gill | 20 | Critical | 47200 | 59 | No
R-0056 | P-1008 | Risk | Resource | Key developer attrition risk | 1 | 3 | 57000 | E-0010 | Closed | 2026-07-21 | 2026-08-12 | Cross-train backup; retention conversation | Arjun Baptiste | 3 | Low | 11400 | 0 | No
R-0057 | P-1017 | Issue | Resource | Client SME availability limited | 5 | 2 | 167000 | E-0043 | Mitigating | 2026-07-27 | 2026-09-07 | Escalated to sponsor; fixed office hours | Victor Chen | 10 | High | 167000 | 46 | Yes
R-0058 | P-1016 | Risk | Vendor | Third-party API delivery delay | 3 | 2 | 53000 | E-0062 | Open | 2026-08-04 | 2026-09-14 | Mock services; contractual SLA escalation | Mariam Brooks | 6 | Medium | 31800 | 38 | No
R-0059 | P-1004 | Issue | Technical | Performance below NFR in load test | 5 | 4 | 33000 | E-0025 | Open | 2026-08-08 | 2026-10-14 | Tuning sprint; caching layer | Kwame Malik | 20 | Critical | 33000 | 34 | No
R-0060 | P-1012 | Assumption | Scope | Client provides test data by Build | 2 | 3 | 36000 | E-0011 | Closed | 2026-08-09 | 2026-10-20 | Confirm in steering minutes | Chloe Reyes | 6 | Medium | 14400 | 0 | No
R-0061 | P-1003 | Risk | Scope | Scope creep from stakeholder requests | 2 | 5 | 176000 | E-0005 | Mitigating | 2026-08-16 | 2026-08-31 | Enforce CR process; weekly scope review | Mei Fraser | 10 | High | 70400 | 26 | Yes
R-0062 | P-1013 | Issue | Technical | Performance below NFR in load test | 5 | 3 | 35000 | E-0028 | Closed | 2026-08-20 | 2026-10-17 | Tuning sprint; caching layer | Grace Chowdhury | 15 | Critical | 35000 | 0 | No
R-0063 | P-1011 | Risk | Resource | Key developer attrition risk | 3 | 1 | 42000 | E-0039 | Open | 2026-08-27 | 2026-09-25 | Cross-train backup; retention conversation | Theo Siddiqui | 3 | Low | 25200 | 15 | No
R-0064 | P-1002 | Risk | Technical | Legacy integration undocumented | 4 | 5 | 17000 | E-0004 | Mitigating | 2026-09-01 | 2026-10-24 | Spike to reverse-engineer; vendor SME | Liam Roy | 20 | Critical | 13600 | 10 | No
R-0065 | P-1017 | Assumption | Scope | Client provides test data by Build | 4 | 2 | 112000 | E-0005 | Mitigating | 2026-09-05 | 2026-11-10 | Confirm in steering minutes | Mei Fraser | 8 | Medium | 89600 | 6 | No
R-0066 | P-1022 | Risk | Vendor | Third-party API delivery delay | 2 | 3 | 12000 | E-0035 | Mitigating | 2026-09-08 | 2026-11-08 | Mock services; contractual SLA escalation | Felix Singh | 6 | Medium | 4800 | 3 | No
R-0067 | P-1022 | Dependency | Vendor | Client identity platform upgrade | 3 | 2 | 22000 | E-0063 | Open | 2026-09-08 | 2026-10-01 | Track in joint RAID; weekly sync | Callum Dubois | 6 | Medium | 13200 | 3 | No
R-0068 | P-1023 | Risk | Schedule | UAT window conflicts with client freeze | 3 | 3 | 17000 | E-0031 | Closed | 2026-09-08 | 2026-09-27 | Negotiate early UAT slot | Jin Alvarez | 9 | Medium | 10200 | 0 | No
R-0069 | P-1023 | Risk | Technical | Legacy integration undocumented | 1 | 2 | 55000 | E-0054 | Closed | 2026-09-08 | 2026-10-11 | Spike to reverse-engineer; vendor SME | Lina Lindgren | 2 | Low | 11000 | 0 | No
R-0070 | P-1024 | Dependency | Vendor | Client identity platform upgrade | 2 | 3 | 12000 | E-0063 | Closed | 2026-09-08 | 2026-10-09 | Track in joint RAID; weekly sync | Callum Dubois | 6 | Medium | 4800 | 0 | No
R-0071 | P-1024 | Risk | Schedule | UAT window conflicts with client freeze | 3 | 2 | 58000 | E-0032 | Closed | 2026-09-08 | 2026-10-07 | Negotiate early UAT slot | Maya Osei | 6 | Medium | 34800 | 0 | No
R-0072 | P-1005 | Issue | Schedule | Environment provisioning delayed | 5 | 2 | 143000 | E-0049 | Open | 2026-09-10 | 2026-11-05 | Escalated with client IT | Bilal Novak | 10 | High | 143000 | 1 | No

## ChangeRequests
CRID | ProjectID | Title | CRType | RaisedDate | RaisedByID | Status | RevenueImpact | CostImpact | ScheduleImpactDays | DecisionDate | DecisionBy | RaisedBy | MarginImpact | MarginEffect | IsPending | DaysInReview
CR-001 | P-1001 | WCAG 2.2 accessibility remediation | Scope | 2026-03-09 | E-0003 | Approved | 35000 | 22000 | 10 | 2026-03-24 | Helena Marsh | Aisha Tremblay | 13000 | Accretive | No | 15
CR-002 | P-1002 | Add auto-glass claim type | Scope | 2026-04-14 | E-0004 | Approved | 85000 | 70000 | 21 | 2026-05-05 | Helena Marsh | Liam Roy | 15000 | Accretive | No | 21
CR-003 | P-1002 | Legacy mainframe interface rework | Technical | 2026-07-20 | E-0004 | Submitted | 0 | 60000 | 14 |  |  | Liam Roy | -60000 | Erodes margin | Yes | 53
CR-004 | P-1003 | Add real-time streaming ingestion | Scope | 2026-02-02 | E-0005 | Approved | 180000 | 110000 | 30 | 2026-02-27 | Helena Marsh | Mei Fraser | 70000 | Accretive | No | 25
CR-005 | P-1003 | Extend data quality rules library | Scope | 2026-08-04 | E-0005 | Draft | 45000 | 30000 | 7 |  |  | Mei Fraser | 15000 | Accretive | Yes | 38
CR-006 | P-1004 | Add 40 VMs to migration scope | Scope | 2026-06-22 | E-0006 | Submitted | 70000 | 45000 | 10 |  |  | Noah Rahimi | 25000 | Accretive | Yes | 81
CR-007 | P-1005 | Model explainability module | Scope | 2026-05-11 | E-0007 | Approved | 120000 | 95000 | 30 | 2026-06-01 | Helena Marsh | Fatima Cohen | 25000 | Accretive | No | 21
CR-008 | P-1005 | Real-time scoring latency target change | Technical | 2026-07-06 | E-0007 | Submitted | 60000 | 80000 | 20 |  |  | Fatima Cohen | -20000 | Erodes margin | Yes | 67
CR-009 | P-1005 | Data residency re-architecture | Technical | 2026-08-24 | E-0007 | Draft | 0 | 110000 | 35 |  |  | Fatima Cohen | -110000 | Erodes margin | Yes | 18
CR-010 | P-1006 | Gift card integration | Scope | 2026-04-01 | E-0009 | Approved | 40000 | 48000 | 12 | 2026-04-20 | Helena Marsh | Olivia Silva | -8000 | Erodes margin | No | 19
CR-011 | P-1006 | Extend peak-season code freeze | Schedule | 2026-07-28 | E-0009 | Rejected | 0 | 15000 | 21 | 2026-08-10 | Steering Committee | Olivia Silva | -15000 | Erodes margin | No | 13
CR-012 | P-1007 | Parent portal module | Scope | 2026-08-17 | E-0008 | Draft | 90000 | 62000 | 25 |  |  | Ethan Park | 28000 | Accretive | Yes | 25
CR-013 | P-1008 | Additional site cut-over (Calgary) | Scope | 2026-05-19 | E-0010 | Approved | 55000 | 38000 | 14 | 2026-06-02 | Helena Marsh | Arjun Baptiste | 17000 | Accretive | No | 14
CR-014 | P-1010 | French language support | Scope | 2026-05-04 | E-0007 | Approved | 30000 | 42000 | 21 | 2026-05-26 | Helena Marsh | Fatima Cohen | -12000 | Erodes margin | No | 22
CR-015 | P-1011 | eCRF vendor integration | Scope | 2026-06-08 | E-0006 | Approved | 75000 | 48000 | 0 | 2026-06-29 | Helena Marsh | Noah Rahimi | 27000 | Accretive | No | 21
CR-016 | P-1013 | Consent management APIs | Scope | 2026-01-19 | E-0004 | Approved | 95000 | 88000 | 21 | 2026-02-09 | Helena Marsh | Liam Roy | 7000 | Accretive | No | 21
CR-017 | P-1013 | Performance hardening sprint | Technical | 2026-08-03 | E-0004 | Submitted | 0 | 40000 | 10 |  |  | Liam Roy | -40000 | Erodes margin | Yes | 39
CR-018 | P-1015 | Add commercial lines to scope | Scope | 2026-05-25 | E-0009 | Approved | 150000 | 185000 | 45 | 2026-06-19 | Helena Marsh | Olivia Silva | -35000 | Erodes margin | No | 25
CR-019 | P-1016 | Second fulfilment centre | Scope | 2026-07-13 | E-0003 | Approved | 65000 | 41000 | 0 | 2026-07-27 | Helena Marsh | Aisha Tremblay | 24000 | Accretive | No | 14
CR-020 | P-1017 | Points engine vendor swap | Technical | 2026-05-18 | E-0005 | Approved | 0 | 65000 | 30 | 2026-06-08 | Helena Marsh | Mei Fraser | -65000 | Erodes margin | No | 21
CR-021 | P-1017 | Reduced launch scope (Phase 1 only) | Scope | 2026-08-26 | E-0005 | Submitted | -40000 | -25000 | -10 |  |  | Mei Fraser | -15000 | Erodes margin | Yes | 16
CR-022 | P-1019 | Payroll system integration | Scope | 2025-10-06 | E-0010 | Approved | 60000 | 52000 | 28 | 2025-10-27 | Helena Marsh | Arjun Baptiste | 8000 | Accretive | No | 21
CR-023 | P-1021 | Offline mode for field crews | Scope | 2026-06-15 | E-0010 | Rejected | 45000 | 51000 | 20 | 2026-07-06 | Steering Committee | Arjun Baptiste | -6000 | Erodes margin | No | 21

## Snapshots
SnapshotDate | ProjectID | Status | PctComplete | ActualCostToDate | CurrentBudget | EAC | ForecastMarginPct | ScheduleSlipDays | CostRAG | ScheduleRAG | MarginRAG | OverallRAG | BurnPct | SnapshotKey
2026-01-31 | P-1001 | Active | 28% | 181025.03 | 726500 | 646517.96 | 41.23% | 1 | Green | Green | Green | Green | 24.92% | 20260131-P-1001
2026-01-31 | P-1002 | Active | 5% | 30142.44 | 466100 | 602848.8 | 11.99% | 1 | Green | Green | Red | Red | 6.467% | 20260131-P-1002
2026-01-31 | P-1003 | Active | 24% | 228237.9 | 769600 | 950991.25 | 18.37% | 17 | Green | Amber | Amber | Amber | 29.66% | 20260131-P-1003
2026-01-31 | P-1006 | Active | 36% | 244237.26 | 582300 | 678436.83 | 27.83% | 4 | Green | Green | Amber | Amber | 41.94% | 20260131-P-1006
2026-01-31 | P-1008 | Active | 10% | 52657.97 | 498500 | 526579.7 | 25.83% | 2 | Green | Green | Amber | Amber | 10.56% | 20260131-P-1008
2026-01-31 | P-1010 | Active | 21% | 123108.69 | 455000 | 586231.86 | 20.24% | 11 | Green | Green | Amber | Amber | 27.06% | 20260131-P-1010
2026-01-31 | P-1013 | Active | 37% | 408346.83 | 934500 | 1103640.08 | 22% | 8 | Green | Green | Amber | Amber | 43.7% | 20260131-P-1013
2026-01-31 | P-1014 | Active | 42% | 387451.61 | 943900 | 922503.83 | 36.38% | 2 | Green | Green | Green | Green | 41.05% | 20260131-P-1014
2026-01-31 | P-1017 | Active | 4% | 26063.25 | 324000 | 324000 | 30.32% | 3 | Green | Green | Green | Green | 8.044% | 20260131-P-1017
2026-01-31 | P-1019 | Active | 91% | 548104.54 | 661200 | 602312.68 | 42.36% | 38 | Green | Amber | Green | Amber | 82.9% | 20260131-P-1019
2026-01-31 | P-1020 | Active | 48% | 180006.13 | 412900 | 375012.77 | 36.44% | 1 | Green | Green | Amber | Amber | 43.6% | 20260131-P-1020
2026-02-28 | P-1001 | Active | 36% | 236158.26 | 726500 | 655995.17 | 40.36% | 2 | Green | Green | Green | Green | 32.51% | 20260228-P-1001
2026-02-28 | P-1002 | Active | 11% | 69555.54 | 466100 | 632323.09 | 7.69% | 3 | Green | Green | Red | Red | 14.92% | 20260228-P-1002
2026-02-28 | P-1003 | Active | 30% | 279801.34 | 879600 | 932671.13 | 30.66% | 20 | Green | Amber | Amber | Amber | 31.81% | 20260228-P-1003
2026-02-28 | P-1004 | Active | 8% | 54322.53 | 738500 | 679031.62 | 41.21% | 1 | Green | Green | Green | Green | 7.356% | 20260228-P-1004
2026-02-28 | P-1006 | Active | 44% | 303819.99 | 582300 | 690499.98 | 26.54% | 4 | Green | Green | Amber | Amber | 52.18% | 20260228-P-1006
2026-02-28 | P-1008 | Active | 20% | 104887.8 | 498500 | 524439 | 26.14% | 4 | Green | Green | Amber | Amber | 21.04% | 20260228-P-1008
2026-02-28 | P-1010 | Active | 30% | 182500.37 | 455000 | 608334.57 | 17.23% | 16 | Amber | Amber | Amber | Amber | 40.11% | 20260228-P-1010
2026-02-28 | P-1011 | Active | 2% | 16660.24 | 620700 | 620700 | 36.34% | 0 | Green | Green | Amber | Amber | 2.684% | 20260228-P-1011
2026-02-28 | P-1013 | Active | 43% | 473619.52 | 1022500 | 1101440.74 | 27.06% | 9 | Green | Green | Amber | Amber | 46.32% | 20260228-P-1013
2026-02-28 | P-1014 | Active | 48% | 432981.9 | 943900 | 902045.63 | 37.79% | 2 | Green | Green | Green | Green | 45.87% | 20260228-P-1014
2026-02-28 | P-1017 | Active | 13% | 73552.84 | 324000 | 565791.08 | -21.68% | 10 | Green | Green | Red | Red | 22.7% | 20260228-P-1017
2026-02-28 | P-1019 | Active | 97% | 604081.35 | 661200 | 622764.28 | 40.41% | 42 | Green | Amber | Green | Amber | 91.36% | 20260228-P-1019
2026-02-28 | P-1020 | Active | 61% | 231452.88 | 412900 | 379430.95 | 35.69% | 2 | Green | Green | Amber | Amber | 56.06% | 20260228-P-1020
2026-02-28 | P-1021 | Active | 6% | 23095.5 | 398600 | 384925 | 38.41% | 8 | Green | Green | Green | Green | 5.794% | 20260228-P-1021
2026-03-31 | P-1001 | Active | 46% | 296718.6 | 748500 | 645040.43 | 43.17% | 2 | Green | Green | Green | Green | 39.64% | 20260331-P-1001
2026-03-31 | P-1002 | Active | 18% | 113559.1 | 466100 | 630883.89 | 7.9% | 6 | Green | Green | Red | Red | 24.36% | 20260331-P-1002
2026-03-31 | P-1003 | Active | 36% | 333911.57 | 879600 | 927532.14 | 31.04% | 23 | Green | Amber | Amber | Amber | 37.96% | 20260331-P-1003
2026-03-31 | P-1004 | Active | 17% | 111167.63 | 738500 | 653927.24 | 43.38% | 2 | Green | Green | Green | Green | 15.05% | 20260331-P-1004
2026-03-31 | P-1005 | Active | 5% | 38595.31 | 459200 | 771906.2 | -4.31% | 11 | Green | Green | Red | Red | 8.405% | 20260331-P-1005
2026-03-31 | P-1006 | Active | 54% | 369581.84 | 582300 | 684410.81 | 27.19% | 5 | Green | Green | Amber | Amber | 63.47% | 20260331-P-1006
2026-03-31 | P-1008 | Active | 32% | 183595.06 | 498500 | 573734.56 | 19.19% | 6 | Green | Green | Amber | Amber | 36.83% | 20260331-P-1008
2026-03-31 | P-1010 | Active | 41% | 242787.9 | 455000 | 592165.61 | 19.43% | 22 | Amber | Amber | Amber | Amber | 53.36% | 20260331-P-1010
2026-03-31 | P-1011 | Active | 8% | 46050.47 | 620700 | 575630.88 | 40.96% | 0 | Green | Green | Green | Green | 7.419% | 20260331-P-1011
2026-03-31 | P-1013 | Active | 51% | 554447.45 | 1022500 | 1087151.86 | 28% | 10 | Green | Green | Amber | Amber | 54.22% | 20260331-P-1013
2026-03-31 | P-1014 | Active | 54% | 480204.58 | 943900 | 889267.74 | 38.67% | 3 | Green | Green | Green | Green | 50.87% | 20260331-P-1014
2026-03-31 | P-1015 | Active | 3% | 37834.75 | 892800 | 892800 | 32.11% | 1 | Green | Green | Green | Green | 4.238% | 20260331-P-1015
2026-03-31 | P-1017 | Active | 23% | 126034.39 | 324000 | 547975.61 | -17.84% | 17 | Amber | Amber | Red | Red | 38.9% | 20260331-P-1017
2026-03-31 | P-1019 | Active | 97% | 669259.85 | 661200 | 689958.61 | 33.98% | 42 | Green | Amber | Green | Amber | 101.2% | 20260331-P-1019
2026-03-31 | P-1020 | Active | 75% | 285872.2 | 412900 | 381162.93 | 35.4% | 2 | Green | Green | Amber | Amber | 69.24% | 20260331-P-1020
2026-03-31 | P-1021 | Active | 14% | 54365.73 | 398600 | 388326.64 | 37.87% | 22 | Green | Amber | Green | Amber | 13.64% | 20260331-P-1021
2026-04-30 | P-1001 | Active | 56% | 362043.81 | 748500 | 646506.8 | 43.04% | 2 | Green | Green | Green | Green | 48.37% | 20260430-P-1001
2026-04-30 | P-1002 | Active | 25% | 177100.32 | 466100 | 708401.28 | -3.42% | 8 | Amber | Green | Red | Red | 38% | 20260430-P-1002
2026-04-30 | P-1003 | Active | 42% | 395445.81 | 879600 | 941537.64 | 30% | 27 | Green | Amber | Amber | Amber | 44.96% | 20260430-P-1003
2026-04-30 | P-1004 | Active | 26% | 167364.4 | 738500 | 643709.23 | 44.27% | 2 | Green | Green | Green | Green | 22.66% | 20260430-P-1004
2026-04-30 | P-1005 | Active | 11% | 76489.28 | 459200 | 695357.09 | 6.03% | 21 | Green | Amber | Red | Red | 16.66% | 20260430-P-1005
2026-04-30 | P-1006 | Active | 63% | 430078.31 | 630300 | 682663.98 | 30.34% | 6 | Green | Green | Amber | Amber | 68.23% | 20260430-P-1006
2026-04-30 | P-1007 | Active | 8% | 45587.42 | 639400 | 569842.75 | 41.25% | 0 | Green | Green | Green | Green | 7.13% | 20260430-P-1007
2026-04-30 | P-1008 | Active | 43% | 238384.99 | 498500 | 554383.7 | 21.92% | 8 | Green | Green | Amber | Amber | 47.82% | 20260430-P-1008
2026-04-30 | P-1010 | Active | 52% | 309014.23 | 455000 | 594258.13 | 19.15% | 27 | Amber | Amber | Amber | Amber | 67.92% | 20260430-P-1010
2026-04-30 | P-1011 | Active | 13% | 77458.23 | 620700 | 595832.54 | 38.89% | 0 | Green | Green | Green | Green | 12.48% | 20260430-P-1011
2026-04-30 | P-1013 | Active | 57% | 629259.47 | 1022500 | 1103963.98 | 26.89% | 12 | Green | Green | Amber | Amber | 61.54% | 20260430-P-1013
2026-04-30 | P-1014 | Active | 60% | 560073.19 | 943900 | 933455.32 | 35.62% | 3 | Green | Green | Green | Green | 59.34% | 20260430-P-1014
2026-04-30 | P-1015 | Active | 9% | 98289.96 | 892800 | 1092110.67 | 16.95% | 3 | Green | Green | Amber | Amber | 11.01% | 20260430-P-1015
2026-04-30 | P-1016 | Active | 8% | 19851.6 | 283700 | 248145 | 38.73% | 0 | Green | Green | Green | Green | 6.997% | 20260430-P-1016
2026-04-30 | P-1017 | Active | 33% | 178418.98 | 324000 | 540663.58 | -16.27% | 25 | Red | Amber | Red | Red | 55.07% | 20260430-P-1017
2026-04-30 | P-1019 | Completed | 100% | 699825.98 | 661200 | 699825.98 | 33.03% | 42 | Green | Amber | Green | Amber | 105.8% | 20260430-P-1019
2026-04-30 | P-1020 | Active | 89% | 335374.28 | 412900 | 376825.03 | 36.13% | 3 | Green | Green | Amber | Amber | 81.22% | 20260430-P-1020
2026-04-30 | P-1021 | Active | 22% | 104312.72 | 398600 | 474148.73 | 24.14% | 35 | Green | Amber | Amber | Amber | 26.17% | 20260430-P-1021
2026-05-31 | P-1001 | Active | 65% | 421047.63 | 748500 | 647765.58 | 42.93% | 3 | Green | Green | Green | Green | 56.25% | 20260531-P-1001
2026-05-31 | P-1002 | Active | 32% | 216623.85 | 536100 | 676949.53 | 12.08% | 10 | Green | Green | Red | Red | 40.41% | 20260531-P-1002
2026-05-31 | P-1003 | Active | 48% | 450709.44 | 879600 | 938978 | 30.19% | 30 | Green | Amber | Amber | Amber | 51.24% | 20260531-P-1003
2026-05-31 | P-1004 | Active | 35% | 255713.41 | 738500 | 730609.74 | 36.74% | 3 | Green | Green | Green | Green | 34.63% | 20260531-P-1004
2026-05-31 | P-1005 | Active | 17% | 123347.11 | 459200 | 725571.24 | 1.95% | 33 | Green | Amber | Red | Red | 26.86% | 20260531-P-1005
2026-05-31 | P-1006 | Active | 70% | 477747.36 | 630300 | 682496.23 | 30.36% | 7 | Green | Green | Amber | Amber | 75.8% | 20260531-P-1006
2026-05-31 | P-1007 | Active | 16% | 95839.3 | 639400 | 598995.62 | 38.25% | 1 | Green | Green | Green | Green | 14.99% | 20260531-P-1007
2026-05-31 | P-1008 | Active | 54% | 293069.83 | 498500 | 542721.91 | 23.56% | 10 | Green | Green | Amber | Amber | 58.79% | 20260531-P-1008
2026-05-31 | P-1009 | Active | 11% | 33623.79 | 342700 | 305670.82 | 42.87% | 1 | Green | Green | Green | Green | 9.811% | 20260531-P-1009
2026-05-31 | P-1010 | Active | 60% | 358485.72 | 497000 | 597476.2 | 21.9% | 33 | Amber | Amber | Amber | Amber | 72.13% | 20260531-P-1010
2026-05-31 | P-1011 | Active | 20% | 115287.52 | 620700 | 576437.6 | 40.88% | 0 | Green | Green | Green | Green | 18.57% | 20260531-P-1011
2026-05-31 | P-1013 | Active | 63% | 696088.71 | 1022500 | 1104902.71 | 26.83% | 13 | Green | Green | Amber | Amber | 68.08% | 20260531-P-1013
2026-05-31 | P-1014 | Active | 65% | 598242.27 | 943900 | 920372.72 | 36.53% | 3 | Green | Green | Green | Green | 63.38% | 20260531-P-1014
2026-05-31 | P-1015 | Active | 15% | 156113.47 | 892800 | 1040756.47 | 20.86% | 5 | Green | Green | Amber | Amber | 17.49% | 20260531-P-1015
2026-05-31 | P-1016 | Active | 19% | 48522.09 | 283700 | 255379.42 | 36.94% | 1 | Green | Green | Amber | Amber | 17.1% | 20260531-P-1016
2026-05-31 | P-1017 | Active | 43% | 233283.67 | 324000 | 542520.16 | -16.67% | 32 | Red | Amber | Red | Red | 72% | 20260531-P-1017
2026-05-31 | P-1020 | Active | 97% | 374977.54 | 412900 | 386574.78 | 34.48% | 3 | Green | Green | Amber | Amber | 90.82% | 20260531-P-1020
2026-05-31 | P-1021 | Active | 30% | 133955.13 | 398600 | 446517.1 | 28.56% | 49 | Green | Red | Amber | Red | 33.61% | 20260531-P-1021
2026-06-30 | P-1001 | Active | 72% | 470988.75 | 748500 | 654151.04 | 42.37% | 3 | Green | Green | Green | Green | 62.92% | 20260630-P-1001
2026-06-30 | P-1002 | Active | 40% | 267366.77 | 536100 | 668416.93 | 13.19% | 12 | Green | Green | Red | Red | 49.87% | 20260630-P-1002
2026-06-30 | P-1003 | Active | 54% | 506271.04 | 879600 | 937538.96 | 30.29% | 34 | Green | Amber | Amber | Amber | 57.56% | 20260630-P-1003
2026-06-30 | P-1004 | Active | 44% | 309298.34 | 738500 | 702950.77 | 39.14% | 4 | Green | Green | Green | Green | 41.88% | 20260630-P-1004
2026-06-30 | P-1005 | Active | 24% | 178371.84 | 554200 | 743216 | 13.58% | 44 | Green | Amber | Red | Red | 32.19% | 20260630-P-1005
2026-06-30 | P-1006 | Active | 77% | 526922.75 | 630300 | 684315.26 | 30.17% | 8 | Green | Green | Amber | Amber | 83.6% | 20260630-P-1006
2026-06-30 | P-1007 | Active | 25% | 146365.91 | 639400 | 585463.64 | 39.64% | 2 | Green | Green | Green | Green | 22.89% | 20260630-P-1007
2026-06-30 | P-1008 | Active | 65% | 359361.73 | 536500 | 552864.2 | 27.73% | 13 | Green | Green | Amber | Amber | 66.98% | 20260630-P-1008
2026-06-30 | P-1009 | Active | 24% | 68777.18 | 342700 | 286571.58 | 46.44% | 1 | Green | Green | Green | Green | 20.07% | 20260630-P-1009
2026-06-30 | P-1010 | Active | 69% | 409389.17 | 497000 | 593317.64 | 22.44% | 38 | Amber | Amber | Amber | Amber | 82.37% | 20260630-P-1010
2026-06-30 | P-1011 | Active | 27% | 160181.7 | 668700 | 593265.56 | 43.5% | 0 | Green | Green | Green | Green | 23.95% | 20260630-P-1011
2026-06-30 | P-1012 | Active | 12% | 39436.2 | 346500 | 328635 | 35.56% | 0 | Green | Green | Green | Green | 11.38% | 20260630-P-1012
2026-06-30 | P-1013 | Active | 70% | 763974.27 | 1022500 | 1091391.81 | 27.72% | 14 | Green | Green | Amber | Amber | 74.72% | 20260630-P-1013
2026-06-30 | P-1014 | Active | 71% | 641650.79 | 943900 | 903733.51 | 37.67% | 3 | Green | Green | Green | Green | 67.98% | 20260630-P-1014
2026-06-30 | P-1015 | Active | 21% | 218007 | 1077800 | 1038128.57 | 29.14% | 6 | Green | Green | Green | Green | 20.23% | 20260630-P-1015
2026-06-30 | P-1016 | Active | 32% | 88977.44 | 283700 | 278054.5 | 31.34% | 2 | Green | Green | Amber | Amber | 31.36% | 20260630-P-1016
2026-06-30 | P-1017 | Active | 52% | 282123.79 | 389000 | 542545.75 | -16.68% | 40 | Red | Amber | Red | Red | 72.53% | 20260630-P-1017
2026-06-30 | P-1020 | Completed | 100% | 376556.9 | 412900 | 376556.9 | 36.18% | 3 | Green | Green | Amber | Amber | 91.2% | 20260630-P-1020
2026-06-30 | P-1021 | Active | 39% | 166995.37 | 398600 | 428193.26 | 31.49% | 63 | Green | Red | Green | Red | 41.9% | 20260630-P-1021
2026-07-31 | P-1001 | Active | 80% | 523234.95 | 748500 | 654043.69 | 42.38% | 4 | Green | Green | Green | Green | 69.9% | 20260731-P-1001
2026-07-31 | P-1002 | Active | 49% | 333929.7 | 536100 | 681489.18 | 11.49% | 15 | Amber | Amber | Red | Red | 62.29% | 20260731-P-1002
2026-07-31 | P-1003 | Active | 60% | 562480.64 | 879600 | 937467.73 | 30.3% | 37 | Green | Amber | Amber | Amber | 63.95% | 20260731-P-1003
2026-07-31 | P-1004 | Active | 53% | 366518.4 | 738500 | 691544.15 | 40.13% | 5 | Green | Green | Green | Green | 49.63% | 20260731-P-1004
2026-07-31 | P-1005 | Active | 32% | 234472.64 | 554200 | 732727 | 14.8% | 55 | Amber | Red | Red | Red | 42.31% | 20260731-P-1005
2026-07-31 | P-1006 | Active | 85% | 577656.11 | 630300 | 679595.42 | 30.65% | 9 | Green | Green | Amber | Amber | 91.65% | 20260731-P-1006
2026-07-31 | P-1007 | Active | 34% | 199543.49 | 639400 | 586892.62 | 39.5% | 2 | Green | Green | Green | Green | 31.21% | 20260731-P-1007
2026-07-31 | P-1008 | Active | 75% | 414126.66 | 536500 | 552168.88 | 27.82% | 15 | Green | Amber | Amber | Amber | 77.19% | 20260731-P-1008
2026-07-31 | P-1009 | Active | 37% | 119221.94 | 342700 | 322221.46 | 39.77% | 2 | Green | Green | Green | Green | 34.79% | 20260731-P-1009
2026-07-31 | P-1010 | Active | 78% | 465132.51 | 497000 | 596323.73 | 22.05% | 44 | Amber | Amber | Amber | Amber | 93.59% | 20260731-P-1010
2026-07-31 | P-1011 | Active | 35% | 206547.68 | 668700 | 590136.23 | 43.8% | 0 | Green | Green | Green | Green | 30.89% | 20260731-P-1011
2026-07-31 | P-1012 | Active | 28% | 90305 | 346500 | 322517.86 | 36.76% | 0 | Green | Green | Green | Green | 26.06% | 20260731-P-1012
2026-07-31 | P-1013 | Active | 76% | 834558.23 | 1022500 | 1098102.93 | 27.28% | 16 | Green | Amber | Amber | Amber | 81.62% | 20260731-P-1013
2026-07-31 | P-1014 | Active | 76% | 684233.81 | 943900 | 900307.64 | 37.91% | 4 | Green | Green | Green | Green | 72.49% | 20260731-P-1014
2026-07-31 | P-1015 | Active | 28% | 279422.04 | 1077800 | 997935.86 | 31.88% | 8 | Green | Green | Green | Green | 25.93% | 20260731-P-1015
2026-07-31 | P-1016 | Active | 46% | 123063.38 | 324700 | 267529.09 | 43.08% | 2 | Green | Green | Green | Green | 37.9% | 20260731-P-1016
2026-07-31 | P-1017 | Active | 61% | 327714.46 | 389000 | 537236.82 | -15.53% | 47 | Red | Red | Red | Red | 84.25% | 20260731-P-1017
2026-07-31 | P-1021 | On Hold | 42% | 183595.87 | 398600 | 437133.02 | 30.06% | 76 | Green | Red | Amber | Red | 46.06% | 20260731-P-1021
2026-08-31 | P-1001 | Active | 87% | 569689.28 | 748500 | 654815.26 | 42.31% | 4 | Green | Green | Green | Green | 76.11% | 20260831-P-1001
2026-08-31 | P-1002 | Active | 57% | 382554.58 | 536100 | 671148.39 | 12.84% | 17 | Amber | Amber | Red | Red | 71.36% | 20260831-P-1002
2026-08-31 | P-1003 | Active | 66% | 614808.15 | 879600 | 931527.5 | 30.74% | 41 | Green | Amber | Amber | Amber | 69.9% | 20260831-P-1003
2026-08-31 | P-1004 | Active | 61% | 440837.72 | 738500 | 722684.79 | 37.43% | 6 | Green | Green | Green | Green | 59.69% | 20260831-P-1004
2026-08-31 | P-1005 | Active | 40% | 289303.7 | 554200 | 723259.25 | 15.9% | 66 | Amber | Red | Amber | Red | 52.2% | 20260831-P-1005
2026-08-31 | P-1006 | Active | 92% | 622397.49 | 630300 | 676519.01 | 30.97% | 10 | Green | Green | Amber | Amber | 98.75% | 20260831-P-1006
2026-08-31 | P-1007 | Active | 43% | 249953.93 | 639400 | 581288.21 | 40.07% | 3 | Green | Green | Green | Green | 39.09% | 20260831-P-1007
2026-08-31 | P-1008 | Active | 85% | 464449.86 | 536500 | 546411.6 | 28.57% | 17 | Green | Amber | Amber | Amber | 86.57% | 20260831-P-1008
2026-08-31 | P-1009 | Active | 50% | 160755.53 | 342700 | 321511.06 | 39.9% | 3 | Green | Green | Green | Green | 46.91% | 20260831-P-1009
2026-08-31 | P-1010 | Active | 86% | 513842.3 | 497000 | 597491.05 | 21.9% | 49 | Amber | Red | Amber | Red | 103.4% | 20260831-P-1010
2026-08-31 | P-1011 | Active | 42% | 248297.41 | 668700 | 591184.31 | 43.7% | 0 | Green | Green | Green | Green | 37.13% | 20260831-P-1011
2026-08-31 | P-1012 | Active | 44% | 142260.82 | 346500 | 323320.05 | 36.6% | 0 | Green | Green | Green | Green | 41.06% | 20260831-P-1012
2026-08-31 | P-1013 | Active | 82% | 899800.48 | 1022500 | 1097317.66 | 27.33% | 17 | Green | Amber | Amber | Amber | 88% | 20260831-P-1013
2026-08-31 | P-1014 | Active | 81% | 726209.58 | 943900 | 896555.04 | 38.17% | 4 | Green | Green | Green | Green | 76.94% | 20260831-P-1014
2026-08-31 | P-1015 | Active | 34% | 339750.83 | 1077800 | 999267.15 | 31.79% | 10 | Green | Green | Green | Green | 31.52% | 20260831-P-1015
2026-08-31 | P-1016 | Active | 60% | 168612.03 | 324700 | 281020.05 | 40.21% | 3 | Green | Green | Green | Green | 51.93% | 20260831-P-1016
2026-08-31 | P-1017 | Active | 70% | 371195.43 | 389000 | 530279.19 | -14.04% | 55 | Red | Red | Red | Red | 95.42% | 20260831-P-1017
2026-08-31 | P-1021 | On Hold | 42% | 183595.87 | 398600 | 437133.02 | 30.06% | 90 | Green | Red | Amber | Red | 46.06% | 20260831-P-1021

## Clients
ClientID | ClientName | Industry | Region | Tier | AccountOwner | PaymentTermsDays | ActiveProjects | LifetimeContractValue | OutstandingAR
C-101 | Northgate Health Network | Healthcare | Ontario | Strategic | Priya Nair | 45 | 1 | 1135000 | 0
C-102 | Crestline Insurance | Insurance | Ontario | Strategic | Marcus Bell | 30 | 2 | 2235000 | 0
C-103 | Maple Ridge Financial | Banking | Ontario | Strategic | Priya Nair | 30 | 2 | 2855000 | 186173.67
C-104 | Harbourview Logistics | Transportation | British Columbia | Key | Daniel Okafor | 45 | 3 | 3075000 | 404879.8
C-105 | Ironbridge Capital | Capital Markets | Ontario | Key | Marcus Bell | 30 | 1 | 1375000 | 0
C-106 | Aurora Retail Group | Retail | Quebec | Key | Sophie Tremblay | 60 | 2 | 1445000 | 702500
C-107 | Pinecrest University | Education | Ontario | Standard | Daniel Okafor | 60 | 1 | 2015000 | 194000
C-108 | Summit Telecom | Telecommunications | Alberta | Key | Sophie Tremblay | 45 | 1 | 1385000 | 76883.12
C-109 | Granite Manufacturing | Manufacturing | Ontario | Standard | Daniel Okafor | 45 | 1 | 1125000 | 0
C-110 | Bluewater Municipal Services | Public Sector | Ontario | Standard | Priya Nair | 60 | 1 | 1855000 | 220500
C-111 | Evergreen Pharma | Life Sciences | Quebec | Strategic | Marcus Bell | 45 | 1 | 1570000 | 152372.33
C-112 | Lakeshore Energy | Utilities | Ontario | Key | Sophie Tremblay | 30 | 1 | 1135000 | 0

## Settings
Setting | Value | Unit | Description
AsOfDate | 2026-09-11 | date | Reporting date every formula measures against. Replace with =TODAY() for live use.
ActualsCutoff | 2026-08-31 | date | Last closed accounting period loaded into Actuals.
RAG_CostAmber | 10% | pts | Cost Amber when BudgetBurnPct exceeds PctComplete by more than this.
RAG_CostRed | 20% | pts | Cost Red when BudgetBurnPct exceeds PctComplete by more than this.
RAG_ScheduleAmberDays | 14 | days | Schedule Amber when forecast slip exceeds this many days.
RAG_ScheduleRedDays | 45 | days | Schedule Red when forecast slip exceeds this many days.
MarginFloor | 15% | % | Margin Red below this forecast margin.
MarginTolerance | 5% | pts | Margin Amber when forecast is more than this below target.
OverallocationThreshold | 100% | % | Person is Overallocated above this total allocation.
UnderutilizationThreshold | 60% | % | Person is Under-utilized below this total allocation.
RiskCriticalScore | 15 | score | RiskScore at or above = Critical.
RiskHighScore | 10 | score | RiskScore at or above = High.
RiskMediumScore | 5 | score | RiskScore at or above = Medium (else Low).
MilestoneAtRiskDays | 14 | days | Milestone At Risk when forecast slips more than this vs baseline.
BudgetNearLimit | 90% | % | Budget line flagged Near limit at or above this burn.
Contingency_High | 5% | % | Contingency applied to High-confidence estimate lines.
Contingency_Medium | 10% | % | Contingency applied to Medium-confidence estimate lines.
Contingency_Low | 15% | % | Contingency applied to Low-confidence estimate lines.
Currency | CAD | code | Reporting currency (informational).
AutoRefreshMinutes | 10 | min | Polling interval the web app should use (informational).

## DataDictionary
Table | Sheet | Column | Kind | DataType | Description
tbl_Projects | Projects | ProjectID | Input | Text | Primary key. Every other table joins on this.
tbl_Projects | Projects | ProjectName | Input | Text | Project display name.
tbl_Projects | Projects | ClientID | Input | Text | FK to Clients.ClientID.
tbl_Projects | Projects | ClientName | Lookup | Text | Client name (lookup).
tbl_Projects | Projects | Portfolio | Input | Text | Portfolio grouping used for roll-ups and the bubble matrix.
tbl_Projects | Projects | BusinessUnit | Input | Text | Owning business unit.
tbl_Projects | Projects | ProjectManagerID | Input | Text | FK to Resources.EmployeeID.
tbl_Projects | Projects | ProjectManager | Lookup | Text | Project manager name (lookup).
tbl_Projects | Projects | ExecutiveSponsor | Input | Text | Client-side executive sponsor.
tbl_Projects | Projects | Status | Input | Text | Planned / Active / On Hold / Completed.
tbl_Projects | Projects | Phase | Input | Text | Current delivery phase.
tbl_Projects | Projects | Priority | Input | Text | P1 (highest) to P3.
tbl_Projects | Projects | ContractType | Input | Text | Fixed Price / Time & Materials / Retainer.
tbl_Projects | Projects | StrategicScore | Input | Integer | 1-10 strategic value score from portfolio governance.
tbl_Projects | Projects | BaselineStart | Input | Date | Approved start date.
tbl_Projects | Projects | BaselineEnd | Input | Date | Approved finish date (baseline).
tbl_Projects | Projects | ForecastEnd | Input | Date | PM's current forecast finish date.
tbl_Projects | Projects | OriginalContractValue | Input | Currency | Signed revenue at contract award (CAD). For T&M/Retainer = forecast revenue at award.
tbl_Projects | Projects | TargetMarginPct | Input | Percent (fraction) | Target gross margin agreed at bid.
tbl_Projects | Projects | PctComplete | Input | Percent (fraction) | PM-reported physical % complete (drives earned value).
tbl_Projects | Projects | LastStatusUpdate | Input | Date | Date the PM last updated status.
tbl_Projects | Projects | ApprovedCRRevenue | Formula | Currency | Revenue added by Approved change requests.
tbl_Projects | Projects | CurrentContractValue | Formula | Currency | OriginalContractValue + ApprovedCRRevenue.
tbl_Projects | Projects | BaselineBudget | Formula | Currency | Sum of Budget lines for the project (incl. contingency).
tbl_Projects | Projects | ApprovedCRCost | Formula | Currency | Cost added by Approved change requests.
tbl_Projects | Projects | CurrentBudget | Formula | Currency | Budget at completion (BAC) = BaselineBudget + ApprovedCRCost.
tbl_Projects | Projects | ActualHours | Formula | Decimal | Timesheet hours booked to date.
tbl_Projects | Projects | ActualCost | Formula | Currency | Actual cost (AC) to date from the Actuals ledger.
tbl_Projects | Projects | ElapsedPct | Formula | Percent (fraction) | Share of baseline duration elapsed at AsOfDate.
tbl_Projects | Projects | EarnedValue | Formula | Currency | EV = PctComplete x BAC.
tbl_Projects | Projects | PlannedValue | Formula | Currency | PV (time-based) = ElapsedPct x BAC.
tbl_Projects | Projects | CPI | Formula | Ratio | Cost performance index = EV / AC (1.00 when no actuals). <1 = over cost.
tbl_Projects | Projects | SPI | Formula | Ratio | Schedule performance index = EV / PV (1.00 when not started). <1 = behind.
tbl_Projects | Projects | EAC | Formula | Currency | Estimate at completion. Completed = AC; <5% complete = MAX(BAC, AC); else AC / PctComplete.
tbl_Projects | Projects | ETC | Formula | Currency | Estimate to complete = EAC - AC.
tbl_Projects | Projects | VAC | Formula | Currency | Variance at completion = BAC - EAC (negative = overrun).
tbl_Projects | Projects | BudgetBurnPct | Formula | Percent (fraction) | AC / BAC.
tbl_Projects | Projects | ForecastMarginAmt | Formula | Currency | CurrentContractValue - EAC.
tbl_Projects | Projects | ForecastMarginPct | Formula | Percent (fraction) | ForecastMarginAmt / CurrentContractValue.
tbl_Projects | Projects | MarginVsTarget | Formula | Percent (fraction) | ForecastMarginPct - TargetMarginPct (percentage points).
tbl_Projects | Projects | ScheduleSlipDays | Formula | Integer (days) | ForecastEnd - BaselineEnd in calendar days.
tbl_Projects | Projects | DaysRemaining | Formula | Integer (days) | Calendar days from AsOfDate to ForecastEnd (0 if completed).
tbl_Projects | Projects | InvoicedToDate | Formula | Currency | Sum of invoices raised.
tbl_Projects | Projects | CollectedToDate | Formula | Currency | Sum of invoices with Status = Paid.
tbl_Projects | Projects | UnbilledWIP | Formula | Currency | Earned revenue not yet invoiced = PctComplete x CurrentContractValue - InvoicedToDate.
tbl_Projects | Projects | OpenRisks | Formula | Integer | RAID items of Type = Risk not Closed.
tbl_Projects | Projects | OpenIssues | Formula | Integer | RAID items of Type = Issue not Closed.
tbl_Projects | Projects | OpenRiskExposure | Formula | Currency | Probability-weighted exposure of open RAID items.
tbl_Projects | Projects | PendingCRs | Formula | Integer | Change requests in Draft or Submitted.
tbl_Projects | Projects | TeamSize | Formula | Integer | People with an assignment active on AsOfDate.
tbl_Projects | Projects | NextMilestoneDate | Formula | Date | Earliest forecast date among incomplete milestones (blank if none).
tbl_Projects | Projects | CostRAG | Formula | Text | Burn minus progress gap vs RAG_CostAmber / RAG_CostRed.
tbl_Projects | Projects | ScheduleRAG | Formula | Text | ScheduleSlipDays vs RAG_ScheduleAmberDays / RAG_ScheduleRedDays.
tbl_Projects | Projects | MarginRAG | Formula | Text | Red below MarginFloor; Amber below Target - MarginTolerance.
tbl_Projects | Projects | OverallRAG | Formula | Text | Worst of Cost, Schedule and Margin RAG.
tbl_Projects | Projects | HealthScore | Formula | Integer | 0-100 composite: 100 - 150 x overburn gap - 0.4 x slip days - 150 x margin shortfall. Blank if Planned.
tbl_Resources | Resources | EmployeeID | Input | Text | Primary key for a person.
tbl_Resources | Resources | FullName | Input | Text | Display name.
tbl_Resources | Resources | Role | Input | Text | Job role; used for staffing and rate cards.
tbl_Resources | Resources | Department | Input | Text | Home department.
tbl_Resources | Resources | Level | Input | Text | Career level L2-L7.
tbl_Resources | Resources | Location | Input | Text | Primary work location.
tbl_Resources | Resources | EmploymentType | Input | Text | FTE or Contractor (contractors carry a higher cost rate).
tbl_Resources | Resources | CostRateHr | Input | Currency | Fully loaded internal cost per hour (CAD).
tbl_Resources | Resources | BillRateHr | Input | Currency | Standard client bill rate per hour (CAD). 0 = non-billable.
tbl_Resources | Resources | WeeklyCapacityHrs | Input | Integer | Contracted hours per week. 0 = not assignable (leadership).
tbl_Resources | Resources | ManagerID | Input | Text | FK to Resources.EmployeeID of line manager.
tbl_Resources | Resources | ManagerName | Lookup | Text | Line manager name (lookup).
tbl_Resources | Resources | PrimarySkill | Input | Text | Headline skill for search and staffing.
tbl_Resources | Resources | StartDate | Input | Date | Hire / contract start date.
tbl_Resources | Resources | CurrentAllocationPct | Formula | Percent (fraction) | Sum of allocation % across assignments active on AsOfDate. >100% = overallocated.
tbl_Resources | Resources | ActiveAssignments | Formula | Integer | Number of assignments active on AsOfDate.
tbl_Resources | Resources | AvailableHrsPerWeek | Formula | Decimal | Unallocated weekly hours = capacity x (1 - allocation).
tbl_Resources | Resources | UtilizationStatus | Formula | Text | Overallocated / Healthy / Under-utilized / Non-assignable, using Settings thresholds.
tbl_Resources | Resources | HoursLoggedYTD | Formula | Decimal | Timesheet hours logged since 1 Jan of the AsOfDate year.
tbl_Resources | Resources | BillableHoursYTD | Formula | Decimal | Billable subset of HoursLoggedYTD.
tbl_Resources | Resources | BillableRatioYTD | Formula | Percent (fraction) | BillableHoursYTD / HoursLoggedYTD.
tbl_Allocations | Allocations | AllocationID | Input | Text | Primary key for a staffing assignment.
tbl_Allocations | Allocations | ProjectID | Input | Text | FK to Projects.
tbl_Allocations | Allocations | ProjectName | Lookup | Text | Lookup.
tbl_Allocations | Allocations | EmployeeID | Input | Text | FK to Resources.
tbl_Allocations | Allocations | EmployeeName | Lookup | Text | Lookup.
tbl_Allocations | Allocations | ProjectRole | Input | Text | Role this person plays on this project.
tbl_Allocations | Allocations | Billable | Input | Text | Yes / No - whether hours are billable to the client.
tbl_Allocations | Allocations | StartDate | Input | Date | Assignment start.
tbl_Allocations | Allocations | EndDate | Input | Date | Assignment end (current plan, includes re-plans).
tbl_Allocations | Allocations | AllocationPct | Input | Percent (fraction) | Share of the person's weekly capacity (0.25 = 25%).
tbl_Allocations | Allocations | IsActive | Formula | Text | Yes if AsOfDate falls within Start-End.
tbl_Allocations | Allocations | WorkingDays | Formula | Integer | NETWORKDAYS between Start and End.
tbl_Allocations | Allocations | PlannedHours | Formula | Decimal | WorkingDays x (WeeklyCapacityHrs / 5) x AllocationPct.
tbl_Allocations | Allocations | CostRateHr | Lookup | Currency | Lookup from Resources.
tbl_Allocations | Allocations | BillRateHr | Lookup | Currency | Lookup from Resources.
tbl_Allocations | Allocations | PlannedCost | Formula | Currency | PlannedHours x CostRateHr.
tbl_Allocations | Allocations | PlannedRevenue | Formula | Currency | PlannedHours x BillRateHr when Billable.
tbl_Allocations | Allocations | ActualHours | Formula | Decimal | Hours this person booked to this project (Actuals).
tbl_Allocations | Allocations | HoursBurnPct | Formula | Percent (fraction) | ActualHours / PlannedHours.
tbl_Estimates | Estimates | EstimateLineID | Input | Text | Primary key for an estimate line.
tbl_Estimates | Estimates | ProjectID | Input | Text | FK to Projects.
tbl_Estimates | Estimates | EstimateVersion | Input | Text | v1 Baseline or v2 Re-forecast.
tbl_Estimates | Estimates | IsCurrent | Input | Text | Yes = the version currently in force for this project.
tbl_Estimates | Estimates | WBSCode | Input | Text | Work breakdown structure code.
tbl_Estimates | Estimates | Phase | Input | Text | Delivery phase.
tbl_Estimates | Estimates | Workstream | Input | Text | Workstream owning the effort.
tbl_Estimates | Estimates | EstimatedHours | Input | Integer | Estimated effort hours.
tbl_Estimates | Estimates | BlendedCostRate | Input | Currency | Blended team cost rate per hour.
tbl_Estimates | Estimates | Confidence | Input | Text | High / Medium / Low - sets the contingency %.
tbl_Estimates | Estimates | EstimatedByID | Input | Text | FK to Resources (estimator).
tbl_Estimates | Estimates | EstimateDate | Input | Date | Date the estimate was produced.
tbl_Estimates | Estimates | EstimatedBy | Lookup | Text | Lookup.
tbl_Estimates | Estimates | ContingencyPct | Formula | Percent (fraction) | From Settings by Confidence.
tbl_Estimates | Estimates | BaseCost | Formula | Currency | EstimatedHours x BlendedCostRate.
tbl_Estimates | Estimates | ContingencyAmt | Formula | Currency | BaseCost x ContingencyPct.
tbl_Estimates | Estimates | TotalEstimate | Formula | Currency | BaseCost + ContingencyAmt.
tbl_Budget | Budget | BudgetLineID | Input | Text | Primary key.
tbl_Budget | Budget | ProjectID | Input | Text | FK to Projects.
tbl_Budget | Budget | ProjectName | Lookup | Text | Lookup.
tbl_Budget | Budget | CostCategory | Input | Text | Labour, Cloud Hosting, Hardware, Software & Licences, Subcontractors, Training, Travel & Expenses, Contingency.
tbl_Budget | Budget | BudgetAmount | Input | Currency | Approved budget (CAD).
tbl_Budget | Budget | ApprovedDate | Input | Date | Approval date.
tbl_Budget | Budget | ApprovedBy | Input | Text | Approver.
tbl_Budget | Budget | Notes | Input | Text | Free text.
tbl_Budget | Budget | ActualToDate | Formula | Currency | Actuals for this project + category.
tbl_Budget | Budget | Remaining | Formula | Currency | BudgetAmount - ActualToDate.
tbl_Budget | Budget | BurnPct | Formula | Percent (fraction) | ActualToDate / BudgetAmount.
tbl_Budget | Budget | LineStatus | Formula | Text | Reserve / Overspent / Near limit / Within budget.
tbl_Actuals | Actuals | ActualID | Input | Text | Primary key for a ledger line.
tbl_Actuals | Actuals | Period | Input | Date | Accounting period (month-end date).
tbl_Actuals | Actuals | ProjectID | Input | Text | FK to Projects.
tbl_Actuals | Actuals | CostCategory | Input | Text | Matches Budget.CostCategory.
tbl_Actuals | Actuals | EmployeeID | Input | Text | FK to Resources for Labour lines; blank otherwise.
tbl_Actuals | Actuals | Vendor | Input | Text | Supplier for non-labour lines.
tbl_Actuals | Actuals | Source | Input | Text | Timesheet / AP Invoice / Expense Claim.
tbl_Actuals | Actuals | Hours | Input | Decimal | Hours (Labour only).
tbl_Actuals | Actuals | Billable | Input | Text | Yes / No.
tbl_Actuals | Actuals | Amount | Input | Currency | Cost amount (CAD).
tbl_Actuals | Actuals | PeriodLabel | Formula | Text | yyyy-mm label for grouping.
tbl_Actuals | Actuals | Portfolio | Lookup | Text | Project portfolio (lookup) for roll-ups.
tbl_Actuals | Actuals | BillableValue | Formula | Currency | Hours x BillRateHr when Billable = Yes.
tbl_Milestones | Milestones | MilestoneID | Input | Text | Primary key.
tbl_Milestones | Milestones | ProjectID | Input | Text | FK to Projects.
tbl_Milestones | Milestones | MilestoneName | Input | Text | Milestone name.
tbl_Milestones | Milestones | Phase | Input | Text | Phase the milestone closes.
tbl_Milestones | Milestones | BaselineDate | Input | Date | Baseline due date.
tbl_Milestones | Milestones | ForecastDate | Input | Date | Current forecast date.
tbl_Milestones | Milestones | ActualDate | Input | Date | Date achieved (blank if not yet).
tbl_Milestones | Milestones | IsBillingMilestone | Input | Text | Yes if achieving it triggers an invoice.
tbl_Milestones | Milestones | BillingPct | Input | Percent (fraction) | Share of original contract value invoiced at this milestone.
tbl_Milestones | Milestones | BillingAmount | Formula | Currency | BillingPct x OriginalContractValue.
tbl_Milestones | Milestones | VarianceDays | Formula | Integer (days) | (Actual or Forecast) - Baseline, in days.
tbl_Milestones | Milestones | Status | Formula | Text | Completed / Overdue / At Risk / On Track.
tbl_Milestones | Milestones | Invoiced | Formula | Text | Yes if an invoice references this milestone.
tbl_Invoices | Invoices | InvoiceID | Input | Text | Primary key.
tbl_Invoices | Invoices | ProjectID | Input | Text | FK to Projects.
tbl_Invoices | Invoices | MilestoneID | Input | Text | FK to Milestones (Fixed Price) - blank for T&M / Retainer.
tbl_Invoices | Invoices | InvoiceDate | Input | Date | Issue date.
tbl_Invoices | Invoices | Description | Input | Text | Invoice description.
tbl_Invoices | Invoices | Amount | Input | Currency | Invoice amount excl. tax (CAD).
tbl_Invoices | Invoices | PaidDate | Input | Date | Date payment received (blank if unpaid).
tbl_Invoices | Invoices | ClientName | Lookup | Text | Lookup via Projects.
tbl_Invoices | Invoices | PaymentTermsDays | Lookup | Integer | Lookup via Projects > Clients.
tbl_Invoices | Invoices | DueDate | Formula | Date | InvoiceDate + PaymentTermsDays.
tbl_Invoices | Invoices | Status | Formula | Text | Paid / Overdue / Outstanding.
tbl_Invoices | Invoices | DaysOutstanding | Formula | Integer | Days from invoice to payment (or to AsOfDate if unpaid).
tbl_Invoices | Invoices | DaysOverdue | Formula | Integer | Days past due for Overdue invoices.
tbl_Invoices | Invoices | AgingBucket | Formula | Text | Paid / Current / 1-30 / 31-60 / 60+.
tbl_RAID | RAID | RAIDID | Input | Text | Primary key.
tbl_RAID | RAID | ProjectID | Input | Text | FK to Projects.
tbl_RAID | RAID | Type | Input | Text | Risk / Issue / Dependency / Assumption.
tbl_RAID | RAID | Category | Input | Text | Risk category.
tbl_RAID | RAID | Title | Input | Text | Short description.
tbl_RAID | RAID | Probability | Input | Integer | 1 (rare) to 5 (certain). Issues are 5.
tbl_RAID | RAID | Impact | Input | Integer | 1 (minor) to 5 (severe).
tbl_RAID | RAID | CostExposure | Input | Currency | Cost if the item fully materialises (CAD).
tbl_RAID | RAID | OwnerID | Input | Text | FK to Resources.
tbl_RAID | RAID | Status | Input | Text | Open / Mitigating / Closed.
tbl_RAID | RAID | RaisedDate | Input | Date | Date logged.
tbl_RAID | RAID | TargetDate | Input | Date | Target resolution date.
tbl_RAID | RAID | Mitigation | Input | Text | Mitigation / response plan.
tbl_RAID | RAID | OwnerName | Lookup | Text | Lookup.
tbl_RAID | RAID | RiskScore | Formula | Integer | Probability x Impact (1-25).
tbl_RAID | RAID | Severity | Formula | Text | Critical / High / Medium / Low from Settings score bands.
tbl_RAID | RAID | ExpectedExposure | Formula | Currency | CostExposure x Probability / 5.
tbl_RAID | RAID | DaysOpen | Formula | Integer | AsOfDate - RaisedDate for items not Closed.
tbl_RAID | RAID | PastTarget | Formula | Text | Yes if not Closed and past TargetDate.
tbl_ChangeRequests | ChangeRequests | CRID | Input | Text | Primary key.
tbl_ChangeRequests | ChangeRequests | ProjectID | Input | Text | FK to Projects.
tbl_ChangeRequests | ChangeRequests | Title | Input | Text | Change description.
tbl_ChangeRequests | ChangeRequests | CRType | Input | Text | Scope / Technical / Schedule / Budget.
tbl_ChangeRequests | ChangeRequests | RaisedDate | Input | Date | Date raised.
tbl_ChangeRequests | ChangeRequests | RaisedByID | Input | Text | FK to Resources.
tbl_ChangeRequests | ChangeRequests | Status | Input | Text | Draft / Submitted / Approved / Rejected. Only Approved flows into Projects.
tbl_ChangeRequests | ChangeRequests | RevenueImpact | Input | Currency | Change to contract value (CAD).
tbl_ChangeRequests | ChangeRequests | CostImpact | Input | Currency | Change to budget (CAD).
tbl_ChangeRequests | ChangeRequests | ScheduleImpactDays | Input | Integer (days) | Change to end date in days.
tbl_ChangeRequests | ChangeRequests | DecisionDate | Input | Date | Approval / rejection date.
tbl_ChangeRequests | ChangeRequests | DecisionBy | Input | Text | Approver or board.
tbl_ChangeRequests | ChangeRequests | RaisedBy | Lookup | Text | Lookup.
tbl_ChangeRequests | ChangeRequests | MarginImpact | Formula | Currency | RevenueImpact - CostImpact.
tbl_ChangeRequests | ChangeRequests | MarginEffect | Formula | Text | Accretive / Neutral / Erodes margin.
tbl_ChangeRequests | ChangeRequests | IsPending | Formula | Text | Yes if Draft or Submitted.
tbl_ChangeRequests | ChangeRequests | DaysInReview | Formula | Integer | Decision - Raised, or AsOfDate - Raised if pending.
tbl_Snapshots | Snapshots | SnapshotDate | Input | Date | Month-end snapshot date. Append-only history for trend charts.
tbl_Snapshots | Snapshots | ProjectID | Input | Text | FK to Projects.
tbl_Snapshots | Snapshots | Status | Input | Text | Status at snapshot.
tbl_Snapshots | Snapshots | PctComplete | Input | Percent (fraction) | % complete at snapshot.
tbl_Snapshots | Snapshots | ActualCostToDate | Input | Currency | AC at snapshot.
tbl_Snapshots | Snapshots | CurrentBudget | Input | Currency | BAC at snapshot.
tbl_Snapshots | Snapshots | EAC | Input | Currency | EAC at snapshot.
tbl_Snapshots | Snapshots | ForecastMarginPct | Input | Percent (fraction) | Forecast margin at snapshot.
tbl_Snapshots | Snapshots | ScheduleSlipDays | Input | Integer (days) | Slip at snapshot.
tbl_Snapshots | Snapshots | CostRAG | Input | Text | RAG at snapshot.
tbl_Snapshots | Snapshots | ScheduleRAG | Input | Text | RAG at snapshot.
tbl_Snapshots | Snapshots | MarginRAG | Input | Text | RAG at snapshot.
tbl_Snapshots | Snapshots | OverallRAG | Input | Text | RAG at snapshot.
tbl_Snapshots | Snapshots | BurnPct | Formula | Percent (fraction) | ActualCostToDate / CurrentBudget.
tbl_Snapshots | Snapshots | SnapshotKey | Formula | Text | Composite key yyyymmdd-ProjectID.
tbl_Clients | Clients | ClientID | Input | Text | Primary key for a client account.
tbl_Clients | Clients | ClientName | Input | Text | Legal/trading name of the client.
tbl_Clients | Clients | Industry | Input | Text | Client industry vertical.
tbl_Clients | Clients | Region | Input | Text | Province / region of the client's head office.
tbl_Clients | Clients | Tier | Input | Text | Account tier: Strategic, Key or Standard.
tbl_Clients | Clients | AccountOwner | Input | Text | Internal account executive.
tbl_Clients | Clients | PaymentTermsDays | Input | Integer | Contractual payment terms in days; drives invoice due dates.
tbl_Clients | Clients | ActiveProjects | Formula | Integer | Count of this client's projects with Status = Active.
tbl_Clients | Clients | LifetimeContractValue | Formula | Currency | Sum of current contract value across all this client's projects.
tbl_Clients | Clients | OutstandingAR | Formula | Currency | Unpaid invoice total for this client.